## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH | Harischandrapur-II | Malda Division | Sharanpur Piped Water Supply Scheme | SM/12631 | New | Material Requisition To Resource Division |  |  | RTOR000036/2022-2023 | 3048/MD | 12/12/2022 | 12/12/2022 | Resource Division | 17.95 | 0 | 0 | 0
2 | MALDAH | Harischandrapur-II | Malda Division | Sharanpur Piped Water Supply Scheme | SM/12631 | New | Acceptance cum formal work order for Sinking of 250mm. Dia. x 150 mm. Big dia. and 135 Mtr. deep Tube Well Drilling by Direct Rotary method with 150 mm dia upvc strainer of 30m length all complete including cost of materials at Heads Work Site of SHARANPUR Piped Water Supply Scheme at Harishchandrapur-II Block of Malda District under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer |  | ORD/000368/2022-2023 | 2697/MD | 17/11/2022 | 17/12/2022 | ASHIS CONSTRUCTION | 9.2 | 8.85 | 96.1 | 0
3 | MALDAH | Harischandrapur-II | Malda Mechanical | Sharanpur Piped Water Supply Scheme | SM/12631 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. I of Sharanpur PWSS, Kushida C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II |  | ORD/000302/2023-2024 | 3004302713 | 21/07/2023 | 19/10/2023 | W.B.S.E.D.C.LTD | 7.5 | 7.5 | 100 | 100
4 | MALDAH | Harischandrapur-II | Malda Mechanical | Sharanpur Piped Water Supply Scheme | SM/12631 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. II of Sharanpur, Kushida C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II |  | ORD/000421/2023-2024 | 3004368694 | 28/07/2023 | 26/10/2023 | W.B.S.E.D.C.LTD | 3.49 | 3.49 | 100 | 100
5 | MALDAH | Harischandrapur-II | Malda Division | Sharanpur Piped Water Supply Scheme | SM/12631 | New | Material Requisition To Resource Division |  |  | RTOR000001/2023-2024 | 1581 | 10/04/2023 | 10/04/2023 | Resource Division | 6.65 | 0 | 0 | 0
6 | MALDAH | Harischandrapur-II | Malda Division | Sharanpur Piped Water Supply Scheme | SM/12631 | New | Material Requisition To Resource Division |  |  | RTOR000015/2023-2024 | 1617/MD | 11/04/2023 | 11/04/2023 | Resource Division | 6.65 | 0 | 0 | 0
7 | MALDAH | Harischandrapur-II | Malda Division | Sharanpur Piped Water Supply Scheme | SM/12631 | New | Acceptance cum formal work order for Sinking of 250mm. Dia. x 150 mm. dia. and 150 Mtr. Deep Big dia Tube well (1 No) at SAHARANPUR Water Supply Scheme under Harishchandrapur-II Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Susanta Pal, JE_Deputation | ORD/000607/2022-2023 | 925/MD | 27/02/2023 | 12/08/2023 | DUTTA ENTERPRISE | 10.13 | 8.9 | 87.86 | 100
8 | MALDAH | Harischandrapur-II | Malda Division | Sharanpur Piped Water Supply Scheme | SM/12631 | New | Formal work order for the work of Implementation of SHARANPUR Water Supply Scheme at Harishchandrapur-II Block of Malda district under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Susanta Pal, JE_Deputation | ORD/000587/2022-2023 | 825/MD | 21/02/2023 | 30/12/2025 | M/S DAS CONSTRUCTION | 189.29 | 91.35 | 48.26 | 85
9 | MALDAH | Harischandrapur-II | Malda Mechanical | Sharanpur Piped Water Supply Scheme | SM/12631 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I ,II and making compound lighting arrangement at T/W no. I of Sharanpur Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/013210) | Assistant Engineer - II | Junior Engineer-05 | ORD/000736/2023-2024 | 2798/MLMD | 17/08/2023 | 01/01/2025 | SHREE BISHNU CONSTRUCTION | 22.93 | 21.91 | 95.53 | 100
10 | MALDAH | Harischandrapur-II | Malda Division | Sharanpur Piped Water Supply Scheme | SM/12631 | New | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Sharanpur Water Supply Scheme under Harishchandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Susanta Pal, JE_Deputation,Mr. Tilok Roy, Junior Engineer | ORD/000297/2024-2025 | 3443/MD | 11/07/2024 | 01/09/2025 | M/S DAS CONSTRUCTION | 22.19 | 0 | 0 | 70
11 | MALDAH | Harischandrapur-II | Malda Division | Sharanpur Piped Water Supply Scheme | SM/12631 | New | Construction of Boundary Wall at 2nd Tube Well site of Sharanpur Water Supply Scheme under Harishchandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer ,Mr. Susanta Pal, JE_Deputation | ORD/000184/2024-2025 | 2959/MD | 10/06/2024 | 01/02/2025 | M/S DAS CONSTRUCTION | 9.32 | 0 | 0 | 0
12 | MALDAH | Harischandrapur-II | Malda Division | Sharanpur Piped Water Supply Scheme | SM/12631 | New | Construction of Boundary Wall at Head Work site of Sharanpur Water Supply Scheme under Harishchandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Susanta Pal, JE_Deputation | ORD/000578/2024-2025 | 5550/MD | 29/10/2024 | 01/01/2026 | M/S DAS CONSTRUCTION | 31.36 | 0 | 0 | 70
13 | MALDAH | Harischandrapur-II | Malda Division | Sharanpur Piped Water Supply Scheme | SM/12631 | New | Erection of Property board related to Jal Jeevan Mission works of Malipakar, Dakhin Gouripur, Arjuna & Sharanpur PWSS under Harishchandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Debasis Pal, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000962/2024-2025 | 651/MD | 19/02/2025 | 26/02/2025 | M/S SABANA CONSTRUCTION | 0.9 | 0 | 0 | 100
14 | MALDAH | Harischandrapur-II | Malda Division | Sharanpur Piped Water Supply Scheme | SM/12631 | New | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Sharanpur Water Supply Scheme under Harishchandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Susanta Pal, JE_Deputation | ORD/000096/2025-2026 | 2338/MD | 22/05/2025 | 31/12/2025 | M/S DAS CONSTRUCTION | 31.48 | 0 | 0 | 0
Total | [13 empty] | 369.06 | 142 | 38.48