## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH | Harischandrapur-II | Malda Division | CHHATRAK PWSS at Harishchandrapur-II of Malda Division PHE Dte. | SM/12632 | New | Material Requisition To Resource Division |  |  | RTOR000035/2022-2023 | 3047/MD | 12/12/2022 | 12/12/2022 | Resource Division | 19.68 | 0 | 0 | 0
2 | MALDAH | Harischandrapur-II | Malda Division | CHHATRAK PWSS at Harishchandrapur-II of Malda Division PHE Dte. | SM/12632 | New | Acceptance cum formal work order for Sinking of 250mm. Dia. x 150 mm. Big dia. and 135 Mtr. deep Tube Well Drilling by Direct Rotary method with 150 mm dia upvc strainer of 30m length all complete including cost of materials at Heads Work Site of CHHATRAK Piped Water Supply Scheme at Harishchandrapur-II Block of Malda District under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer |  | ORD/000369/2022-2023 | 2698/MD | 17/11/2022 | 17/12/2022 | MERCURY ENGINEERING COMPANY | 9.2 | 0 | 0 | 0
3 | MALDAH | Harischandrapur-II | Malda Mechanical | CHHATRAK PWSS at Harishchandrapur-II of Malda Division PHE Dte. | SM/12632 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of Chhatrak PWSS, Harishchandrapur C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II |  | ORD/000092/2023-2024 | 3004232695 | 17/05/2023 | 15/08/2023 | W.B.S.E.D.C.LTD | 5.3 | 0 | 0 | 0
4 | MALDAH | Harischandrapur-II | Malda Mechanical | CHHATRAK PWSS at Harishchandrapur-II of Malda Division PHE Dte. | SM/12632 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. I of CHHATRAK PWSS, Kushida C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II |  | ORD/000301/2023-2024 | 3004302727 | 21/07/2023 | 19/10/2023 | W.B.S.E.D.C.LTD | 8.02 | 0 | 0 | 100
5 | MALDAH | Harischandrapur-II | Malda Division | CHHATRAK PWSS at Harishchandrapur-II of Malda Division PHE Dte. | SM/12632 | New | Material Requisition To Resource Division |  |  | RTOR000016/2023-2024 | 1613/MD | 11/04/2023 | 11/04/2023 | Resource Division | 4.3 | 0 | 0 | 0
6 | MALDAH | Harischandrapur-II | Malda Division | CHHATRAK PWSS at Harishchandrapur-II of Malda Division PHE Dte. | SM/12632 | New | Material Requisition To Resource Division |  |  | RTOR000002/2023-2024 | 1584/MD | 10/04/2023 | 10/04/2023 | Resource Division | 4.3 | 0 | 0 | 0
7 | MALDAH | Harischandrapur-II | Malda Division | CHHATRAK PWSS at Harishchandrapur-II of Malda Division PHE Dte. | SM/12632 | New | Formal work order for the work of Implementation of CHHATRAK Water Supply Scheme at Harishchandrapur-I Block of Malda district under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000594/2022-2023 | 875/MD | 22/02/2023 | 01/10/2026 | M/S TRILOCHAN CONSTRUCTION CO | 150.77 | 0 | 0 | 90
8 | MALDAH | Harischandrapur-II | Malda Mechanical | CHHATRAK PWSS at Harishchandrapur-II of Malda Division PHE Dte. | SM/12632 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I ,II and making compound lighting arrangement at T/W no. I of Chhatrak Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/012833) | Assistant Engineer - II | Junior Engineer-05 | ORD/000027/2023-2024 | 786/MLMD | 27/04/2023 | 27/10/2025 | M/S S. S. ENTERPRISE | 25.16 | 0 | 0 | 85
9 | MALDAH | Harischandrapur-II | Malda Division | CHHATRAK PWSS at Harishchandrapur-II of Malda Division PHE Dte. | SM/12632 | New | Construction of Boundary Wall at 2nd Tubewell site of Chhatrak Water Supply Scheme under Harishchandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000213/2024-2025 | 3034/MD | 13/06/2024 | 13/07/2024 | BIDYUT MAHALDAR | 10.41 | 0 | 0 | 0
10 | MALDAH | Harischandrapur-II | Malda Division | CHHATRAK PWSS at Harishchandrapur-II of Malda Division PHE Dte. | SM/12632 | New | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Chhatrak Water Supply Scheme under Harishchandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000480/2024-2025 | 4995/MD | 27/09/2024 | 11/11/2024 | BIDYUT MAHALDAR | 14.99 | 0 | 0 | 0
11 | MALDAH | Harischandrapur-II | Malda Division | CHHATRAK PWSS at Harishchandrapur-II of Malda Division PHE Dte. | SM/12632 | New | Material Requisition To Resource Division |  |  | RTOR000019/2024-2025 | 3995/MD | 08/08/2024 | 08/08/2024 | Resource Division | 2.22 | 0 | 0 | 0
12 | MALDAH | Harischandrapur-II | Malda Division | CHHATRAK PWSS at Harishchandrapur-II of Malda Division PHE Dte. | SM/12632 | New | Acceptance cum formal work order for Sinking of 250mm. Dia. x 150 mm. dia. and 150 Mtr. Deep Big dia Tube well (1 No) at CHHATRAK Water Supply Scheme under Harishchandrapur-II Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000606/2022-2023 | 924/MD | 27/02/2023 | 29/03/2023 | SAUDAGAR INDIA | 10.13 | 0 | 0 | 0
13 | MALDAH | Harischandrapur-II | Malda Division | CHHATRAK PWSS at Harishchandrapur-II of Malda Division PHE Dte. | SM/12632 | New | Construction of Boundary Wall at Head Work site of Chhatrak Water Supply Scheme under Harischandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000212/2024-2025 | 3033/MD | 13/06/2024 | 01/12/2025 | M/S TRILOCHAN CONSTRUCTION CO | 26.65 | 0 | 0 | 75
Total | [13 empty] | 291.12 | 0 | 0