## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Malda Division | Augmentation of Jatradanga Piped water supply scheme | SM/12734 | Augmentation | Acceptance cum formal work order for Construction of 3.60 Mtr. X 3.00 Mtr. Bore Hole Pump House for Tube Well No. 3 of JATRADANGA Water Supply Scheme under Malda Division, PHE Dte. | Mr. Prosanta Mandal, Assistant Engineer | Mr. Sujit Sarkar, Junior Engineer | ORD/000241/2020-2021 | 3228MD | 28/12/2020 | 26/02/2021 | M/S A. B. CONSTRUCTION | 4.74 | 4.74 | 100 | 1
2 | MALDAH |  | Malda Division | Augmentation of Jatradanga Piped water supply scheme | SM/12734 | Augmentation | Acceptance cum formal work order for Design, Preparation & Submission of DPR as per existing route survey data for Augmentation of JATRADANGA Piped Water Supply Scheme under Malda Division, PHE Dte. | Mr. Prosanta Mandal, Assistant Engineer | Mr. Sujit Sarkar, Junior Engineer | ORD/000541/2021-2022 | 2695/MD | 09/09/2021 | 16/09/2021 | RADIANT | 1.25 | 1.24 | 98.65 | 1
3 | MALDAH |  | Malda Division | Augmentation of Jatradanga Piped water supply scheme | SM/12734 | Augmentation | Acceptance cum formal work order for Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement at 2nd Tube Well site. of JATRADANGA Water Supply Scheme at Old Malda Block of Malda District under Malda Division, PHE Dte. | Mr. Prosanta Mandal, Assistant Engineer | Mr. Sujit Sarkar, Junior Engineer | ORD/000485/2022-2023 | 1133/MD | 20/03/2023 | 04/05/2023 | M/S KAMALA ENTERPRISE | 4.16 | 0 | 0 | 0
4 | MALDAH |  | Malda Mechanical | Augmentation of Jatradanga Piped water supply scheme | SM/12734 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II of Augmentation of Jatradanga Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/010498) | Assistant Engineer - II | Junior Engineer-07 | ORD/000250/2023-2024 | 2221/MLMD | 18/07/2023 | 16/10/2023 | JOY MAA SANTOSHI ENTERPRISE. | 6.42 | 0 | 0 | 0
5 | MALDAH |  | Malda Division | Augmentation of Jatradanga Piped water supply scheme | SM/12734 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000029/2023-2024 | 1809/MD | 27/04/2023 | 27/04/2023 | Resource Division | 6.98 | 0 | 0 | 0
6 | MALDAH |  | Malda Division | Augmentation of Jatradanga Piped water supply scheme | SM/12734 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000051/2023-2024 | 1811/MD | 27/04/2023 | 27/04/2023 | Resource Division | 66.49 | 0 | 0 | 0
7 | MALDAH |  | Malda Division | Augmentation of Jatradanga Piped water supply scheme | SM/12734 | Augmentation | Formal work order for the work of Augmentation of JATRADANGA Piped Water Supply Scheme at Old Malda Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Mr. Amit Biswas, Assistant Engineer,Mr. Prosanta Mandal, Assistant Engineer | Bikash Balo, Junior Engineer | ORD/000293/2023-2024 | 2830/MD | 25/07/2023 | 20/04/2024 | M/S KUNDU CONSTRUCTION | 171.22 | 70.94 | 41.43 | 53
Total | [13 empty] | 261.26 | 76.91 | 29.44