## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Malda Division | Procurement of chemicals, Instruments and glassware including OMAS Consumables and Annual Computer Maintenance and peripherals of both PHED & NGO managed laboratories under Malda Division, PHE Dte. | SM/12741 | Support-WQMSP | Acceptance cum formal work order for Annual Maintence Contract (AMC) for software upgradation, other software related issues in existing computers, refilling of cartridge of the printers, replacement of battery of UPS and other related peripherals in 8 nos. i.e. District, Sub-District & NGO Laboratories under Malda Division, PHE Dte. in the district of Malda, (Period from 01/09/2020 to 31/08/2021). | Mr. Amit Biswas, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000046/2020-2021 | 1906/MD | 26/08/2020 | 26/08/2021 | DIGITAL CONSULTANTS | 1.2 | 1.2 | 100 | 0
2 | MALDAH |  | Malda Division | Procurement of chemicals, Instruments and glassware including OMAS Consumables and Annual Computer Maintenance and peripherals of both PHED & NGO managed laboratories under Malda Division, PHE Dte. | SM/12741 | Support-WQMSP | Acceptance cum formal work order for Engagement of resource person for operation of Double Beam Atomic Absorption Spectrophotometer (AAS) in the Malda district water testing laboratory situated in Malda district under Malda Division, PHE Dte. (Period from 01/07/2021 to 30/06/2022). | Mr. Amit Biswas, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000198/2021-2022 | 1882/MD | 30/06/2021 | 30/06/2022 | M/S JHA CONSTRUCTION | 2.55 | 2.55 | 100 | 0
3 | MALDAH |  | Malda Division | Procurement of chemicals, Instruments and glassware including OMAS Consumables and Annual Computer Maintenance and peripherals of both PHED & NGO managed laboratories under Malda Division, PHE Dte. | SM/12741 | Support-WQMSP | Acceptance cum formal work order for Maintenance of Malda District Laboratory PHE Dte. under Malda Division PHE Dte. (Period From 01/09/2021 to 31/08/2022). | Mr. Amit Biswas, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000378/2021-2022 | 2554/MD | 31/08/2021 | 31/08/2022 | M/S AMIT KUMAR GUPTA | 0.99 | 0.99 | 100 | 0
4 | MALDAH |  | Malda Division | Procurement of chemicals, Instruments and glassware including OMAS Consumables and Annual Computer Maintenance and peripherals of both PHED & NGO managed laboratories under Malda Division, PHE Dte. | SM/12741 | Support-WQMSP | Acceptance cum formal work order for Requirements of Chemicals, Reagents & glasswares for smooth running of Water Tesings for 1. Chanchal SD Laboratory 2. Balupur SD Laboratory 3. Sanskriti o samaj unnayan parishad SD Laboratory under Malda Division, PHE Dte. of Malda District. | Mr. Amit Biswas, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000447/2021-2022 | 3092/MD | 29/10/2021 | 13/11/2021 | LAXMI ENTERPRISE | 20.69 | 20.69 | 100 | 0
5 | MALDAH |  | Malda Division | Procurement of chemicals, Instruments and glassware including OMAS Consumables and Annual Computer Maintenance and peripherals of both PHED & NGO managed laboratories under Malda Division, PHE Dte. | SM/12741 | Support-WQMSP | Acceptance cum formal work order for Supply of spares for AAS 3500 & for hydride generator of AAS of malda district laboratory under Malda Division, PHE Dte. | Mr. Amit Biswas, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000430/2021-2022 | 2913/MD | 28/09/2021 | 08/10/2021 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 2.87 | 2.87 | 100 | 0
6 | MALDAH |  | Malda Division | Procurement of chemicals, Instruments and glassware including OMAS Consumables and Annual Computer Maintenance and peripherals of both PHED & NGO managed laboratories under Malda Division, PHE Dte. | SM/12741 | Support-WQMSP | Acceptance cum formal work order for Requirements of Chemicals, Reagents & glasswares for smooth running of Water Tesings for 1. Malda District Laboratory 2. Paschim Banga Vigyan Mancha SD Laboratory 3. Community polytechnic cell SD Laboratory 4. Gazole SD Laboratory 5. Bulbulchandi SD Laboratory under Malda Division, PHE Dte. of Malda District. | Mr. Amit Biswas, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000429/2021-2022 | 2912/MD | 28/09/2021 | 13/10/2021 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 33.9 | 33.9 | 100 | 0
7 | MALDAH |  | Malda Division | Procurement of chemicals, Instruments and glassware including OMAS Consumables and Annual Computer Maintenance and peripherals of both PHED & NGO managed laboratories under Malda Division, PHE Dte. | SM/12741 | Support-WQMSP | Acceptance cum formal work order for Supply, installation, demonstration, training of all laboratory requirement including assigning resource person for guidance to prepare required documents, records & performing internal calibration, clearing non-compliances related to NABL recognition as a composite work in connection for NABL Accreditation of Chanchal Sub-District Laboratories under Malda Division, PHE Dte., Malda. | Mr. Amit Biswas, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000397/2021-2022 | 2682/MD | 08/09/2021 | 07/11/2021 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 4.88 | 4.55 | 93.14 | 0
8 | MALDAH |  | Malda Division | Procurement of chemicals, Instruments and glassware including OMAS Consumables and Annual Computer Maintenance and peripherals of both PHED & NGO managed laboratories under Malda Division, PHE Dte. | SM/12741 | Support-WQMSP | Acceptance cum formal work order for Procurement of consumables for On-site Mobile Analysis System (OMAS) at 1) Malda District Laboratory, 2) Gazole Sub-District Laboratory, 3) Chanchal Sub-District Laboratory, 4) Community Polytechnic Cell Sub-District Laboratory & 5) Sanskrity - O - Samaj Unnayan Parishad Sub-District Laboratory for water quality testing under Malda Division, PHE Dte. | Mr. Amit Biswas, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000649/2021-2022 | 625/MD | 15/03/2022 | 05/04/2022 | SAKTI ENTERPRISE | 12.9 | 12.9 | 100 | 0
9 | MALDAH |  | Malda Division | Procurement of chemicals, Instruments and glassware including OMAS Consumables and Annual Computer Maintenance and peripherals of both PHED & NGO managed laboratories under Malda Division, PHE Dte. | SM/12741 | Support-WQMSP | Supply of 13 Nos. Chemicals, Glassware and Installation of the pre-requisites needed for successful application & recognition from NABL for 11 mandatory water quality parameters of Mobile Laboratory Van stationed in Maldah District under PHE Department, Govt. of West Bengal. | Mr. Amit Biswas, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000385/2023-2024 | 3247/MD | 22/08/2023 | 06/09/2023 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD. | 0.63 | 0 | 0 | 0
10 | MALDAH |  | Malda Division | Procurement of chemicals, Instruments and glassware including OMAS Consumables and Annual Computer Maintenance and peripherals of both PHED & NGO managed laboratories under Malda Division, PHE Dte. | SM/12741 | Support-WQMSP | Supply & Delivery of Spare for AAS, consumables for AAS, chemicals and allied work required for maintaining NABL for Malda District water testing Laboratory under The Executive Engineer, Malda Division, PHE Dte. | Mr. Amit Biswas, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000386/2023-2024 | 3248/MD | 22/08/2023 | 29/08/2023 | LAXMI ENTERPRISE | 2.28 | 0 | 0 | 0
11 | MALDAH |  | Malda Division | Procurement of chemicals, Instruments and glassware including OMAS Consumables and Annual Computer Maintenance and peripherals of both PHED & NGO managed laboratories under Malda Division, PHE Dte. | SM/12741 | Support-WQMSP | Supply of 52 Nos. Chemicals, Glassware and Installation of the pre-requisites needed for successful application & recognition from NABL for 11 mandatory water quality parameters of Mobile Laboratory Van stationed in Maldah District under PHE Department, Govt. of West Bengal. | Mr. Amit Biswas, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000384/2023-2024 | 3246/MD | 22/08/2023 | 06/09/2023 | LAXMI ENTERPRISE | 1.21 | 0 | 0 | 0
12 | MALDAH |  | Malda Division | Procurement of chemicals, Instruments and glassware including OMAS Consumables and Annual Computer Maintenance and peripherals of both PHED & NGO managed laboratories under Malda Division, PHE Dte. | SM/12741 | Support-WQMSP | Engagement of Chemist, Bacteriologist and Laboratory Assistant including related upkeeping works for Sanskrity-O-Samaj Unnayan Parishad Sub-District Laboratory under Malda Division, PHE Dte. In the district of Malda. (Period from 01/10/2023 to 31/03/2024). | Mr. Amit Biswas, Assistant Engineer |  | ORD/000565/2023-2024 | 3806/MD | 29/09/2023 | 30/03/2024 | GOBINDA ENTERPRISE | 2.84 | 0 | 0 | 0
13 | MALDAH |  | Malda Division | Procurement of chemicals, Instruments and glassware including OMAS Consumables and Annual Computer Maintenance and peripherals of both PHED & NGO managed laboratories under Malda Division, PHE Dte. | SM/12741 | Support-WQMSP | Continuation work order for Engagement of Chemist, Bacteriologist and Laboratory Assistant including related upkeeping works for Sahapur Sub-District Laboratory (erstwhile PBVM) under Malda Division, PHE Dte. in the district of Malda. (Period from 01/07/2023 to 30/09/2023). | Mr. Amit Biswas, Assistant Engineer | Bikash Balo, Junior Engineer | ORD/000210/2023-2024 | 2315/MD | 08/06/2023 | 08/09/2023 | M/S MAA TARA ENTERPRISE | 1.42 | 1.42 | 100 | 100
14 | MALDAH |  | Malda Division | Procurement of chemicals, Instruments and glassware including OMAS Consumables and Annual Computer Maintenance and peripherals of both PHED & NGO managed laboratories under Malda Division, PHE Dte. | SM/12741 | Support-WQMSP | Engagement and providing arrear of Bacteriologist at Chanchal Sub-District Laboratory, Gazol Sub-District Laboratory and Bulbulchandi Sub-District Laboratory under Malda Division, PHE Dte. in the district of Malda. (Period from 01/06/2023 to 30/09/2023). | Mr. Amit Biswas, Assistant Engineer,Mr. Arnab Giri, Assistant Engineer,Mr. Sumit Kumar Ghosh, Assistant Engineer |  | ORD/000359/2023-2024 | 3022/MD | 08/08/2023 | 08/12/2023 | NABODAYA MULTIPURPOSE CO-OPERATIVE SOCIETY LTD. | 2.6 | 2.16 | 83.33 | 100
15 | MALDAH |  | Malda Division | Procurement of chemicals, Instruments and glassware including OMAS Consumables and Annual Computer Maintenance and peripherals of both PHED & NGO managed laboratories under Malda Division, PHE Dte. | SM/12741 | Support-WQMSP | Acceptance cum formal work order for Engagement of personnel for testing, entry and collection of water for Malda District water Testing Laboratory under Malda Division, PHE Dte. in the district of Malda. (Period From 01/03/2022 to 31/08/2022). | Mr. Amit Biswas, Assistant Engineer,Mr. Debasis Pal, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000628/2021-2022 | 495/MD | 28/02/2022 | 06/03/2022 | SUDEB KARMAKAR | 3.55 | 3.55 | 100 | 100
16 | MALDAH |  | Malda Division | Procurement of chemicals, Instruments and glassware including OMAS Consumables and Annual Computer Maintenance and peripherals of both PHED & NGO managed laboratories under Malda Division, PHE Dte. | SM/12741 | Support-WQMSP | Acceptance cum formal work order for Payment of Enhanced Rate for Lab Personnel in Gazole and Manikchak Sub-District Laboratories under Malda Division, PHE Dte. | Mr. Amit Biswas, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000070/2023-2024 | 121/RWS | 22/05/2023 | 22/08/2024 | NABODAYA MULTIPURPOSE CO-OPERATIVE SOCIETY LTD. | 3.83 | 2.05 | 53.33 | 60
17 | MALDAH |  | Malda Division | Procurement of chemicals, Instruments and glassware including OMAS Consumables and Annual Computer Maintenance and peripherals of both PHED & NGO managed laboratories under Malda Division, PHE Dte. | SM/12741 | Support-WQMSP | Acceptance cum Formal Work Order for Payment of Enhanced Rate for Lab Personnel in Malda District Laboratory under Malda Division, PHE Dte. | Mr. Amit Biswas, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000073/2023-2024 | 124/RWS | 22/05/2023 | 22/08/2024 | NABODAYA MULTIPURPOSE CO-OPERATIVE SOCIETY LTD. | 4.33 | 2.31 | 53.33 | 60
18 | MALDAH |  | Malda Division | Procurement of chemicals, Instruments and glassware including OMAS Consumables and Annual Computer Maintenance and peripherals of both PHED & NGO managed laboratories under Malda Division, PHE Dte. | SM/12741 | Support-WQMSP | Acceptance cum work order for Payment of Enhanced Rate for Lab Personnel in Bulbulchandi and Chanchal Sub-District Laboratories under Malda Division, PHE Dte. | Mr. Amit Biswas, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000071/2023-2024 | 122/RWS | 22/05/2023 | 22/08/2024 | NABODAYA MULTIPURPOSE CO-OPERATIVE SOCIETY LTD. | 3.44 | 1.57 | 45.71 | 60
19 | MALDAH |  | Malda Division | Procurement of chemicals, Instruments and glassware including OMAS Consumables and Annual Computer Maintenance and peripherals of both PHED & NGO managed laboratories under Malda Division, PHE Dte. | SM/12741 | Support-WQMSP | Acceptance cum Formal Work Order for Payment of Enhanced Rate for Lab Personnel in Sahapur and Balupur Sub-District Laboratories under Malda Division, PHE Dte | Mr. Amit Biswas, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000074/2023-2024 | 125/RWS | 22/05/2023 | 22/08/2024 | NABODAYA MULTIPURPOSE CO-OPERATIVE SOCIETY LTD. | 4.72 | 2.52 | 53.33 | 60
20 | MALDAH |  | Malda Division | Procurement of chemicals, Instruments and glassware including OMAS Consumables and Annual Computer Maintenance and peripherals of both PHED & NGO managed laboratories under Malda Division, PHE Dte. | SM/12741 | Support-WQMSP | Acceptance cum work order for Payment of Enhanced Rate for Lab Personnel in Sanskrity-O-Samaj Unnayan Parishad Sub-District Laboratory under Malda Division, PHE Dte. | Mr. Amit Biswas, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000072/2023-2024 | 123/RWS | 22/05/2023 | 22/08/2024 | NABODAYA MULTIPURPOSE CO-OPERATIVE SOCIETY LTD. | 2.36 | 1.26 | 53.33 | 65
21 | MALDAH |  | Malda Division | Procurement of chemicals, Instruments and glassware including OMAS Consumables and Annual Computer Maintenance and peripherals of both PHED & NGO managed laboratories under Malda Division, PHE Dte. | SM/12741 | Support-WQMSP | Continuation work order for Engagement of Chemist, Bacteriologist and Laboratory Assistant including related upkeeping works for Manikchak Sub-District Laboratory (erstwhile CDTP) under Malda Division, PHE Dte. in the district of Malda. (Period from 01/07/2023 to 30/09/2023). | Mr. Amit Biswas, Assistant Engineer | Rahul Das Biswas, Junior Engineer | ORD/000211/2023-2024 | 2316/MD | 08/06/2023 | 08/09/2023 | NABODAYA MULTIPURPOSE CO-OPERATIVE SOCIETY LTD. | 1.42 | 1.42 | 100 | 100
22 | MALDAH |  | Malda Division | Procurement of chemicals, Instruments and glassware including OMAS Consumables and Annual Computer Maintenance and peripherals of both PHED & NGO managed laboratories under Malda Division, PHE Dte. | SM/12741 | Support-WQMSP | Engagement of Chemist, Bacteriologist and Laboratory Assistant including related upkeeping works for Sahapur Sub-District Laboratory (erstwhile PBVM) under Malda Division, PHE Dte. in the district of Malda. (Period from 01/10/2023 to 31/03/2024). | Mr. Amit Biswas, Assistant Engineer | Bikash Balo, Junior Engineer | ORD/000550/2023-2024 | 3721/MD | 26/09/2023 | 27/03/2024 | M/S RAKHI ENTERPRISE | 2.84 | 2.84 | 100 | 100
23 | MALDAH |  | Malda Division | Procurement of chemicals, Instruments and glassware including OMAS Consumables and Annual Computer Maintenance and peripherals of both PHED & NGO managed laboratories under Malda Division, PHE Dte. | SM/12741 | Support-WQMSP | Engagement of Chemist, Bacteriologist and Laboratory Assistant including related upkeeping works for Balupur WTP Sub-District Laboratory under Malda Division, PHE Dte. in the district of Malda. (Period from 01/10/2023 to 31/03/2024). | Mr. Amit Biswas, Assistant Engineer | Tapan Haldar, Junior Engineer | ORD/000553/2023-2024 | 3724/MD | 26/09/2023 | 27/03/2024 | M/S RAKHI ENTERPRISE | 2.84 | 2.84 | 100 | 100
24 | MALDAH |  | Malda Division | Procurement of chemicals, Instruments and glassware including OMAS Consumables and Annual Computer Maintenance and peripherals of both PHED & NGO managed laboratories under Malda Division, PHE Dte. | SM/12741 | Support-WQMSP | Engagement of Chemist, Bacteriologist and Laboratory Assistant including related upkeeping works for Bulbulchandi Sub-District Laboratory under Malda Division, PHE Dte. In the district of Malda. (Period from 01/10/2023 to 31/03/2024). | Mr. Amit Biswas, Assistant Engineer,Mr. Arnab Giri, Assistant Engineer | Mukaddar Parvage, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | ORD/000555/2023-2024 | 3726/MD | 26/09/2023 | 27/03/2024 | S. N. CONSTRUCTION | 3.19 | 3.09 | 96.74 | 100
25 | MALDAH |  | Malda Division | Procurement of chemicals, Instruments and glassware including OMAS Consumables and Annual Computer Maintenance and peripherals of both PHED & NGO managed laboratories under Malda Division, PHE Dte. | SM/12741 | Support-WQMSP | Acceptance cum formal work order for Engagement of resource person for supervising the protocol / standard operating procedures/ technical documentation of laboratory water testing activities as per ISO/IEC 17025:2017 including performing statutory internal audit, refresher training course and any other required laboratory management process and allied works to comply NABL accreditation system of Malda District Laboratory under Malda Division, PHE Dte. for a period of 06 (six) months. | Mr. Amit Biswas, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000591/2022-2023 | 873/MD | 22/02/2023 | 21/08/2023 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 5.5 | 5.5 | 100 | 100
26 | MALDAH |  | Malda Division | Procurement of chemicals, Instruments and glassware including OMAS Consumables and Annual Computer Maintenance and peripherals of both PHED & NGO managed laboratories under Malda Division, PHE Dte. | SM/12741 | Support-WQMSP | Repairing of Samsi Sub-District Laboratory under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Amit Biswas, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000946/2023-2024 | 658/MD | 08/02/2024 | 24/03/2024 | M/S FOUR STAR CONSTRUCTION | 3.68 | 3.65 | 99.12 | 100
27 | MALDAH |  | Malda Division | Procurement of chemicals, Instruments and glassware including OMAS Consumables and Annual Computer Maintenance and peripherals of both PHED & NGO managed laboratories under Malda Division, PHE Dte. | SM/12741 | Support-WQMSP | Continuation work order for maintenance of Bulbulchandi Sub-District Laboratory under Malda Division, PHE Dte.for 06(Six) months.(Period from 06/01/2024 to 30/06/2024) | Mr. Amit Biswas, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000968/2023-2024 | 437/RWS | 29/11/2023 | 29/05/2024 | NABODAYA MULTIPURPOSE CO-OPERATIVE SOCIETY LTD. | 0.37 | 0.36 | 95.86 | 100
28 | MALDAH |  | Malda Division | Procurement of chemicals, Instruments and glassware including OMAS Consumables and Annual Computer Maintenance and peripherals of both PHED & NGO managed laboratories under Malda Division, PHE Dte. | SM/12741 | Support-WQMSP | Continuation work order for Engagement of Chemist, Bacteriologist and Laboratory Assistant including related upkeeping works for Bulbulchandi Sub-District Laboratory under Malda Division, PHE Dte. In the district of Malda. (Period from 01/04/2024 to 30/09/2024). | Mr. Amit Biswas, Assistant Engineer | Sumit Kumar Ganguly, Junior Engineer | ORD/001111/2023-2024 | 1372/MD | 15/03/2024 | 14/09/2024 | S. N. CONSTRUCTION | 2.98 | 0 | 0 | 100
29 | MALDAH |  | Malda Division | Procurement of chemicals, Instruments and glassware including OMAS Consumables and Annual Computer Maintenance and peripherals of both PHED & NGO managed laboratories under Malda Division, PHE Dte. | SM/12741 | Support-WQMSP | Continuation work order for Engagement of Chemist, Bacteriologist and Laboratory Assistant including related upkeeping works for Manikchak Sub-District Laboratory (erstwhile CDTP) under Malda Division, PHE Dte. In the district of Malda. (Period from 01/04/2024 to 30/09/2024). | Mr. Amit Biswas, Assistant Engineer | Rahul Das Biswas, Junior Engineer | ORD/001130/2023-2024 | 1368/MD | 15/03/2024 | 14/09/2024 | NABODAYA MULTIPURPOSE CO-OPERATIVE SOCIETY LTD | 2.63 | 2.63 | 100 | 100
30 | MALDAH |  | Malda Division | Procurement of chemicals, Instruments and glassware including OMAS Consumables and Annual Computer Maintenance and peripherals of both PHED & NGO managed laboratories under Malda Division, PHE Dte. | SM/12741 | Support-WQMSP | Acceptance cum formal work order for Engagement of Chemist/Bacteriologist and Laboratory Assistant for testing, entry and collection, of New Water Testing Laboratory of GAZOLE Water Supply Scheme under Malda Division, PHE Dte. in the district of Malda. (Period from 01/10/2022 to 30/09/2023). | Mr. Arnab Giri, Assistant Engineer | Amit Karmakar, Junior Engineer | ORD/000329/2022-2023 | 2361/MD | 29/09/2022 | 29/09/2023 | M/S MAHABIR ENTERPRISE | 3.9 | 3.9 | 100 | 100
Total | [13 empty] | 142.55 | 122.7 | 86.07