## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH | Harischandrapur-I | Malda Mechanical | BAIRAT Piped Water Supply Scheme | SM/12743 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. II of BAIRAT ,Harishchandrapur C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II |  | ORD/000293/2023-2024 | 3004353764 | 17/07/2023 | 15/10/2023 | W.B.S.E.D.C.LTD | 9.45 | 9.45 | 100 | 100
2 | MALDAH | Harischandrapur-I | Malda Mechanical | BAIRAT Piped Water Supply Scheme | SM/12743 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of Bairat, Harishchandrapur C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II |  | ORD/000636/2023-2024 | 3004353771 | 08/08/2023 | 06/11/2023 | W.B.S.E.D.C.LTD | 4.51 | 4.51 | 100 | 100
3 | MALDAH | Harischandrapur-I | Malda Division | BAIRAT Piped Water Supply Scheme | SM/12743 | New | Material Requisition To Resource Division |  |  | RTOR000058/2023-2024 | 1811/MD | 27/04/2023 | 27/04/2023 | Resource Division | 27.83 | 0 | 0 | 0
4 | MALDAH | Harischandrapur-I | Malda Mechanical | BAIRAT Piped Water Supply Scheme | SM/12743 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Bairat Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/014439) | Assistant Engineer - II | Junior Engineer-05 | ORD/000374/2023-2024 | 2382/MLMD | 28/07/2023 | 11/06/2026 | M/S. KUNDU CONSTRACTION | 27.77 | 23.81 | 85.73 | 86
5 | MALDAH | Harischandrapur-I | Malda Division | BAIRAT Piped Water Supply Scheme | SM/12743 | New | Material Requisition To Resource Division |  |  | RTOR000107/2023-2024 | 37/MD | 04/01/2024 | 04/01/2024 | Resource Division | 16.2 | 0 | 0 | 0
6 | MALDAH | Harischandrapur-I | Malda Division | BAIRAT Piped Water Supply Scheme | SM/12743 | New | Formal work order for the work of Implementation of BAIRAT Piped Water Supply Scheme at Harishchandrapur-I Dev. Block of Malda District under Malda Division, PHE Dte. Govt. of West Bengal. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000534/2022-2023 | 581/MD | 09/02/2023 | 01/09/2025 | USHA ENTERPRISE | 732.14 | 589.95 | 80.58 | 79
7 | MALDAH | Harischandrapur-I | Malda Division | BAIRAT Piped Water Supply Scheme | SM/12743 | New | Construction of Boundary Wall at Head Work site of Bairat Water Supply Scheme under Harishchandrapur-I Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000884/2023-2024 | 160/MD | 08/01/2024 | 01/04/2025 | USHA ENTERPRISE | 21.58 | 0 | 0 | 70
8 | MALDAH | Harischandrapur-I | Malda Division | BAIRAT Piped Water Supply Scheme | SM/12743 | New | Design, Supplying, Fabrication, Erection & Commissioning including 3 (three) months Trial Run of 80m³/hr. capacity Pressure type IRON ELIMINATION Plant with Construction of Blower room & backwash water disposal at head work site of Bairat Water Supply Scheme of Harishchandrapur-I Dev. Block under Malda Division P.H.E Dte in the District of Malda. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000132/2025-2026 | 2506/MD | 29/05/2025 | 11/10/2025 | USHA ENTERPRISE | 31.65 | 0 | 0 | 0
9 | MALDAH | Harischandrapur-I | Malda Division | BAIRAT Piped Water Supply Scheme | SM/12743 | New | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Bairat Water Supply Scheme under Harishchandrapur-I Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000094/2025-2026 | 2336/MD | 22/05/2025 | 21/07/2025 | MAHA MAYA CONSTRUCTION | 26.17 | 0 | 0 | 0
Total | [13 empty] | 897.31 | 627.72 | 69.96