## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Malda Division | Source Augmentation of Basara Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/12760 | Augmentation | Acceptance cum formal work order for Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement in connection with source Augmentation of Basara Piped Water Supply Scheme at Bamangola Block of Malda District under Malda Division, PHE Dte. | Mr. Arnab Giri, Assistant Engineer | Ramen Karmakar, Junior Engineer | ORD/000728/2022-2023 | 1202/MD | 21/03/2023 | 05/05/2023 | M.S. ENTERPRISE | 4.17 | 0 | 0 | 0
2 | MALDAH |  | Malda Division | Source Augmentation of Basara Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/12760 | Augmentation | Acceptance cum formal work order for Sinking of (200mm. Dia. x 150 mm. dia.) Big dia. Tube Well (120 Mtr. Deep) by D.R. Rig method using P.V.C. pipe and Gravel Filter including supply of Materials at BASARA Piped Water Supply Scheme (Tube Well No-3) of Malda District under Malda Division, PHE Dte. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000835/2022-2023 | 2706/MD | 17/11/2022 | 17/12/2022 | RATAN CHANDRA SARKAR | 6.81 | 0 | 0 | 0
3 | MALDAH |  | Central Drilling | Source Augmentation of Basara Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/12760 | Augmentation | Resistivity survey for Sankail PWSS, Basara PWSS and Pannapur PWSS at Habibipur & Bamongola block under Malda district, CMSD-II (D), CDD, PHE Dte. |  |  | ORD/000012/2023-2024 | 135/CMSD-II(D) | 24/05/2023 | 08/06/2023 | S B S ENTERPRISE | 0.82 | 0.27 | 33.33 | 100
4 | MALDAH |  | Malda Division | Source Augmentation of Basara Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/12760 | Augmentation | Sinking of ( 200 mm Dia. X 150 mm Dia.) Tube well No.-4 (250 M deep) by D.R Rig. Method using P.V.C. Pipe & Gravel Filter including Supply of materials at BASARA Water Supply Scheme of Bamongola Block under Malda Division, P.H.E Dte in the District of Malda. | Mr. Amit Biswas, Assistant Engineer | Mukaddar Parvage, Junior Engineer | ORD/000919/2023-2024 | 380/MD | 17/01/2024 | 02/03/2024 | A. L. ENGINEERING SOLUTION | 12.74 | 0 | 0 | 100
5 | MALDAH |  | Malda Division | Source Augmentation of Basara Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/12760 | Augmentation | Acceptance cum formal work order for Extension of Pipe line and replacing of damage A.C /upvc pipe line by different dia UPVC pipe for BASARA Piped Water Supply Scheme at Bamangola Dev. Block in the District of Malda under Malda Division, PHE Dte. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000413/2022-2023 | 2987/MD | 07/12/2022 | 30/06/2025 | M/S JHA CONSTRUCTION | 81.06 | 0 | 0 | 100
6 | MALDAH |  | Malda Mechanical | Source Augmentation of Basara Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/12760 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. IV of Basara Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/015035) | Assistant Engineer - II | Junior Engineer-03 | ORD/000310/2023-2024 | 2312/MLMD | 26/07/2023 | 11/01/2025 | JOY ENTERPRISE. | 11.01 | 3.92 | 35.59 | 22
7 | MALDAH |  | Malda Division | Source Augmentation of Basara Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/12760 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Bujurkhali, Harinandanbati & Chandipur Mouza of Basara Water Supply Scheme under Bamongola Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000783/2024-2025 | 349/MD | 30/01/2025 | 02/05/2025 | DHRITIPALI | 21.06 | 0 | 0 | 0
8 | MALDAH |  | Malda Division | Source Augmentation of Basara Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/12760 | Augmentation | Construction of Boundary Wall of Basara Water Supply Scheme under Bamongola Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000486/2024-2025 | 4999/MD | 27/09/2024 | 01/02/2025 | JOY GURU ENTERPRISE | 10.2 | 2.48 | 24.3 | 100
9 | MALDAH |  | Malda Mechanical | Source Augmentation of Basara Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/12760 | Augmentation | QUOTATION PAYMENT FOR PH NO 4 OF BASORA W/S SCHEME UNDER BAMONGOLA CCC UNDER MALDA DISTRICT |  |  | BILL/00476/2025-2026 |  | 22/05/2025 | 22/05/2025 | W.B.S.E.D.C.LTD | 11.37 | 0 | 0 | 0
10 | MALDAH |  | Malda Division | Source Augmentation of Basara Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/12760 | Augmentation | Augmentation of Head work site Pump House, Pump House No.-2, Earth filling and 2 Nos. Boundary wall at Basora Water Supply scheme at Bamangola Dev. Block under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000829/2024-2025 | 1000/MD | 12/03/2025 | 01/09/2025 | SABITA CONSTRUCTION COMPANY | 8.5 | 0 | 0 | 100
Total | [13 empty] | 167.74 | 6.67 | 3.98