## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Malda Division | Source Augmentation of Gun Sankrul Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/12761 | Augmentation | Acceptance cum formal work order for Sinking of (250mm. Dia. x 200 mm. dia.) Big dia. Tube Well (120 Mtr. Deep) by D.R. Rig method using P.V.C. pipe and Gravel Filter including supply of Materials at GUN SANKARUL Piped Water Supply Scheme (Tube Well No-3) of Old Malda Block of Malda District under Malda Division, PHE Dte. | Mr. Arnab Giri, Assistant Engineer | Ramen Karmakar, Junior Engineer | ORD/000378/2022-2023 | 2704/MD | 17/11/2022 | 17/12/2022 | A. L. ENGINEERING SOLUTION | 8.52 | 8.44 | 99.06 | 1
2 | MALDAH |  | Malda Mechanical | Source Augmentation of Gun Sankrul Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/12761 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at T/W No. III of Gun Sankrul PWSS , Old Malda C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II |  | ORD/000052/2023-2024 | 3004243248 | 27/04/2023 | 26/07/2023 | W.B.S.E.D.C.LTD | 5.61 | 5.61 | 100 | 0
3 | MALDAH |  | Malda Division | Source Augmentation of Gun Sankrul Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/12761 | Augmentation | Acceptance cum formal work order for Sinking of ( 250mm. Dia. x 200mm. Dia ) Big dia Tube Well No - 4 ( 120.00 Mtr. deep ) by D.R. Rig method using P.V.C. pipe including supply of Materials at GUN SANKRUL Supply Scheme under Malda Division P.H.E Dte in the District of Malda. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000716/2022-2023 | 1174/MD | 20/03/2023 | 19/04/2023 | ASHIS CONSTRUCTION | 8.52 | 7.66 | 89.94 | 100
4 | MALDAH |  | Malda Division | Source Augmentation of Gun Sankrul Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/12761 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000021/2022-2023 | 2407/MD | 17/10/2022 | 17/10/2022 | Resource Division | 5.56 | 0 | 0 | 0
5 | MALDAH |  | Malda Mechanical | Source Augmentation of Gun Sankrul Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/12761 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. III of Gunsankrul Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/014744) | Assistant Engineer - II | Junior Engineer-07 | ORD/001127/2022-2023 | 510/MLMD | 20/03/2023 | 16/09/2023 | SHREE BISHNU CONSTRUCTION | 10.58 | 10.51 | 99.38 | 100
6 | MALDAH |  | Malda Division | Source Augmentation of Gun Sankrul Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/12761 | Augmentation | Acceptance cum formal work order for Construction of 2 (two) Nos 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement in connection with source Augmentation of Gun Sankrul Piped Water Supply Scheme at Old Malda Block of Malda District under Malda Division, PHE Dte. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000058/2023-2024 | 2003/MD | 17/05/2023 | 01/07/2023 | M/S. CHATTERJEE ENTERPRISE | 8.3 | 7.94 | 95.64 | 100
7 | MALDAH |  | Malda Mechanical | Source Augmentation of Gun Sankrul Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/12761 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. IV of Source Augmentation GunSankrul Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. | Assistant Engineer - II | Junior Engineer-07 | ORD/000222/2024-2025 | 2177/MLMD | 20/08/2024 | 18/11/2024 | SHREE BISHNU CONSTRUCTION | 10.62 | 10.57 | 99.52 | 100
8 | MALDAH |  | Malda Division | Source Augmentation of Gun Sankrul Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/12761 | Augmentation | Construction of Boundary Wall at Bhabuk Mouza under Gun Sankrul Water Supply Scheme under Old Malda Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/001025/2023-2024 | 1251/MD | 15/03/2024 | 14/04/2024 | M/S GHOSH CONSTRUCTION | 9.57 | 9.54 | 99.71 | 100
9 | MALDAH |  | Malda Mechanical | Source Augmentation of Gun Sankrul Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/12761 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at TW No- IV of Gunsankrul, Old Malda CCC in the dist of Malda Under Malda Mechanical Division PHE Dte. |  |  | BILL/03512/2023-2024 | BP-2023-24-532 | 15/02/2024 | 15/02/2024 | W.B.S.E.D.C.LTD | 10.49 | 0 | 0 | 0
10 | MALDAH |  | Malda Division | Source Augmentation of Gun Sankrul Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/12761 | Augmentation | Acceptance cum formal work order for Extension of Pipe line and replacing of damage A.C pipe line by different dia UPVC pipe for GUN SANKRUL Piped Water Supply Scheme (Pashim Banjapara-, JL- 32, Chirakuti, JL-39, Hatidubi JL-40, Bag Malancha JL-41) at Old Malda Dev. Block in the District of Malda under Malda Division, PHE Dte. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000405/2022-2023 | 2988/MD | 07/12/2022 | 02/03/2025 | MANAS KUMAR SAHA | 65.41 | 60.28 | 92.15 | 90
11 | MALDAH |  | Malda Division | Source Augmentation of Gun Sankrul Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/12761 | Augmentation | Acceptance cum formal work order for Extension of Pipe line and replacing of damage A.C /upvc pipe line by different dia UPVC pipe for GUN SANKRUL Piped Water Supply Scheme (Kuripara-, JL- 36, Bhabuk, JL-37, Paramanika JL-38) at Old Malda Dev. Block in the District of Malda under Malda Division, PHE Dte. | Mr. Arnab Giri, Assistant Engineer | Ramen Karmakar, Junior Engineer,Ziaur Rahaman, Junior Engineer | ORD/000406/2022-2023 | 2989/MD | 07/12/2022 | 21/01/2023 | KRISHNENDU DUTTA | 59.95 | 52.25 | 87.16 | 100
Total | [13 empty] | 203.14 | 172.8 | 85.07