## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Malda Division | Source Augmentation of Bhabuk Water Supply Scheme of Habibpur Block under Malda Division P.H.E Dte. Malda | SM/12762 | Augmentation | Acceptance cum formal work order for Extension of Pipe line and replacing of damage A.C /upvc pipe line by different dia UPVC pipe for BHABUK Piped Water Supply Scheme at Habibpur Dev. Block in the District of Malda under Malda Division, PHE Dte. | Mr. Arnab Giri, Assistant Engineer | Biswajit Gosh, Junior Engineer,Mukaddar Parvage, Junior Engineer | ORD/000410/2022-2023 | 2984/MD | 07/12/2022 | 21/01/2023 | SOVON KUMAR DAS | 43.65 | 40.92 | 93.75 | 1
2 | MALDAH |  | Malda Division | Source Augmentation of Bhabuk Water Supply Scheme of Habibpur Block under Malda Division P.H.E Dte. Malda | SM/12762 | Augmentation | Acceptance cum formal work order for Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement in connection with source Augmentation of Bhabuk Piped Water Supply Scheme at Habibpur Block of Malda District under Malda Division, PHE Dte. | Mr. Arnab Giri, Assistant Engineer | Biswajit Gosh, Junior Engineer,Mukaddar Parvage, Junior Engineer | ORD/000727/2022-2023 | 1201/MD | 21/03/2023 | 05/05/2023 | M.S. ENTERPRISE | 4.17 | 2.06 | 49.48 | 0
3 | MALDAH |  | Malda Division | Source Augmentation of Bhabuk Water Supply Scheme of Habibpur Block under Malda Division P.H.E Dte. Malda | SM/12762 | Augmentation | Acceptance cum formal work order for Sinking of (250mm. Dia. x 200 mm. dia.) Big dia. Tube Well (135 Mtr. Deep) by D.R. Rig method using P.V.C. pipe and Gravel Filter including supply of Materials at BHABUK Piped Water Supply Scheme (Tube Well No-3) of Habibpur Block of Malda District under Malda Division, PHE Dte. | Mr. Arnab Giri, Assistant Engineer | Biswajit Gosh, Junior Engineer,Mukaddar Parvage, Junior Engineer | ORD/000379/2022-2023 | 2705/MD | 17/11/2022 | 17/12/2022 | A. L. ENGINEERING SOLUTION | 9.14 | 6.4 | 69.96 | 100
4 | MALDAH |  | Malda Division | Source Augmentation of Bhabuk Water Supply Scheme of Habibpur Block under Malda Division P.H.E Dte. Malda | SM/12762 | Augmentation | Acceptance cum formal work order for Hiring of inspection Vehicle (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long journey and should be covered anywhere without any trouble on monthly hire basis for Official use of the office of the Executive Engineer, Malda Division, PHE Dte. (Period from 01/11/2022 to 30/04/2023). | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000518/2022-2023 | 2474/MD | 21/10/2022 | 21/10/2023 | SHABNAM ARA | 4.5 | 0.2 | 4.39 | 21
5 | MALDAH |  | Malda Mechanical | Source Augmentation of Bhabuk Water Supply Scheme of Habibpur Block under Malda Division P.H.E Dte. Malda | SM/12762 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at T/W No. III of Bhabuk, Aiho C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. |  |  | BILL/02484/2023-2024 | BP-2023-24-420 | 04/01/2024 |  | W.B.S.E.D.C.LTD | 6.71 | 0 | 0 | 0
6 | MALDAH |  | Malda Division | Source Augmentation of Bhabuk Water Supply Scheme of Habibpur Block under Malda Division P.H.E Dte. Malda | SM/12762 | Augmentation | Emergent Laying of different diameter UPVC Pipeline and others allied work for Gap negotiatiomn for BHABUK its adjoining mouzas Piped Water Supply Scheme at Habibpur Block of Malda District under Malda Division, PHE Dte., Govt. of West Bengal. | Mr. Arnab Giri, Assistant Engineer | Amit Karmakar, Junior Engineer | ORD/000966/2023-2024 | 805/MD | 21/02/2024 | 06/04/2024 | GOBINDA ENTERPRISE | 12.33 | 0 | 0 | 0
7 | MALDAH |  | Malda Division | Source Augmentation of Bhabuk Water Supply Scheme of Habibpur Block under Malda Division P.H.E Dte. Malda | SM/12762 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of SOURCE AUGMENTATION of BHABUK Water Supply Scheme at Habibpur Dev. Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Arnab Giri, Assistant Engineer | Amit Karmakar, Junior Engineer | ORD/001017/2023-2024 | 1519/MD | 16/03/2024 | 30/04/2024 | M/S JHA CONSTRUCTION | 20.45 | 0 | 0 | 0
8 | MALDAH |  | Malda Mechanical | Source Augmentation of Bhabuk Water Supply Scheme of Habibpur Block under Malda Division P.H.E Dte. Malda | SM/12762 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. III of Bhabuk Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/014864) | Assistant Engineer - II | Junior Engineer-03 | ORD/000309/2023-2024 | 2311/MLMD | 26/07/2023 | 23/11/2023 | SUBRATA KUMAR DAS. | 10.52 | 5.66 | 53.81 | 30
Total | [13 empty] | 111.46 | 55.24 | 49.56