## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Malda Division | Source Augmentation of Mekpur Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/12763 | Augmentation | Acceptance cum formal work order for Sinking of (250mm. Dia. x 200 mm. dia.) Big dia. Tube Well (120 Mtr. Deep) by D.R. Rig method using P.V.C. pipe and Gravel Filter including supply of Materials at MEKPUR Piped Water Supply Scheme (Tube Well No-4) of Old Malda Block of Malda District under Malda Division, PHE Dte. | Mr. Arnab Giri, Assistant Engineer | Ramen Karmakar, Junior Engineer | ORD/000377/2022-2023 | 2703/MD | 17/11/2022 | 17/12/2022 | A. L. ENGINEERING SOLUTION | 8.42 | 8.42 | 100 | 1
2 | MALDAH |  | Malda Mechanical | Source Augmentation of Mekpur Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/12763 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. III, IV & V of Source Augmentation of Mekpur Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/014459) | Assistant Engineer - II |  | ORD/001126/2022-2023 | 509/MLMD | 20/03/2023 | 18/07/2023 | ORIENTAL ENGINEERING CO. | 34.55 | 20.21 | 58.5 | 58
3 | MALDAH |  | Malda Mechanical | Source Augmentation of Mekpur Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/12763 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at T/W No. III of Mekpur PWSS, Old Malda C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II |  | ORD/000049/2023-2024 | 3004243230 | 27/04/2023 | 26/07/2023 | W.B.S.E.D.C.LTD | 4.5 | 4.5 | 100 | 0
4 | MALDAH |  | Malda Mechanical | Source Augmentation of Mekpur Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/12763 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at T/W No. IV of Mekpur PWSS, Old Malda C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II |  | ORD/000050/2023-2024 | 3004243234 | 27/04/2023 | 26/07/2023 | W.B.S.E.D.C.LTD | 2.42 | 2.42 | 100 | 0
5 | MALDAH |  | Malda Division | Source Augmentation of Mekpur Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/12763 | Augmentation | Acceptance cum formal work order for Sinking of (250mm. Dia. x 200 mm. dia.) Big dia. Tube Well (120 Mtr. Deep) by D.R. Rig method using P.V.C. pipe and Gravel Filter including supply of Materials at MEKPUR Piped Water Supply Scheme (Tube Well No-3) of Old Malda Block of Malda District under Malda Division, PHE Dte. | Mr. Arnab Giri, Assistant Engineer | Ramen Karmakar, Junior Engineer | ORD/000376/2022-2023 | 2702/MD | 17/11/2022 | 17/12/2022 | A. L. ENGINEERING SOLUTION | 8.42 | 8.42 | 100 | 1
6 | MALDAH |  | Malda Division | Source Augmentation of Mekpur Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/12763 | Augmentation | Acceptance cum formal work order for Construction of 2 (two) Nos 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement in connection with source Augmentation of Mekpur Piped Water Supply Scheme at Old Malda Block of Malda District under Malda Division, PHE Dte. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000054/2023-2024 | 1985/MD | 17/05/2023 | 01/07/2023 | HIRAK ROY CHOUDHURY | 8.28 | 8.27 | 99.89 | 100
7 | MALDAH |  | Malda Division | Source Augmentation of Mekpur Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/12763 | Augmentation | Construction of Boundary Wall at Goalpara Mouza under Mekpur Water Supply Scheme under Old Malda Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/001012/2023-2024 | 1514/MD | 16/03/2024 | 15/04/2024 | S. N. CONSTRUCTION | 11.32 | 9.01 | 79.63 | 100
8 | MALDAH |  | Malda Division | Source Augmentation of Mekpur Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/12763 | Augmentation | Acceptance cum formal work order for Extension of Pipe line and replacing of damage A.C /upvc pipe line by different dia UPVC pipe for MEKPUR Piped Water Supply Scheme (JL-15 Samsabad, JL-20 Kadamtali, JL-21 Badanpur, JL-22 Chhotapara, JL-23 Lakshmi Kandar and JL-27 Rahutgaon) at Old Malda Dev. Block in the District of Malda under Malda Division, PHE Dte. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000411/2022-2023 | 2985/MD | 07/12/2022 | 21/01/2023 | MANIK CHOUDHURY | 55.22 | 54.19 | 98.14 | 100
9 | MALDAH |  | Malda Division | Source Augmentation of Mekpur Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/12763 | Augmentation | Extension of pipe line and replacing of damage A.C./uPVC pipe line by different dia. UPVC pipe for MEKPUR Piped Water Supply Scheme at Old Malda Block under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000973/2023-2024 | 870/MD | 27/02/2024 | 12/04/2024 | S. R. ENTERPRISE | 6.07 | 5.63 | 92.83 | 100
10 | MALDAH |  | Malda Mechanical | Source Augmentation of Mekpur Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/12763 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at T/W No. III of Mekpur, Old malda C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. |  |  | BILL/02569/2023-2024 | BP-2023-24-462 | 17/01/2024 | 17/01/2024 | W.B.S.E.D.C.LTD | 1.01 | 0 | 0 | 0
11 | MALDAH |  | Malda Division | Source Augmentation of Mekpur Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/12763 | Augmentation | Acceptance cum formal work order for Extension of Pipe line and replacing of damage A.C /upvc pipe line by different dia UPVC pipe for MEKPUR Piped Water Supply Scheme (JL-11 Tutkhan, JL-12 Goalpara, and JL-14 Gotpara) at Old Malda Dev. Block in the District of Malda under Malda Division, PHE Dte. | Mr. Arnab Giri, Assistant Engineer | Ramen Karmakar, Junior Engineer,Ziaur Rahaman, Junior Engineer | ORD/000412/2022-2023 | 2986/MD | 07/12/2022 | 01/01/2025 | M/S PARIMAL DAS | 56.72 | 53.93 | 95.08 | 1
12 | MALDAH |  | Malda Division | Source Augmentation of Mekpur Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/12763 | Augmentation | Design, Supplying, Fabrication, Erection & Commissioning including 3 (three) months Trial Run of 35 m³/hr. capacity Pressure type Iron Elimination Plant with Construction of Blower room & backwash water disposal at Tube Well No. 3 of Mekpur Water Supply Scheme of Old Malda Dev. Block under Malda Division P.H.E Dte in the District of Malda. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000137/2025-2026 | 2615/MD | 02/06/2025 | 15/10/2025 | M/S PARIMAL DAS | 17.27 | 0 | 0 | 0
13 | MALDAH |  | Malda Division | Source Augmentation of Mekpur Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/12763 | Augmentation | Design, Supplying, Fabrication, Erection & Commissioning including 3 (three) months Trial Run of 35 m³/hr. capacity Pressure type Iron Elimination Plant with Construction of Blower room & backwash water disposal at Tube Well No. 4 of Mekpur Water Supply Scheme of Old Malda Dev. Block under Malda Division P.H.E Dte in the District of Malda. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000138/2025-2026 | 2616/MD | 02/06/2025 | 15/10/2025 | M/S PARIMAL DAS | 17.27 | 0 | 0 | 0
14 | MALDAH |  | Malda Division | Source Augmentation of Mekpur Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/12763 | Augmentation | Augmentation of Head work site Pump House, Pump House No.-2, Earth filling and 2 Nos. Boundary wall at Mekpur Water Supply scheme at Old Malda Dev. Block under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000843/2024-2025 | 1068/MD | 19/03/2025 | 18/05/2025 | S. R. ENTERPRISE | 8.04 | 0 | 0 | 0
15 | MALDAH |  | Malda Division | Source Augmentation of Mekpur Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/12763 | Augmentation | Construction of Boundary Wall at Kadamtali Mouza under Mekpur Water Supply Scheme under Old Malda Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000252/2024-2025 | 3188/MD | 27/06/2024 | 26/04/2025 | MANIK CHOUDHURY | 19.96 | 0 | 0 | 100
Total | [13 empty] | 259.48 | 175.01 | 67.45