## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH | Harischandrapur-I | Malda Division | SRI CHANDRAPUR Piped Water Supply Scheme | SM/12764 | New | Material Requisition To Resource Division |  |  | RTOR000036/2023-2024 | 1799/MD | 27/04/2023 | 27/04/2023 | Resource Division | 42.87 | 0 | 0 | 0
2 | MALDAH | Harischandrapur-I | Malda Mechanical | SRI CHANDRAPUR Piped Water Supply Scheme | SM/12764 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I ,II and making compound lighting arrangement at T/W no. I of Sri Chandrapur Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/014411) | Assistant Engineer - II | Junior Engineer-05 | ORD/000386/2023-2024 | 2394/MLMD | 28/07/2023 | 24/01/2024 | KAMAKHYA ENTERPRISE. | 26.58 | 22.68 | 85.34 | 85
3 | MALDAH | Harischandrapur-I | Malda Division | SRI CHANDRAPUR Piped Water Supply Scheme | SM/12764 | New | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Sri Chandrapur Water Supply Scheme under Harishchandrapur-I Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000646/2024-2025 | 5923/MD | 26/11/2024 | 10/01/2025 | M/S ALISA CONSTRUCTIION | 65.18 | 0 | 0 | 0
4 | MALDAH | Harischandrapur-I | Malda Division | SRI CHANDRAPUR Piped Water Supply Scheme | SM/12764 | New | Construction of Boundary Wall at 2nd Tube Well site of Sri Chandrapur Water Supply Scheme under Harishchandrapur-I Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000311/2024-2025 | 3951/MD | 07/08/2024 | 21/09/2024 | M/S ALISA CONSTRUCTIION | 8.68 | 0 | 0 | 0
5 | MALDAH | Harischandrapur-I | Malda Division | SRI CHANDRAPUR Piped Water Supply Scheme | SM/12764 | New | Material Requisition To Resource Division |  |  | RTOR000122/2023-2024 | 92/MD | 05/01/2024 | 05/01/2024 | Resource Division | 12.32 | 0 | 0 | 0
6 | MALDAH | Harischandrapur-I | Malda Mechanical | SRI CHANDRAPUR Piped Water Supply Scheme | SM/12764 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. II of SRI CHANDRAPUR PWSS, Kushida C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. |  |  | BILL/02541/2023-2024 | BP-2023-24-444 | 10/01/2024 | 10/01/2024 | W.B.S.E.D.C.LTD | 3.78 | 0 | 0 | 0
7 | MALDAH | Harischandrapur-I | Malda Mechanical | SRI CHANDRAPUR Piped Water Supply Scheme | SM/12764 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of SRI CHANDRAPUR PWSS, Kushida C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. |  |  | BILL/02542/2023-2024 | BP-2023-24-445 | 10/01/2024 | 10/01/2024 | W.B.S.E.D.C.LTD | 10.15 | 0 | 0 | 0
8 | MALDAH | Harischandrapur-I | Malda Division | SRI CHANDRAPUR Piped Water Supply Scheme | SM/12764 | New | Formal work order for the work of Implementation of SRI CHANDRAPUR Water Supply Scheme at Harishchandrapur-I Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000031/2023-2024 | 1851/MD | 02/05/2023 | 30/07/2025 | M/S ALISA CONSTRUCTIION | 389.77 | 140.31 | 36 | 65
9 | MALDAH | Harischandrapur-I | Malda Division | SRI CHANDRAPUR Piped Water Supply Scheme | SM/12764 | New | Laying of Distribution of UPVC Pipeline of SRI CHANDRAPUR Piped Water Supply Scheme at Harishchandrapur-I Block of Malda District under Malda Division, PHE Dte., Govt. of West Bengal. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000705/2023-2024 | 4634/MD | 23/11/2023 | 09/10/2025 | M/S TRILOCHAN CONSTRUCTION CO | 80.4 | 56.6 | 70.4 | 100
10 | MALDAH | Harischandrapur-I | Malda Division | SRI CHANDRAPUR Piped Water Supply Scheme | SM/12764 | New | Road Restoration and Laying of parallel/ dedicated pipe line for better functionality of Srichandrapur Water Supply Scheme under Harishchandrapur -I Block under Malda Division, PHE Dte. in the district of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000694/2025-2026 | 5921/MD | 26/11/2025 | 25/01/2026 | KAUSHIK MAJUMDAR | 10.02 | 0 | 0 | 0
11 | MALDAH | Harischandrapur-I | Malda Division | SRI CHANDRAPUR Piped Water Supply Scheme | SM/12764 | New | Material Requisition To Resource Division |  |  | RTOR000074/2025-2026 | 5536/MD | 29/10/2025 | 29/10/2025 | Resource Division | 4.82 | 0 | 0 | 0
12 | MALDAH | Harischandrapur-I | Malda Division | SRI CHANDRAPUR Piped Water Supply Scheme | SM/12764 | New | Construction of Boundary Wall at Head Work site of Sri Chandrapur Water Supply Scheme under Harishchandrapur-I Block under Malda Division, PHE Dte. in the district of Malda. (3rd Call). | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000011/2025-2026 | 2419/MD | 27/05/2025 | 11/07/2025 | SAHA CONSTRUCTION | 27.27 | 0 | 0 | 5
Total | [13 empty] | 681.85 | 219.59 | 32.21