## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH | Gazole | Malda Mechanical | SAIDPUR Piped Water Supply Scheme | SM/12766 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I & II and making compound lighting arrangement at T/W no. I of Saidpur Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/014263) | Assistant Engineer - II | Junior Engineer-06,Junior Engineer-07 | ORD/000491/2023-2024 | 2563/MLMD | 04/08/2023 | 29/09/2025 | SUBRATA SAHA | 28.62 | 22.47 | 78.51 | 78
2 | MALDAH | Gazole | Malda Mechanical | SAIDPUR Piped Water Supply Scheme | SM/12766 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. I of Saidpur PWSS , Gazol C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II | Junior Engineer-07 | ORD/001897/2023-2024 | 3004467185 | 17/10/2023 | 15/01/2024 | W.B.S.E.D.C.LTD | 3.87 | 3.87 | 100 | 100
3 | MALDAH | Gazole | Malda Mechanical | SAIDPUR Piped Water Supply Scheme | SM/12766 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. II of Saidpur PWSS , Gazol C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II | Junior Engineer-07 | ORD/001898/2023-2024 | 3004467024 | 17/10/2023 | 15/01/2024 | W.B.S.E.D.C.LTD | 6.11 | 6.11 | 100 | 100
4 | MALDAH | Gazole | Malda Division | SAIDPUR Piped Water Supply Scheme | SM/12766 | New | Material Requisition To Resource Division |  |  | RTOR000048/2023-2024 | 1811/MD | 27/04/2023 | 27/04/2023 | Resource Division | 20.1 | 0 | 0 | 0
5 | MALDAH | Gazole | Malda Division | SAIDPUR Piped Water Supply Scheme | SM/12766 | New | Material Requisition To Resource Division |  |  | RTOR000158/2023-2024 | 240/MD | 10/01/2024 | 10/01/2024 | Resource Division | 12.66 | 0 | 0 | 0
6 | MALDAH | Gazole | Malda Division | SAIDPUR Piped Water Supply Scheme | SM/12766 | New | Formal work order for the work of Implementation of SAIDPUR Water Supply Scheme at Gazole Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Mr. Arnab Giri, Assistant Engineer | Amit Karmakar, Junior Engineer | ORD/000118/2023-2024 | 2320/MD | 08/06/2023 | 24/12/2025 | NEOGI ENTERPRISE | 651.25 | 382.68 | 58.76 | 60
7 | MALDAH | Gazole | Malda Division | SAIDPUR Piped Water Supply Scheme | SM/12766 | New | Providing balance Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Saidpur Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Arnab Giri, Assistant Engineer | Amit Karmakar, Junior Engineer | ORD/000669/2024-2025 | 6168/MD | 05/12/2024 | 15/11/2025 | ANJIMA CONSTRUCTION CO. | 22.39 | 0 | 0 | 0
8 | MALDAH | Gazole | Malda Division | SAIDPUR Piped Water Supply Scheme | SM/12766 | New | Construction of Boundary Wall at 2nd Tube Well site of Saidpur Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Arnab Giri, Assistant Engineer | Amit Karmakar, Junior Engineer | ORD/000182/2024-2025 | 2957/MD | 10/06/2024 | 10/07/2024 | SAYEM ENTERPRISE | 7.16 | 0 | 0 | 100
Total | [13 empty] | 752.17 | 415.13 | 55.19