## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH | Chanchal-I | Malda Mechanical | NABAGRAM Piped Water Supply Scheme | SM/12767 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of NABAGRAM PWSS, Chanchal C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II |  | ORD/001016/2023-2024 | 3004407809 | 11/09/2023 | 10/12/2023 | W.B.S.E.D.C.LTD | 12.15 | 0 | 0 | 100
2 | MALDAH | Chanchal-I | Malda Mechanical | NABAGRAM Piped Water Supply Scheme | SM/12767 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. II of Nabagram, Chanchal C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II | Junior Engineer-05 | ORD/001886/2023-2024 | 3004460870 | 17/10/2023 | 15/01/2024 | W.B.S.E.D.C.LTD | 3.46 | 0 | 0 | 100
3 | MALDAH | Chanchal-I | Malda Division | NABAGRAM Piped Water Supply Scheme | SM/12767 | New | Material Requisition To Resource Division |  |  | RTOR000044/2023-2024 | 1811/MD | 27/04/2023 | 27/04/2023 | Resource Division | 21.33 | 0 | 0 | 0
4 | MALDAH | Chanchal-I | Malda Mechanical | NABAGRAM Piped Water Supply Scheme | SM/12767 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Nabagram Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/013452) | Assistant Engineer - II | Junior Engineer-05 | ORD/000766/2023-2024 | 2566/MLMD | 04/08/2023 | 29/09/2025 | DAS ENTERPRISE. | 29.85 | 0 | 0 | 87
5 | MALDAH | Chanchal-I | Malda Division | NABAGRAM Piped Water Supply Scheme | SM/12767 | New | Material Requisition To Resource Division |  |  | RTOR000119/2023-2024 | 89/MD | 05/01/2024 | 05/01/2024 | Resource Division | 18.48 | 0 | 0 | 0
6 | MALDAH | Chanchal-I | Malda Division | NABAGRAM Piped Water Supply Scheme | SM/12767 | New | Formal work order for the work of Implementation of NABAGRAM Water Supply Scheme at Chanchal-I Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Susanta Pal, JE_Deputation | ORD/000027/2023-2024 | 1838/MD | 02/05/2023 | 31/12/2024 | R. K. ENTERPRISE | 587.5 | 0 | 0 | 80
7 | MALDAH | Chanchal-I | Malda Division | NABAGRAM Piped Water Supply Scheme | SM/12767 | New | Laying of Distribution Line, Providing FHTC, Construction of Pump House at Nabagram Piped Water Supply Scheme at Chanchal-I Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Susanta Pal, JE_Deputation | ORD/000142/2024-2025 | 2903/MD | 07/06/2024 | 27/06/2025 | M/S FOUR STAR CONSTRUCTION | 92.58 | 0 | 0 | 78
8 | MALDAH | Chanchal-I | Malda Division | NABAGRAM Piped Water Supply Scheme | SM/12767 | New | Construction of Boundary Wall at 2nd Tube Well site of Nabagram Water Supply Scheme under Chanchal-I Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Susanta Pal, JE_Deputation | ORD/000158/2024-2025 | 2933/MD | 10/06/2024 | 10/07/2024 | M/S BHARATI CONSTRUCTION | 7.23 | 0 | 0 | 80
9 | MALDAH | Chanchal-I | Malda Division | NABAGRAM Piped Water Supply Scheme | SM/12767 | New | Construction of Boundary Wall at Head Work site of Nabagram Water Supply Scheme under Chanchal-I Block under Malda Division, PHE Dte. in the district of Malda. (2nd Call) | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Susanta Pal, JE_Deputation | ORD/000150/2025-2026 | 2688/MD | 04/06/2025 | 19/07/2025 | MODERN CO-OPERATIVE LABOUR CONTRCT & CONSTRUCTION SOCIETY LIMITED. | 34.99 | 0 | 0 | 0
10 | MALDAH | Chanchal-I | Malda Division | NABAGRAM Piped Water Supply Scheme | SM/12767 | New | Restoration of Road at Bhagabatipur Mouza of Nabagram Piped Water Supply Scheme at Chanchal-I Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Susanta Pal, JE_Deputation | ORD/000198/2025-2026 | 3632/MD | 24/07/2025 | 07/09/2025 | M/S FOUR STAR CONSTRUCTION | 12.6 | 0 | 0 | 0
11 | MALDAH | Chanchal-I | Malda Division | NABAGRAM Piped Water Supply Scheme | SM/12767 | New | Design, Supplying, Fabrication, Erection & Commissioning including 3 (three) months Trial Run of 80 m³/hr. capacity Pressure type Iron Elimination Plant with Construction of Blower room & backwash water disposal at Nabagram Water Supply Scheme of Chanchal-I Dev. Block under Malda Division P.H.E Dte in the District of Malda. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Susanta Pal, JE_Deputation | ORD/000197/2025-2026 | 3631/MD | 24/07/2025 | 21/11/2025 | VISCOUS ENGINEERS PVT. LTD. | 31.97 | 0 | 0 | 0
Total | [13 empty] | 852.15 | 0 | 0