## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH | Gazole | Malda Mechanical | BHADAR Piped Water Supply Scheme | SM/12768 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of Bhadar PWSS, Gazole C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II |  | ORD/000771/2023-2024 | 3004390642 | 16/08/2023 | 14/11/2023 | W.B.S.E.D.C.LTD | 16.23 | 16.23 | 100 | 100
2 | MALDAH | Gazole | Malda Division | BHADAR Piped Water Supply Scheme | SM/12768 | New | Placing of diesel driven Car on hire basis for official use of the office of the Assistant Engineer, Malda Sadar Sub-Division, PHE Dte. under Malda Division, PHE Dte. in good running condition. (Period from 01/07/2023 to 30/09/2023). | Mr. Arnab Giri, Assistant Engineer |  | ORD/000596/2023-2024 | 487/MD | 21/06/2023 | 21/09/2023 | SUBHANKAR SINGH | 0.31 | 0.31 | 100 | 100
3 | MALDAH | Gazole | Malda Division | BHADAR Piped Water Supply Scheme | SM/12768 | New | Material Requisition To Resource Division |  |  | RTOR000040/2023-2024 | 1810/MD | 27/04/2023 | 27/04/2023 | Resource Division | 20.43 | 0 | 0 | 0
4 | MALDAH | Gazole | Malda Mechanical | BHADAR Piped Water Supply Scheme | SM/12768 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Bhadar Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/014278) | Assistant Engineer - II | Junior Engineer-06,Junior Engineer-07 | ORD/001662/2023-2024 | 3340/MLMD | 30/10/2023 | 27/04/2024 | MOON LIGHT CONSTRUCTION AND STAR GOLD ENTERPRISE | 25.45 | 23.75 | 93.33 | 93
5 | MALDAH | Gazole | Malda Division | BHADAR Piped Water Supply Scheme | SM/12768 | New | Material Requisition To Resource Division |  |  | RTOR000098/2023-2024 | 26/MD | 04/01/2024 | 04/01/2024 | Resource Division | 12.71 | 0 | 0 | 0
6 | MALDAH | Gazole | Malda Division | BHADAR Piped Water Supply Scheme | SM/12768 | New | Service Connection charge at P/H No. II of Bhadar Water Supply Scheme under Gazole C.C.C. in the district of Malda. |  |  | BILL/00748/2023-2024 | BP-2023-24-404 | 26/12/2023 | 26/12/2023 | WBSEDCL | 11.36 | 0 | 0 | 0
7 | MALDAH | Gazole | Malda Division | BHADAR Piped Water Supply Scheme | SM/12768 | New | Construction of Boundary Wall at 2nd Tube Well Site of BHADAR Piped Water Supply Scheme at Gazole Dev. Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Arnab Giri, Assistant Engineer | Amit Karmakar, Junior Engineer | ORD/000198/2024-2025 | 2930/MD | 10/06/2024 | 25/07/2024 | NANDAN ENTERPRISE | 6.73 | 0 | 0 | 70
8 | MALDAH | Gazole | Malda Division | BHADAR Piped Water Supply Scheme | SM/12768 | New | Laying of Distribution Sysytem and Providing Functional Household Tap Connection (FHTC) of BHADAR Piped Water Supply Scheme at Gazole Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Arnab Giri, Assistant Engineer | Amit Karmakar, Junior Engineer | ORD/000200/2024-2025 | 2928/MD | 10/06/2024 | 01/07/2025 | MOONLIGHT CONSTRUCTION AND STAR GOLD ENTERPRISE | 55.17 | 27.8 | 50.38 | 50
Total | [13 empty] | 148.4 | 68.08 | 45.88