## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH | Chanchal-I | Malda Division | MATIHARPUR Piped Water Supply Scheme | SM/12769 | New | Acceptance cum formal work order for Laying of Distribution of UPVC Pipeline of MATIHARPUR Piped Water Supply Scheme at Chanchal-I Block of Malda District under Malda Division, PHE Dte., Govt. of West Bengal. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000656/2022-2023 | 1010/MD | 10/03/2023 | 09/05/2023 | M/S DAS CONSTRUCTION | 84.75 | 0 | 0 | 0
2 | MALDAH | Chanchal-I | Malda Division | MATIHARPUR Piped Water Supply Scheme | SM/12769 | New | Material Requisition To Resource Division |  |  | RTOR000056/2023-2024 | 1811/MD | 27/04/2023 | 27/04/2023 | Resource Division | 50.44 | 0 | 0 | 0
3 | MALDAH | Chanchal-I | Malda Division | MATIHARPUR Piped Water Supply Scheme | SM/12769 | New | Material Requisition To Resource Division |  |  | RTOR000118/2023-2024 | 88/MD | 05/01/2024 | 05/01/2024 | Resource Division | 15.4 | 0 | 0 | 0
4 | MALDAH | Chanchal-I | Malda Mechanical | MATIHARPUR Piped Water Supply Scheme | SM/12769 | New | New service connection at MOTIHARPUR PWSS T/W NO II Under EE/MLMD PHE DTE DIST. Malda.(CHANCHAL c c c) |  |  | BILL/00763/2024-2025 | BP-2024-25-199 | 22/05/2024 | 22/05/2024 | W.B.S.E.D.C.LTD | 5.4 | 0 | 0 | 0
5 | MALDAH | Chanchal-I | Malda Mechanical | MATIHARPUR Piped Water Supply Scheme | SM/12769 | New | New service connection at motiharpur T/W no I under EE/MLMD PHE DTE Dist. malda (chanchal c. c. c) |  |  | BILL/03550/2023-2024 | BP-2023-24-563 | 16/02/2024 | 16/02/2024 | W.B.S.E.D.C.LTD | 9.37 | 0 | 0 | 0
6 | MALDAH | Chanchal-I | Malda Mechanical | MATIHARPUR Piped Water Supply Scheme | SM/12769 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I ,II & III and making compound lighting arrangement at T/W no. I of Matiharpur Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/013447) | Assistant Engineer - II | Junior Engineer-05 | ORD/000322/2023-2024 | 2324/MLMD | 26/07/2023 | 26/06/2026 | HANNAN BUILDERS PVT. LTD. | 38.62 | 17.88 | 46.31 | 46
7 | MALDAH | Chanchal-I | Malda Division | MATIHARPUR Piped Water Supply Scheme | SM/12769 | New | Construction of Boundary Wall at Head Work site of Matiharpur Water Supply Scheme under Chanchal-I Block under Malda Division, PHE Dte. in the district of Malda. (2nd Call) | Mr. Sumit Kumar Ghosh, Assistant Engineer | Yusuf Sk, Junior Engineer | ORD/000154/2025-2026 | 2692/MD | 04/06/2025 | 19/07/2025 | M/S ROY CONSTRUCTION | 29.35 | 0 | 0 | 0
8 | MALDAH | Chanchal-I | Malda Division | MATIHARPUR Piped Water Supply Scheme | SM/12769 | New | Construction of Boundary Wall at 2nd Tube Well site of Matiharpur Water Supply Scheme under Chanchal-I Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000189/2024-2025 | 2968/MD | 10/06/2024 | 11/12/2024 | M/S ROY CONSTRUCTION | 9.24 | 0 | 0 | 99
9 | MALDAH | Chanchal-I | Malda Division | MATIHARPUR Piped Water Supply Scheme | SM/12769 | New | Material Requisition To Resource Division |  |  | RTOR000035/2025-2026 | 2821/MD | 11/06/2025 | 11/06/2025 | Resource Division | 6.35 | 0 | 0 | 0
10 | MALDAH | Chanchal-I | Malda Division | MATIHARPUR Piped Water Supply Scheme | SM/12769 | New | Formal work order for Implementation of MATIHARPUR Water Supply Scheme at Chanchal-I Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer,Yusuf Sk, Junior Engineer | ORD/000743/2022-2023 | 1250/MD | 22/03/2023 | 22/08/2026 | RAY CONSTRUCTION CO. | 601.86 | 258.96 | 43.03 | 75
Total | [13 empty] | 850.78 | 276.85 | 32.54