## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH | Gazole | Malda Division | Alal Zone-II Piped Water Supply Scheme | SM/12877 | New | Acceptance cum formal work order for Laying of Distribution of UPVC Pipeline of ALAL ZONE-II Piped Water Supply Scheme at Gazole Block of Malda District under Malda Division, PHE Dte., Govt. of West Bengal. | Mr. Arnab Giri, Assistant Engineer | Amit Karmakar, Junior Engineer | ORD/000099/2023-2024 | 2326/MD | 08/06/2023 | 07/08/2023 | M/S. TEWARI CONSTRUCTION | 50.63 | 0 | 0 | 0
2 | MALDAH | Gazole | Malda Division | Alal Zone-II Piped Water Supply Scheme | SM/12877 | New | Acceptance cum formal work order for Route survey, design and preparation of DPR of Alal Zone-II Piped Water Supply Scheme at Gazole Dev. Block under Malda Division, PHE Dte. | Mr. Arnab Giri, Assistant Engineer | Ramen Karmakar, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | ORD/000687/2021-2022 | 652/MD | 22/03/2022 | 06/04/2022 | TECHVISION | 3.33 | 0 | 0 | 0
3 | MALDAH | Gazole | Malda Division | Alal Zone-II Piped Water Supply Scheme | SM/12877 | New | Material Requisition To Resource Division |  |  | RTOR000066/2023-2024 | 1811/MD | 27/04/2023 | 27/04/2023 | Resource Division | 10.65 | 0 | 0 | 0
4 | MALDAH | Gazole | Malda Mechanical | Alal Zone-II Piped Water Supply Scheme | SM/12877 | New | Supply, installation, commissioning of electro-mechanical components & Trial operation at T/W no. I & II, and making compound lighting arrangement at head worksite of Alal Zone-II Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/011886) | Assistant Engineer - II | Junior Engineer-06,Junior Engineer-07 | ORD/000512/2023-2024 | 2584/MLMD | 04/08/2023 | 13/11/2025 | DAS CONSTRUCTION | 25.24 | 0 | 0 | 70
5 | MALDAH | Gazole | Malda Division | Alal Zone-II Piped Water Supply Scheme | SM/12877 | New | Material Requisition To Resource Division |  |  | RTOR000156/2023-2024 | 252/MD | 10/01/2024 | 10/01/2024 | Resource Division | 8.7 | 0 | 0 | 0
6 | MALDAH | Gazole | Malda Mechanical | Alal Zone-II Piped Water Supply Scheme | SM/12877 | New | W.B.S.E.D.C.LTD Quotation charge at TW No- I of Alal Zone-II, Gazole CCC in the dist of Malda Under Malda Mechanical Division PHE Dte. |  |  | BILL/03715/2023-2024 | BP-2023-24-712 | 18/03/2024 | 18/03/2024 | W.B.S.E.D.C.LTD | 4.64 | 0 | 0 | 0
7 | MALDAH | Gazole | Malda Division | Alal Zone-II Piped Water Supply Scheme | SM/12877 | New | Formal work order for the work of Augmentation of ALAL ZONE-II Piped Water Supply Scheme at Gajol Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Arnab Giri, Assistant Engineer | Amit Karmakar, Junior Engineer | ORD/000050/2023-2024 | 2000/MD | 17/05/2023 | 16/12/2025 | KRISHNENDU DUTTA | 357.66 | 0 | 0 | 50
8 | MALDAH | Gazole | Malda Division | Alal Zone-II Piped Water Supply Scheme | SM/12877 | New | Construction of Boundary Wall at Head Work site of Alal Zone-II Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Arnab Giri, Assistant Engineer | Amit Karmakar, Junior Engineer ,Ziaur Rahaman, Junior Engineer | ORD/000266/2024-2025 | 3415/MD | 09/07/2024 | 01/01/2026 | KRISHNENDU DUTTA | 33.49 | 0 | 0 | 0
9 | MALDAH | Gazole | Malda Division | Alal Zone-II Piped Water Supply Scheme | SM/12877 | New | Construction of Boundary Wall at 2nd Tube Well site of Alal Zone-II Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Arnab Giri, Assistant Engineer | Amit Karmakar, Junior Engineer | ORD/000312/2024-2025 | 3952/MD | 07/08/2024 | 01/01/2026 | KRISHNENDU DUTTA | 8.71 | 0 | 0 | 0
10 | MALDAH | Gazole | Malda Division | Alal Zone-II Piped Water Supply Scheme | SM/12877 | New | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Alal Zone-II Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Arnab Giri, Assistant Engineer | Amit Karmakar, Junior Engineer | ORD/000716/2024-2025 | 6407/MD | 19/12/2024 | 16/12/2025 | KRISHNENDU DUTTA | 28.08 | 0 | 0 | 0
11 | MALDAH | Gazole | Malda Division | Alal Zone-II Piped Water Supply Scheme | SM/12877 | New | Dedicated Pipe laying for better Functionality and Providing Balance FHTC, Construction of Approach Road, Land development and allied work for ALAL Zone-II Water Supply Scheme at Gazole Block of Malda district under Malda Division, PHE Dte. Govt. of West Bengal. | Mr. Arnab Giri, Assistant Engineer | Amit Karmakar, Junior Engineer | ORD/000216/2025-2026 | 3777/MD | 04/08/2025 | 03/10/2025 | MANIK CHOUDHURY | 34.6 | 0 | 0 | 0
Total | [13 empty] | 565.71 | 0 | 0