## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH | Habibpur | Malda Division | JAMALPUR Piped Water Supply Scheme. | SM/12879 | New | Material Requisition To Resource Division |  |  | RTOR000146/2023-2024 | 123/MD | 06/01/2024 |  | Resource Division | 46.72 | 0 | 0 | 0
2 | MALDAH | Habibpur | Malda Division | JAMALPUR Piped Water Supply Scheme. | SM/12879 | New | Construction of Boundary Wall at 2nd Tubewell site of Jamalpur Water Supply Scheme under Habibpur Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Amit Biswas, Assistant Engineer | Mukaddar Parvage, Junior Engineer | ORD/001033/2023-2024 | 1259/MD | 15/03/2024 | 14/04/2024 | LABANYA ENGINEERS CO-OPERATIVE SOCIETY LTD. | 8.5 | 0 | 0 | 0
3 | MALDAH | Habibpur | Malda Mechanical | JAMALPUR Piped Water Supply Scheme. | SM/12879 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Jamalpur Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/013493) | Assistant Engineer - II | Junior Engineer-03 | ORD/000739/2023-2024 | 2800/MLMD | 17/08/2023 | 13/02/2024 | NABAUDYAG ELECTRICAL ENGINEERING CO-OPERATIV SOCIETY LTD. | 27.35 | 8.81 | 32.19 | 30
4 | MALDAH | Habibpur | Malda Division | JAMALPUR Piped Water Supply Scheme. | SM/12879 | New | Formal work order for the work of Implementation of JAMALPUR Piped Water Supply Scheme at Habibpur Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Arnab Giri, Assistant Engineer | Mukaddar Parvage, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | ORD/000008/2023-2024 | 1570/MD | 10/04/2023 | 05/01/2024 | MAHAVIR PUMPS MANUFACTURING PVT. LTD. | 735.7 | 102.73 | 13.96 | 30
5 | MALDAH | Habibpur | Malda Division | JAMALPUR Piped Water Supply Scheme. | SM/12879 | New | Acceptance cum formal work order for Laying of Distribution of UPVC Pipeline of JAMALPUR Piped Water Supply Scheme at Habibpur Block of Malda District under Malda Division, PHE Dte., Govt. of West Bengal. | Mr. Arnab Giri, Assistant Engineer | Mukaddar Parvage, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | ORD/000667/2022-2023 | 1061/MD | 15/03/2023 | 14/05/2023 | BINA CONSTRUCTION | 51.95 | 39.76 | 76.54 | 100
Total | [13 empty] | 870.23 | 151.3 | 17.39