## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH | Harischandrapur-II | Malda Division | UTTAR BHAKURIA Piped Water Supply Scheme. | SM/12881 | New | Material Requisition To Resource Division |  |  | RTOR000018/2023-2024 | 1615/MD | 11/04/2023 | 11/04/2023 | Resource Division | 1.32 | 0 | 0 | 0
2 | MALDAH | Harischandrapur-II | Malda Mechanical | UTTAR BHAKURIA Piped Water Supply Scheme. | SM/12881 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I and making compound lighting arrangement at T/W no. I of Uttar Bhakuria Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/013230) | Assistant Engineer - II | Junior Engineer-05 | ORD/000389/2023-2024 | 2397/MLMD | 28/07/2023 | 24/01/2024 | JIBU SINGHA | 12.27 | 9.97 | 81.23 | 81
3 | MALDAH | Harischandrapur-II | Malda Mechanical | UTTAR BHAKURIA Piped Water Supply Scheme. | SM/12881 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of UTTAR BHAKURIA PWSS, Bhaluka C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. |  |  | BILL/02545/2023-2024 | BP-2023-24-446 | 10/01/2024 | 10/01/2024 | W.B.S.E.D.C.LTD | 4.22 | 0 | 0 | 0
4 | MALDAH | Harischandrapur-II | Malda Division | UTTAR BHAKURIA Piped Water Supply Scheme. | SM/12881 | New | Acceptance cum formal work order for Implementation of UTTAR BHAKURIA Piped Water Supply Scheme at Harishchandrapur-II Block of Malda district under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Susanta Pal, JE_Deputation | ORD/000488/2022-2023 | 196/MD | 19/01/2023 | 01/09/2024 | M/S SABANA CONSTRUCTION | 39.58 | 28.08 | 70.96 | 90
Total | [13 empty] | 57.39 | 38.05 | 66.3