## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH | Gazole | Malda Mechanical | JIGIN Piped Water Supply Scheme | SM/13430 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. II of Jigin PWSS, Pandua C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II |  | ORD/000780/2023-2024 | 3004387500 | 18/08/2023 | 16/11/2023 | W.B.S.E.D.C.LTD | 10.6 | 0 | 0 | 100
2 | MALDAH | Gazole | Malda Mechanical | JIGIN Piped Water Supply Scheme | SM/13430 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of Jigin PWSS, Pandua C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II |  | ORD/000779/2023-2024 | 3004387515 | 18/08/2023 | 16/11/2023 | W.B.S.E.D.C.LTD | 6.63 | 0 | 0 | 100
3 | MALDAH | Gazole | Malda Division | JIGIN Piped Water Supply Scheme | SM/13430 | New | Material Requisition To Resource Division |  |  | RTOR000050/2023-2024 | 1811/MD | 27/04/2023 | 27/04/2023 | Resource Division | 34.75 | 0 | 0 | 0
4 | MALDAH | Gazole | Malda Mechanical | JIGIN Piped Water Supply Scheme | SM/13430 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Jigin Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/015837) | Assistant Engineer - II | Junior Engineer-06,Junior Engineer-07 | ORD/000317/2023-2024 | 2319/MLMD | 26/07/2023 | 01/01/2025 | RMD TRADING. | 26.24 | 0 | 0 | 78
5 | MALDAH | Gazole | Malda Division | JIGIN Piped Water Supply Scheme | SM/13430 | New | Acceptance cum formal work order for Construction of 5.40 mtr.X 3.6 mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement at Head Work Site of JIGIN Water Supply Scheme at Gazole Block of Malda District under Malda Division, PHE Dte. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000483/2022-2023 | 1129/MD | 20/03/2023 | 04/05/2023 | JOYDEB SENGUPTA | 6.58 | 0 | 0 | 100
6 | MALDAH | Gazole | Malda Division | JIGIN Piped Water Supply Scheme | SM/13430 | New | Acceptance cum formal work order for Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement at 2nd Tube Well site. of JIGIN Water Supply Scheme at Gazole Block of Malda District under Malda Division, PHE Dte. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000685/2022-2023 | 1134/MD | 20/03/2023 | 04/05/2023 | M/S ROY CONSTRUCTION | 4.21 | 0 | 0 | 100
7 | MALDAH | Gazole | Malda Division | JIGIN Piped Water Supply Scheme | SM/13430 | New | Providing balance Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Jigin Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000127/2025-2026 | 2509/MD | 29/05/2025 | 28/07/2025 | ARKADEEP ENTERPRISE | 7.24 | 0 | 0 | 0
8 | MALDAH | Gazole | Malda Division | JIGIN Piped Water Supply Scheme | SM/13430 | New | Formal work order for Implementation of JIGIN Water Supply Scheme at Gazole Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000741/2022-2023 | 1251/MD | 22/03/2023 | 01/11/2024 | GOBINDA ENTERPRISE | 88.5 | 0 | 0 | 100
Total | [13 empty] | 184.75 | 0 | 0