## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH | Gazole | Malda Division | ALINAGAR Piped Water Supply Scheme | SM/13431 | New | Placing of diesel driven vehicle on hire basis for official use of the office of the Assistant Engineer, Chanchal Sub-Division, PHE Dte. under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer |  | ORD/000831/2022-2023 | 667/CSD | 29/12/2022 | 29/12/2023 | SUDIPTA GHOSH | 0.85 | 0.33 | 38.34 | 37
2 | MALDAH | Gazole | Malda Mechanical | ALINAGAR Piped Water Supply Scheme | SM/13431 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No.I of Alinagar, Pandua C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II | Junior Engineer-07 | ORD/001888/2023-2024 | 3004496764 | 28/11/2023 | 26/02/2024 | W.B.S.E.D.C.LTD | 4.45 | 4.45 | 100 | 100
3 | MALDAH | Gazole | Malda Mechanical | ALINAGAR Piped Water Supply Scheme | SM/13431 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. II of Alinagar , Pandua C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II | Junior Engineer-07 | ORD/001889/2023-2024 | 3004496739 | 28/11/2023 | 26/02/2024 | W.B.S.E.D.C.LTD | 4.01 | 4.01 | 100 | 100
4 | MALDAH | Gazole | Malda Division | ALINAGAR Piped Water Supply Scheme | SM/13431 | New | Continuation work order for Hiring of 1 no diesel vehicle in good condition (traffic worthily) having licensed contract carriage permit from Regional Transport Authority for office of the Superintending Engineer, North Bengal Circle-II, PHE Dte. (Period from 12/11/2023 to 09/05/2024=180 Days). | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/001231/2023-2024 | 4566/MD | 10/11/2023 | 08/05/2024 | TARUN KUMAR BHATTACHARYA | 0.86 | 1.05 | 122.97 | 0
5 | MALDAH | Gazole | Malda Division | ALINAGAR Piped Water Supply Scheme | SM/13431 | New | Construction of Boundary Wall at Head Work site of Alinagar Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000882/2023-2024 | 158/MD | 08/01/2024 | 22/02/2024 | M/S N. N. ENTERPRISE | 14.51 | 14.51 | 99.99 | 100
6 | MALDAH | Gazole | Malda Division | ALINAGAR Piped Water Supply Scheme | SM/13431 | New | Construction of Boundary Wall at 2nd Tube Well Site of ALINAGAR Piped Water Supply Scheme at Gazole Dev. Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000980/2023-2024 | 975/MD | 04/03/2024 | 18/04/2024 | BANIK BROTHERS | 9.13 | 0 | 0 | 100
7 | MALDAH | Gazole | Malda Division | ALINAGAR Piped Water Supply Scheme | SM/13431 | New | Material Requisition To Resource Division |  |  | RTOR000145/2023-2024 | 122/MD | 06/01/2024 | 06/01/2024 | Resource Division | 28.48 | 0 | 0 | 0
8 | MALDAH | Gazole | Malda Division | ALINAGAR Piped Water Supply Scheme | SM/13431 | New | Formal work order for the work of Implementation of ALINAGAR Water Supply Scheme at Gazole Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000614/2022-2023 | 940/MD | 27/02/2023 | 01/07/2026 | BANIK BROTHERS | 458.54 | 345.34 | 75.31 | 75
9 | MALDAH | Gazole | Malda Division | ALINAGAR Piped Water Supply Scheme | SM/13431 | New | Sinking of Tubewell, Laying of Distribution Line, Providing FHTC, Construction of Pump House & Boundary wall at Alinagar Piped Water Supply Scheme at Gazol Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000144/2024-2025 | 2901/MD | 07/06/2024 | 26/05/2025 | SUDIP DEY | 83.78 | 0 | 0 | 85
10 | MALDAH | Gazole | Malda Division | ALINAGAR Piped Water Supply Scheme | SM/13431 | New | Laying of Parallel/ Dedicated Pipeline for better Functionality at Alinagar Piped Water Supply Scheme at Gazole Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Sri Biswadip Sengupta, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000246/2025-2026 | 4348/MD | 10/09/2025 | 24/11/2026 | BANIK BROTHERS | 26.97 | 0 | 0 | 0
11 | MALDAH | Gazole | Malda Mechanical | ALINAGAR Piped Water Supply Scheme | SM/13431 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Alinagar Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/015847) | Assistant Engineer - II | Junior Engineer-06,Junior Engineer-07 | ORD/000373/2023-2024 | 2381/MLMD | 28/07/2023 | 29/06/2025 | M/S. KUNDU CONSTRACTION | 27.37 | 24.36 | 88.98 | 100
12 | MALDAH | Gazole | Malda Division | ALINAGAR Piped Water Supply Scheme | SM/13431 | New | Bamboo piing, earth filing for protection of pipe line at different places for Alinagar Piped Water Supply Scheme at Gazole Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000590/2024-2025 | 5624/MD | 06/11/2024 | 06/12/2024 | BANIK BROTHERS | 8.66 | 0 | 0 | 100
Total | [13 empty] | 667.59 | 394.04 | 59.02