## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH | Gazole | Malda Division | ALINAGAR Piped Water Supply Scheme | SM/13431 | New | Placing of diesel driven vehicle on hire basis for official use of the office of the Assistant Engineer, Chanchal Sub-Division, PHE Dte. under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer |  | ORD/000831/2022-2023 | 667/CSD | 29/12/2022 | 29/12/2023 | SUDIPTA GHOSH | 0.85 | 0.33 | 38.34 | 37
2 | MALDAH | Gazole | Malda Mechanical | ALINAGAR Piped Water Supply Scheme | SM/13431 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No.I of Alinagar, Pandua C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II | Junior Engineer-07 | ORD/001888/2023-2024 | 3004496764 | 28/11/2023 | 26/02/2024 | W.B.S.E.D.C.LTD | 4.45 | 4.23 | 95.13 | 100
3 | MALDAH | Gazole | Malda Mechanical | ALINAGAR Piped Water Supply Scheme | SM/13431 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. II of Alinagar , Pandua C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II | Junior Engineer-07 | ORD/001889/2023-2024 | 3004496739 | 28/11/2023 | 26/02/2024 | W.B.S.E.D.C.LTD | 4.01 | 4.01 | 100 | 100
4 | MALDAH | Gazole | Malda Division | ALINAGAR Piped Water Supply Scheme | SM/13431 | New | Material Requisition To Resource Division |  |  | RTOR000145/2023-2024 | 122/MD | 06/01/2024 |  | Resource Division | 28.48 | 0 | 0 | 0
5 | MALDAH | Gazole | Malda Division | ALINAGAR Piped Water Supply Scheme | SM/13431 | New | Formal work order for the work of Implementation of ALINAGAR Water Supply Scheme at Gazole Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000614/2022-2023 | 940/MD | 27/02/2023 | 24/11/2023 | BANIK BROTHERS | 458.54 | 232.18 | 50.63 | 75
6 | MALDAH | Gazole | Malda Division | ALINAGAR Piped Water Supply Scheme | SM/13431 | New | Construction of Boundary Wall at 2nd Tube Well Site of ALINAGAR Piped Water Supply Scheme at Gazole Dev. Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000980/2023-2024 | 975/MD | 04/03/2024 | 18/04/2024 | BANIK BROTHERS | 9.13 | 0 | 0 | 0
7 | MALDAH | Gazole | Malda Division | ALINAGAR Piped Water Supply Scheme | SM/13431 | New | Submission of car hire bill on daily rate hired basis, for Office of the Assistant Engineer, Chanchal Sub-Division, P.H.E. Dte. (Period from 07-12-2022 To 02-01-2023). |  |  | BILL/00380/2023-2024 | null | 05/09/2023 |  | SAUDIPTA KUMAR DAS | 0.33 | 0 | 0 | 0
8 | MALDAH | Gazole | Malda Division | ALINAGAR Piped Water Supply Scheme | SM/13431 | New | Sinking of Tubewell, Laying of Distribution Line, Providing FHTC, Construction of Pump House & Boundary wall at Alinagar Piped Water Supply Scheme at Gazol Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000144/2024-2025 | 2901/MD | 07/06/2024 | 06/08/2024 | SUDIP DEY | 83.78 | 0 | 0 | 0
9 | MALDAH | Gazole | Malda Mechanical | ALINAGAR Piped Water Supply Scheme | SM/13431 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Alinagar Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/015847) | Assistant Engineer - II | Junior Engineer-07 | ORD/000373/2023-2024 | 2381/MLMD | 28/07/2023 | 24/01/2024 | M/S. KUNDU CONSTRACTION | 27.37 | 10.6 | 38.74 | 88
10 | MALDAH | Gazole | Malda Division | ALINAGAR Piped Water Supply Scheme | SM/13431 | New | Continuation work order for Hiring of 1 no diesel vehicle in good condition (traffic worthily) having licensed contract carriage permit from Regional Transport Authority for office of the Superintending Engineer, North Bengal Circle-II, PHE Dte. (Period from 12/11/2023 to 09/05/2024=180 Days). | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/001231/2023-2024 | 4566/MD | 10/11/2023 | 08/05/2024 | TARUN KUMAR BHATTACHARYA | 0.86 | 1.05 | 122.97 | 0
11 | MALDAH | Gazole | Malda Division | ALINAGAR Piped Water Supply Scheme | SM/13431 | New | Construction of Boundary Wall at Head Work site of Alinagar Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000882/2023-2024 | 158/MD | 08/01/2024 | 22/02/2024 | M/S N. N. ENTERPRISE | 14.51 | 0 | 0 | 100
Total | [13 empty] | 632.29 | 252.4 | 39.92