## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH | Habibpur | Malda Division | HORGOA Piped Water Supply Scheme | SM/13432 | New | Material Requisition To Resource Division |  |  | RTOR000039/2023-2024 | 1810/MD | 27/04/2023 | 27/04/2023 | Resource Division | 20.8 | 0 | 0 | 0
2 | MALDAH | Habibpur | Malda Division | HORGOA Piped Water Supply Scheme | SM/13432 | New | Formal work order for the work of Implementation of HORGOA Piped Water Supply Scheme at Habibpur Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000037/2023-2024 | 1887/MD | 08/05/2023 | 01/04/2025 | M/S PARIMAL DAS | 418.92 | 208.6 | 49.79 | 45
3 | MALDAH | Habibpur | Malda Division | HORGOA Piped Water Supply Scheme | SM/13432 | New | Sinking of Tubewell, Providing FHTC, Construction of Pump House & Boundary wall at Horgoa Piped Water Supply Scheme at Habibpur Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000483/2024-2025 | 5083/MD | 27/09/2024 | 26/11/2024 | M/S TECHNICO & CO | 44.88 | 0 | 0 | 0
4 | MALDAH | Habibpur | Malda Mechanical | HORGOA Piped Water Supply Scheme | SM/13432 | New | W.B.S.E.D.C.LTD Quotation charge at Pole shifting at Horgoa, Aiho C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. |  |  | BILL/03234/2023-2024 |  | 26/01/2024 | 26/01/2024 | W.B.S.E.D.C.LTD | 0.57 | 0 | 0 | 0
5 | MALDAH | Habibpur | Malda Mechanical | HORGOA Piped Water Supply Scheme | SM/13432 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. II of Horgoa, Aiho C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. |  |  | BILL/02463/2023-2024 | BP-2023-24-396 | 03/01/2024 | 03/01/2024 | W.B.S.E.D.C.LTD | 7.77 | 0 | 0 | 0
6 | MALDAH | Habibpur | Malda Division | HORGOA Piped Water Supply Scheme | SM/13432 | New | Jack Pushing of M.S. pipe of 200 mm dia. through 600 mm dia M.S. pipe by Hydraulic Jacking Technique method through RLY. Track at (KM.-18/8-18/9) between Bulbulchandi(BBC) to Singabad(SQB) station for HARGOA and it's adjoining Mouzas Water Supply Scheme under Malda Division, PHE Dte. in the district of Malda. |  |  | BILL/00189/2024-2025 | BP-2024-25-91 | 13/06/2024 | 13/06/2024 | RAIL BHOOMI CROSSING SEVA (IR-RBCS), NORTHEAST FRONTIER RAILWAY KATIHAR DIVISION | 0.11 | 0 | 0 | 0
7 | MALDAH | Habibpur | Malda Mechanical | HORGOA Piped Water Supply Scheme | SM/13432 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of Horgoa, Aiho C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. |  |  | BILL/02489/2023-2024 | BP-2023-24-424 | 04/01/2024 | 04/01/2024 | W.B.S.E.D.C.LTD | 3.6 | 0 | 0 | 0
8 | MALDAH | Habibpur | Malda Division | HORGOA Piped Water Supply Scheme | SM/13432 | New | Jack Pushing of M.S. pipe of 200 mm dia. through 600 mm dia M.S. pipe by Hydraulic Jacking Technique method through RLY. Track at (KM.-18/8-18/9) between Bulbulchandi(BBC) to Singabad(SQB) station for HARGOA and it's adjoining Mouzas Water Supply Scheme under Malda Division, PHE Dte. in the district of Malda. |  |  | BILL/00347/2024-2025 | BP-2024-25-194 | 06/08/2024 | 06/08/2024 | RAIL BHOOMI CROSSING SEVA (IR-RBCS), NORTHEAST FRONTIER RAILWAY KATIHAR DIVISION | 6.2 | 0 | 0 | 0
9 | MALDAH | Habibpur | Malda Division | HORGOA Piped Water Supply Scheme | SM/13432 | New | Acceptance cum formal work order for Laying of Distribution of UPVC Pipeline of HORGOA Piped Water Supply Scheme at Habibpur Block of Malda District under Malda Division, PHE Dte., Govt. of West Bengal. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000098/2023-2024 | 2325/MD | 08/06/2023 | 07/08/2023 | M/S S. S. ENTERPRISE | 75.74 | 39.56 | 52.23 | 40
10 | MALDAH | Habibpur | Malda Division | HORGOA Piped Water Supply Scheme | SM/13432 | New | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Hargoa Water Supply Scheme under Habibpur Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000628/2024-2025 | 5835/MD | 22/11/2024 | 01/10/2025 | RABIUL ISLAM | 15.25 | 0 | 0 | 0
11 | MALDAH | Habibpur | Malda Division | HORGOA Piped Water Supply Scheme | SM/13432 | New | Construction of Boundary Wall at Head Work Site of Hargoa Water Supply Scheme under Habibpur Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000629/2024-2025 | 5836/MD | 22/11/2024 | 30/08/2025 | M/S ANKUSH ENTERPRISE | 22.71 | 0 | 0 | 90
12 | MALDAH | Habibpur | Malda Division | HORGOA Piped Water Supply Scheme | SM/13432 | New | Construction of Boundary Wall at 2nd Tube well site of Hargoa Water Supply Scheme under Habibpur Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000124/2025-2026 | 2482/MD | 28/05/2025 | 27/07/2025 | SAYEM ENTERPRISE | 6.89 | 0 | 0 | 0
13 | MALDAH | Habibpur | Malda Division | HORGOA Piped Water Supply Scheme | SM/13432 | New | Jack Pushing of M.S. pipe of 200 mm dia. through 600 mm dia M.S. pipe by Hydraulic Jacking Technique method through RLY. Track at KM 18/9-19/0 betweenBulbulchandi (BBC) to Shingabad Station(SQB) Station for HARGOA and it's adjoining Mouzas Water Supply Scheme under Malda Division, PHE Dte. in the district of Malda. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000911/2023-2024 | 384/MD | 17/01/2024 | 01/04/2025 | GHOSH CONSTRUCTION | 28.86 | 0 | 0 | 100
14 | MALDAH | Habibpur | Malda Division | HORGOA Piped Water Supply Scheme | SM/13432 | New | Material Requisition To Resource Division |  |  | RTOR000029/2025-2026 | 2831/MD | 11/06/2025 | 11/06/2025 | Resource Division | 10.56 | 0 | 0 | 0
15 | MALDAH | Habibpur | Malda Mechanical | HORGOA Piped Water Supply Scheme | SM/13432 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I ,II and making compound lighting arrangement at T/W no. I of Horgao Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/015215) | Assistant Engineer - II | Junior Engineer-03,Junior Engineer-06 | ORD/000318/2023-2024 | 2320/MLMD | 26/07/2023 | 10/07/2026 | M/S CHANDRANATH MUKHERJEE. | 26.64 | 21.71 | 81.49 | 80
Total | [13 empty] | 689.51 | 269.87 | 39.14