## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH | Harischandrapur - I | Malda Division | BISHANPUR PIPED WATER SUPPLY SCHEME | SM/13507 | New | Material Requisition To Resource Division |  |  | RTOR000034/2023-2024 | 1803/MD | 27/04/2023 |  | Resource Division | 38.38 | 0 | 0 | 0
2 | MALDAH | Harischandrapur - I | Malda Mechanical | BISHANPUR PIPED WATER SUPPLY SCHEME | SM/13507 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I ,II and making compound lighting arrangement at T/W no. I of Bishanpur Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/014466) | Assistant Engineer - II |  | ORD/000376/2023-2024 | 2384/MLMD | 28/07/2023 | 24/01/2024 | DAS ENTERPRISE. | 26.53 | 0 | 0 | 0
3 | MALDAH | Harischandrapur - I | Malda Division | BISHANPUR PIPED WATER SUPPLY SCHEME | SM/13507 | New | Material Requisition To Resource Division |  |  | RTOR000123/2023-2024 | 93/MD | 05/01/2024 |  | Resource Division | 8.31 | 0 | 0 | 0
4 | MALDAH | Harischandrapur - I | Malda Mechanical | BISHANPUR PIPED WATER SUPPLY SCHEME | SM/13507 | New | New service connection at BISHANPUR PWSS T/W NO II Under EE/MLMD PHE DTE DIST. Malda.( KUSHIDA c c c) |  |  | BILL/00235/2024-2025 | BP-2024-25-87 | 16/04/2024 |  | W.B.S.E.D.C.LTD | 14.51 | 0 | 0 | null
5 | MALDAH | Harischandrapur - I | Malda Mechanical | BISHANPUR PIPED WATER SUPPLY SCHEME | SM/13507 | New | New service connection at BISHANPUR T/W NO I Under EE/MLMD PHE DTE DIST. Malda.( KUSHIDA c c c) |  |  | BILL/00234/2024-2025 | BP-2024-25-86 | 16/04/2024 |  | W.B.S.E.D.C.LTD | 4.65 | 0 | 0 | null
6 | MALDAH | Harischandrapur - I | Malda Division | BISHANPUR PIPED WATER SUPPLY SCHEME | SM/13507 | New | Construction of Boundary Wall at 2nd Tube Well site of Bishanpur Water Supply Scheme under Harishchandrapur-I Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000217/2024-2025 | 3038/MD | 13/06/2024 | 13/07/2024 | A. K. CONSTRUCTION | 10.45 | 0 | 0 | 0
7 | MALDAH | Harischandrapur - I | Malda Division | BISHANPUR PIPED WATER SUPPLY SCHEME | SM/13507 | New | Construction of Boundary Wall at Head Work site of Bishanpur Water Supply Scheme under Harishchandrapur-I Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000216/2024-2025 | 3037/MD | 13/06/2024 | 13/07/2024 | A. K. CONSTRUCTION | 25.52 | 0 | 0 | 0
8 | MALDAH | Harischandrapur - I | Malda Division | BISHANPUR PIPED WATER SUPPLY SCHEME | SM/13507 | New | Laying of Distribution of UPVC Pipeline of BISHANPUR Piped Water Supply Scheme at Harishchandrapur-I Block of Malda District under Malda Division, PHE Dte., Govt. of West Bengal. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer ,Mr. Susanta Pal, JE_Deputation | ORD/000748/2023-2024 | 4995/MD | 15/12/2023 | 13/02/2024 | M/S ALISA CONSTRUCTIION | 93.44 | 10.25 | 10.97 | 75
9 | MALDAH | Harischandrapur - I | Malda Division | BISHANPUR PIPED WATER SUPPLY SCHEME | SM/13507 | New | Formal work order for the work of Implementation of BISHANPUR Piped Water Supply Scheme at Harishchandrapur-I Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000042/2023-2024 | 1911/MD | 11/05/2023 | 05/02/2024 | A. K. CONSTRUCTION | 349.38 | 80.58 | 23.06 | 25
Total | [13 empty] | 571.16 | 90.83 | 15.9