## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH | Habibpur | Malda Mechanical | OLTARA PIPED WATER SUPPLY SCHEME. | SM/13718 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. I of OLTARA, Aiho C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II | Junior Engineer-03 | ORD/001966/2023-2024 | 3004508478 | 05/12/2023 | 04/03/2024 | W.B.S.E.D.C.LTD | 9.14 | 9.14 | 100 | 100
2 | MALDAH | Habibpur | Malda Division | OLTARA PIPED WATER SUPPLY SCHEME. | SM/13718 | New | Material Requisition To Resource Division |  |  | RTOR000082/2023-2024 | 1811/MD | 27/04/2023 | 27/04/2023 | Resource Division | 50.37 | 0 | 0 | 0
3 | MALDAH | Habibpur | Malda Division | OLTARA PIPED WATER SUPPLY SCHEME. | SM/13718 | New | Providing balance Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Oltara Water Supply Scheme under Habibpur Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000714/2024-2025 | 6405/MD | 19/12/2024 | 02/02/2025 | M/S JHA CONSTRUCTION | 65.17 | 0 | 0 | 0
4 | MALDAH | Habibpur | Malda Mechanical | OLTARA PIPED WATER SUPPLY SCHEME. | SM/13718 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. I of OLTARA, Aiho C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. |  |  | BILL/02504/2023-2024 | BP-2023-24-419A | 04/01/2024 | 04/01/2024 | W.B.S.E.D.C.LTD | 0.01 | 0 | 0 | 0
5 | MALDAH | Habibpur | Malda Mechanical | OLTARA PIPED WATER SUPPLY SCHEME. | SM/13718 | New | QUOTATION PAYMENT FOR OLTARA PH3 UNDER AIHO CCC UNDER MALDA DISTRICT |  |  | BILL/03564/2023-2024 | BP-2023-24-586 | 22/02/2024 | 22/02/2024 | W.B.S.E.D.C.LTD | 12.19 | 0 | 0 | 0
6 | MALDAH | Habibpur | Malda Mechanical | OLTARA PIPED WATER SUPPLY SCHEME. | SM/13718 | New | QUOTATION PAYMENT FOR OLTARA PH 2 UNDER AIHO CCC UNDER DISTRICT OF MALDA |  |  | BILL/03565/2023-2024 | BP-2023-24-585 | 22/02/2024 | 22/02/2024 | W.B.S.E.D.C.LTD | 12.93 | 0 | 0 | 0
7 | MALDAH | Habibpur | Malda Division | OLTARA PIPED WATER SUPPLY SCHEME. | SM/13718 | New | Formal work order for Implementation of OLTARA Water Supply Scheme at Habibpur Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000742/2022-2023 | 1253/MD | 22/03/2023 | 20/10/2025 | DUTTA ENTERPRISE | 919.78 | 663.66 | 72.15 | 85
8 | MALDAH | Habibpur | Malda Mechanical | OLTARA PIPED WATER SUPPLY SCHEME. | SM/13718 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I ,II & III and making compound lighting arrangement at T/W no. I of Oltara Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/013242) | Assistant Engineer - II | Junior Engineer-03,Junior Engineer-06 | ORD/000388/2023-2024 | 2396/MLMD | 28/07/2023 | 25/06/2026 | PROGRESSIVE ENG'S CO-OP. SOCIETY LTD | 43.33 | 24.67 | 56.95 | 60
9 | MALDAH | Habibpur | Malda Division | OLTARA PIPED WATER SUPPLY SCHEME. | SM/13718 | New | Material Requisition To Resource Division |  |  | RTOR000036/2025-2026 | 2822/MD | 11/06/2025 | 11/06/2025 | Resource Division | 21.78 | 0 | 0 | 0
10 | MALDAH | Habibpur | Malda Division | OLTARA PIPED WATER SUPPLY SCHEME. | SM/13718 | New | Material Requisition To Resource Division |  |  | RTOR000075/2025-2026 | 5537/MD | 29/10/2025 | 29/10/2025 | Resource Division | 21.78 | 0 | 0 | 0
11 | MALDAH | Habibpur | Malda Division | OLTARA PIPED WATER SUPPLY SCHEME. | SM/13718 | New | Design, Supplying, Fabrication, Erection & Commissioning including 3 (three) months Trial Run of 90m³/hr. capacity Pressure type IRON ELIMINATION Plant with Construction of Blower room & backwash water disposal at head work site of Oltara Water Supply Scheme of Habibpur Block under Malda Division P.H.E Dte in the District of Malda. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000204/2024-2025 | 2991/MD | 11/06/2024 | 08/12/2024 | M/S JHA CONSTRUCTION | 32.88 | 0 | 0 | 0
12 | MALDAH | Habibpur | Malda Division | OLTARA PIPED WATER SUPPLY SCHEME. | SM/13718 | New | Construction of Boundary Wall at Head work Site of Oltara Water Supply Scheme under Habibpur Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000205/2024-2025 | 2992/MD | 11/06/2024 | 07/01/2025 | DUTTA ENTERPRISE | 22.22 | 0 | 0 | 0
13 | MALDAH | Habibpur | Malda Division | OLTARA PIPED WATER SUPPLY SCHEME. | SM/13718 | New | Construction of Boundary Wall at 2nd Tubewell site of Oltara Water Supply Scheme under Habibpur Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000161/2024-2025 | 2936/MD | 10/06/2024 | 06/01/2025 | DUTTA ENTERPRISE | 7.55 | 0 | 0 | 0
14 | MALDAH | Habibpur | Malda Division | OLTARA PIPED WATER SUPPLY SCHEME. | SM/13718 | New | Construction of Boundary Wall at 3rd Tubewell site of Oltara Water Supply Scheme under Habibpur Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000162/2024-2025 | 2937/MD | 10/06/2024 | 06/01/2025 | DUTTA ENTERPRISE | 7.55 | 0 | 0 | 0
Total | [13 empty] | 1226.66 | 697.47 | 56.86