## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH | Habibpur | Malda Division | CHAKSUKUR PIPED WATER SUPPLY SCHEME. | SM/13719 | New | Material Requisition To Resource Division |  |  | RTOR000006/2023-2024 | 1582/MD | 10/04/2023 |  | Resource Division | 17.4 | 0 | 0 | 0
2 | MALDAH | Habibpur | Malda Division | CHAKSUKUR PIPED WATER SUPPLY SCHEME. | SM/13719 | New | Material Requisition To Resource Division |  |  | RTOR000086/2023-2024 | 1811/MD | 27/04/2023 |  | Resource Division | 25.7 | 0 | 0 | 0
3 | MALDAH | Habibpur | Malda Mechanical | CHAKSUKUR PIPED WATER SUPPLY SCHEME. | SM/13719 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. II of CHAKSUKUR, Aiho C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. |  |  | BILL/02487/2023-2024 | BP-2023-24-422 | 04/01/2024 |  | W.B.S.E.D.C.LTD | 3.54 | 0 | 0 | 0
4 | MALDAH | Habibpur | Malda Mechanical | CHAKSUKUR PIPED WATER SUPPLY SCHEME. | SM/13719 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. II of CHAKSUKUR, Aiho C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. |  |  | BILL/02487/2023-2024 | BP-2023-24-422 | 04/01/2024 |  | W.B.S.E.D.C.LTD | 3.54 | 0 | 0 | 0
5 | MALDAH | Habibpur | Malda Mechanical | CHAKSUKUR PIPED WATER SUPPLY SCHEME. | SM/13719 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of CHAKSUKUR, Aiho C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. |  |  | BILL/02488/2023-2024 | BP-2023-24-423 | 04/01/2024 |  | W.B.S.E.D.C.LTD | 6.75 | 0 | 0 | 0
6 | MALDAH | Habibpur | Malda Mechanical | CHAKSUKUR PIPED WATER SUPPLY SCHEME. | SM/13719 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of CHAKSUKUR, Aiho C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. |  |  | BILL/02488/2023-2024 | BP-2023-24-423 | 04/01/2024 |  | W.B.S.E.D.C.LTD | 6.75 | 0 | 0 | 0
7 | MALDAH | Habibpur | Malda Mechanical | CHAKSUKUR PIPED WATER SUPPLY SCHEME. | SM/13719 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Chaksukur Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/013215) | Assistant Engineer - II | Junior Engineer-03 | ORD/000311/2023-2024 | 2313/MLMD | 26/07/2023 | 23/11/2023 | JAL PRAVAHIKA PVT. LTD. | 29.64 | 11.81 | 39.86 | 65
8 | MALDAH | Habibpur | Malda Division | CHAKSUKUR PIPED WATER SUPPLY SCHEME. | SM/13719 | New | Formal work order for the work of Implementation of CHAKSUKUR Piped Water Supply at Habibpur Dev. Block in the District Malda under Malda Division, PHE Dte. Govt. of West Bengal. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000661/2022-2023 | 1035/MD | 13/03/2023 | 12/03/2024 | HANNAN BUILDERS PVT. LTD. | 880.48 | 328.3 | 37.29 | 40
9 | MALDAH | Habibpur | Malda Division | CHAKSUKUR PIPED WATER SUPPLY SCHEME. | SM/13719 | New | Placement of fund against the work for road restoration for laying pipe line for Bulbulchandi- Katlapukur road from 11.645 KM to 13.904 Km and Nimbari to Harishchandrapur road from 0.00 KM to 0.889 KM under Kadirpur and Chaksukur PWSS under Malda Division,PHE Dte. |  |  | BILL/00514/2024-2025 | null | 04/09/2024 |  | EXECUTIVE ENGINEER, PUBLIC WORKS (ROADS) DIRECTORATE. | 14.42 | 0 | 0 | null
Total | [13 empty] | 988.21 | 340.12 | 34.42