## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH | Gazole | Malda Division | EMAMNAGAR PIPED WATER SUPPLY SCHEME. | SM/13720 | New | Material Requisition To Resource Division |  |  | RTOR000009/2023-2024 | 1811/MD | 27/04/2023 |  | Resource Division | 113.13 | 0 | 0 | 0
2 | MALDAH | Gazole | Malda Mechanical | EMAMNAGAR PIPED WATER SUPPLY SCHEME. | SM/13720 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Emamnagar Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/014505) | Assistant Engineer - II |  | ORD/000379/2023-2024 | 2387/MLMD | 28/07/2023 | 24/01/2024 | DAS ENTERPRISE. | 28.65 | 0 | 0 | 0
3 | MALDAH | Gazole | Malda Mechanical | EMAMNAGAR PIPED WATER SUPPLY SCHEME. | SM/13720 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. II of Emamnagar PWSS , Gazol C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II | Junior Engineer-07 | ORD/001896/2023-2024 | 3004467227 | 17/10/2023 | 15/01/2024 | W.B.S.E.D.C.LTD | 3.4 | 3.4 | 100 | 100
4 | MALDAH | Gazole | Malda Mechanical | EMAMNAGAR PIPED WATER SUPPLY SCHEME. | SM/13720 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. I of Emamnagar PWSS , Gazol C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II | Junior Engineer-07 | ORD/001895/2023-2024 | 3004467170 | 17/10/2023 | 15/01/2024 | W.B.S.E.D.C.LTD | 3.8 | 3.6 | 94.82 | 100
5 | MALDAH | Gazole | Malda Division | EMAMNAGAR PIPED WATER SUPPLY SCHEME. | SM/13720 | New | Material Requisition To Resource Division |  |  | RTOR000151/2023-2024 | 250/MD | 10/01/2024 |  | Resource Division | 16.78 | 0 | 0 | 0
6 | MALDAH | Gazole | Malda Division | EMAMNAGAR PIPED WATER SUPPLY SCHEME. | SM/13720 | New | Formal work order for the work of Implementation of EMAMNAGAR Piped Water Supply Scheme at Gazole Dev. Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Mr. Arnab Giri, Assistant Engineer | Amit Karmakar, Junior Engineer | ORD/000662/2022-2023 | 1039/MD | 13/03/2023 | 12/03/2024 | GHOSH BROTHERS | 1113.74 | 317.12 | 28.47 | 15
7 | MALDAH | Gazole | Malda Division | EMAMNAGAR PIPED WATER SUPPLY SCHEME. | SM/13720 | New | Construction of Boundary Wall at 2nd Tube Well site of Emamnagar Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Arnab Giri, Assistant Engineer | Amit Karmakar, Junior Engineer | ORD/000180/2024-2025 | 2955/MD | 10/06/2024 | 10/07/2024 | MARSS INTERNATIONAL | 8.32 | 0 | 0 | 0
Total | [13 empty] | 1287.82 | 324.12 | 25.17