## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH | Gazole | Malda Division | EMAMNAGAR PIPED WATER SUPPLY SCHEME. | SM/13720 | New | Formal work order for the work of Implementation of EMAMNAGAR Piped Water Supply Scheme at Gazole Dev. Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Mr. Arnab Giri, Assistant Engineer | Amit Karmakar, Junior Engineer | ORD/000662/2022-2023 | 1039/MD | 13/03/2023 | 01/04/2027 | GHOSH BROTHERS | 1113.74 | 634.24 | 56.95 | 50
2 | MALDAH | Gazole | Malda Mechanical | EMAMNAGAR PIPED WATER SUPPLY SCHEME. | SM/13720 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Emamnagar Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/014505) | Assistant Engineer - II | Junior Engineer-06,Junior Engineer-07 | ORD/000379/2023-2024 | 2387/MLMD | 28/07/2023 | 27/05/2026 | DAS ENTERPRISE. | 28.65 | 0 | 0 | 0
3 | MALDAH | Gazole | Malda Mechanical | EMAMNAGAR PIPED WATER SUPPLY SCHEME. | SM/13720 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. II of Emamnagar PWSS , Gazol C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II | Junior Engineer-07 | ORD/001896/2023-2024 | 3004467227 | 17/10/2023 | 15/01/2024 | W.B.S.E.D.C.LTD | 3.4 | 3.4 | 100 | 100
4 | MALDAH | Gazole | Malda Mechanical | EMAMNAGAR PIPED WATER SUPPLY SCHEME. | SM/13720 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. I of Emamnagar PWSS , Gazol C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II | Junior Engineer-07 | ORD/001895/2023-2024 | 3004467170 | 17/10/2023 | 15/01/2024 | W.B.S.E.D.C.LTD | 3.8 | 3.8 | 100 | 100
5 | MALDAH | Gazole | Malda Division | EMAMNAGAR PIPED WATER SUPPLY SCHEME. | SM/13720 | New | Material Requisition To Resource Division |  |  | RTOR000009/2023-2024 | 1811/MD | 27/04/2023 | 27/04/2023 | Resource Division | 113.13 | 0 | 0 | 0
6 | MALDAH | Gazole | Malda Division | EMAMNAGAR PIPED WATER SUPPLY SCHEME. | SM/13720 | New | Providing balance Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Emamnagar Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Arnab Giri, Assistant Engineer | Amit Karmakar, Junior Engineer | ORD/000719/2024-2025 | 6410/MD | 19/12/2024 | 30/03/2026 | ABANI BHUSAN GHOSH | 52.11 | 0 | 0 | 0
7 | MALDAH | Gazole | Malda Division | EMAMNAGAR PIPED WATER SUPPLY SCHEME. | SM/13720 | New | Construction of Boundary Wall at 2nd Tube Well site of Emamnagar Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Arnab Giri, Assistant Engineer | Amit Karmakar, Junior Engineer | ORD/000180/2024-2025 | 2955/MD | 10/06/2024 | 10/07/2024 | MARSS INTERNATIONAL | 8.32 | 0 | 0 | 100
8 | MALDAH | Gazole | Malda Division | EMAMNAGAR PIPED WATER SUPPLY SCHEME. | SM/13720 | New | Material Requisition To Resource Division |  |  | RTOR000151/2023-2024 | 250/MD | 10/01/2024 | 10/01/2024 | Resource Division | 16.78 | 0 | 0 | 0
9 | MALDAH | Gazole | Malda Division | EMAMNAGAR PIPED WATER SUPPLY SCHEME. | SM/13720 | New | Construction of Boundary Wall at Head Work site of Emamnagar Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. (2nd Call) | Mr. Arnab Giri, Assistant Engineer | Amit Karmakar, Junior Engineer | ORD/000149/2025-2026 | 2687/MD | 04/06/2025 | 15/01/2026 | LAXMI ENTERPRISE | 28.8 | 0 | 0 | 0
Total | [13 empty] | 1368.73 | 641.44 | 46.86