## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH | Gazole | Malda Division | DUBA KHOSKOAN PIPED WATER SUPPLY SCHEME. | SM/13721 | New | Material Requisition To Resource Division |  |  | RTOR000038/2023-2024 | 1811/MD | 27/04/2023 | 27/04/2023 | Resource Division | 15.2 | 0 | 0 | 0
2 | MALDAH | Gazole | Malda Mechanical | DUBA KHOSKOAN PIPED WATER SUPPLY SCHEME. | SM/13721 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Duba Khoskoan Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/014431) | Assistant Engineer - II | Junior Engineer-06,Junior Engineer-07 | ORD/000378/2023-2024 | 2386/MLMD | 28/07/2023 | 13/12/2025 | MANIK CHANDRA SAHA. | 27.39 | 0 | 0 | 70
3 | MALDAH | Gazole | Malda Division | DUBA KHOSKOAN PIPED WATER SUPPLY SCHEME. | SM/13721 | New | Material Requisition To Resource Division |  |  | RTOR000168/2023-2024 | 249/MD | 10/01/2024 | 10/01/2024 | Resource Division | 14.04 | 0 | 0 | 0
4 | MALDAH | Gazole | Malda Mechanical | DUBA KHOSKOAN PIPED WATER SUPPLY SCHEME. | SM/13721 | New | W.B.S.E.D.C.LTD Quotation charge at TW No- II of Dubakhoskan, Gazol CCC in the dist of Malda Under Malda Mechanical Division PHE Dte. |  |  | BILL/03689/2023-2024 | BP-2023-24-672 | 11/03/2024 | 11/03/2024 | W.B.S.E.D.C.LTD | 3.51 | 0 | 0 | 0
5 | MALDAH | Gazole | Malda Mechanical | DUBA KHOSKOAN PIPED WATER SUPPLY SCHEME. | SM/13721 | New | W.B.S.E.D.C.LTD Quotation charge at TW No- I of Dubakhoskan, Gazol CCC in the dist of Malda Under Malda Mechanical Division PHE Dte. |  |  | BILL/03688/2023-2024 | BP-2023-24-671 | 11/03/2024 | 11/03/2024 | W.B.S.E.D.C.LTD | 4.58 | 0 | 0 | 0
6 | MALDAH | Gazole | Malda Division | DUBA KHOSKOAN PIPED WATER SUPPLY SCHEME. | SM/13721 | New | Formal work order for the work of Implementation of DUBA KHOSKON Water Supply Scheme at Gazole Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000374/2023-2024 | 3118/MD | 11/08/2023 | 01/01/2025 | M/S NANDY ENTERPRISES | 904.54 | 0 | 0 | 0
7 | MALDAH | Gazole | Malda Division | DUBA KHOSKOAN PIPED WATER SUPPLY SCHEME. | SM/13721 | New | Providing balance Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at DubaKhaskon Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000726/2024-2025 | 6417/MD | 19/12/2024 | 01/10/2025 | M/S MANDAL & SONS | 36.96 | 0 | 0 | 0
Total | [13 empty] | 1006.21 | 0 | 0