## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH | Gazole | Malda Division | Mahil Piped Water Supply Scheme | SM/13733 | New | Formal work order for the work of Implementation of MAHIL Piped Water Supply at Gazole Dev. Block in the District Malda under Malda Division, PHE Dte. Govt. of West Bengal. | Mr. Arnab Giri, Assistant Engineer | Amit Karmakar, Junior Engineer | ORD/000663/2022-2023 | 1038/MD | 13/03/2023 | 01/04/2027 | GHOSH BROTHERS | 1500.23 | 521.29 | 34.75 | 40
2 | MALDAH | Gazole | Malda Mechanical | Mahil Piped Water Supply Scheme | SM/13733 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I ,II & III and making compound lighting arrangement at T/W no. I of Mahil Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/014388) | Assistant Engineer - II | Junior Engineer-06,Junior Engineer-07 | ORD/000383/2023-2024 | 2391/MLMD | 28/07/2023 | 29/10/2025 | NABAUDYAG ELECTRICAL ENGINEERING CO-OPERATIV SOCIETY LTD. | 42.44 | 38.43 | 90.54 | 91
3 | MALDAH | Gazole | Malda Mechanical | Mahil Piped Water Supply Scheme | SM/13733 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of Mahil PWSS, Gazole C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II |  | ORD/000718/2023-2024 | 3004390525 | 11/08/2023 | 09/11/2023 | W.B.S.E.D.C.LTD | 3.58 | 3.58 | 100 | 100
4 | MALDAH | Gazole | Malda Mechanical | Mahil Piped Water Supply Scheme | SM/13733 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. II of Mahil PWSS, Gazole C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II |  | ORD/000719/2023-2024 | 3004390616 | 11/08/2023 | 09/11/2023 | W.B.S.E.D.C.LTD | 6.34 | 6.34 | 100 | 100
5 | MALDAH | Gazole | Malda Division | Mahil Piped Water Supply Scheme | SM/13733 | New | Material Requisition To Resource Division |  |  | RTOR000004/2023-2024 | 1583/MD | 10/04/2023 | 10/04/2023 | Resource Division | 29.33 | 0 | 0 | 0
6 | MALDAH | Gazole | Malda Division | Mahil Piped Water Supply Scheme | SM/13733 | New | Material Requisition To Resource Division |  |  | RTOR000032/2023-2024 | 1804/MD | 27/04/2023 | 27/04/2023 | Resource Division | 69.4 | 0 | 0 | 0
7 | MALDAH | Gazole | Malda Division | Mahil Piped Water Supply Scheme | SM/13733 | New | Construction of Boundary Wall at Head Work site of Mahil Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Arnab Giri, Assistant Engineer | Amit Karmakar, Junior Engineer | ORD/000247/2024-2025 | 3052/MD | 13/06/2024 | 09/07/2025 | J. M. CONSTRUCTION | 23.32 | 4.84 | 20.74 | 60
8 | MALDAH | Gazole | Malda Division | Mahil Piped Water Supply Scheme | SM/13733 | New | Material Requisition To Resource Division |  |  | RTOR000150/2023-2024 | 244/MD | 10/01/2024 | 10/01/2024 | Resource Division | 23.41 | 0 | 0 | 0
9 | MALDAH | Gazole | Malda Mechanical | Mahil Piped Water Supply Scheme | SM/13733 | New | W.B.S.E.D.C.LTD Quotation charge at TW No- III of Mahil, Gazole CCC in the dist of Malda Under Malda Mechanical Division PHE Dte. |  |  | BILL/03719/2023-2024 | BP-2023-24-708 | 18/03/2024 | 18/03/2024 | W.B.S.E.D.C.LTD | 3.96 | 0 | 0 | 0
10 | MALDAH | Gazole | Malda Division | Mahil Piped Water Supply Scheme | SM/13733 | New | Providing balance Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Mahil Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Arnab Giri, Assistant Engineer | Amit Karmakar, Junior Engineer | ORD/000647/2024-2025 | 439/MD | 06/02/2025 | 23/03/2025 | KAR CONSTRUCTION AND ORDER SUPPLIERS | 53.22 | 0 | 0 | 0
Total | [13 empty] | 1755.22 | 574.47 | 32.73