## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH | Gazole | Malda Mechanical | ARAZI JALSA PIPED WATER SUPPLY SCHEME. | SM/13734 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. I of ARAZI JALSA , Pandua C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II | Junior Engineer-07 | ORD/001899/2023-2024 | 3004481943 | 08/11/2023 | 06/02/2024 | W.B.S.E.D.C.LTD | 9.23 | 9.23 | 100 | 100
2 | MALDAH | Gazole | Malda Mechanical | ARAZI JALSA PIPED WATER SUPPLY SCHEME. | SM/13734 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. II of ARAZI JALSA , Pandua C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II | Junior Engineer-07 | ORD/001900/2023-2024 | 3004481907 | 08/11/2023 | 06/02/2024 | W.B.S.E.D.C.LTD | 4.21 | 4.21 | 100 | 100
3 | MALDAH | Gazole | Malda Division | ARAZI JALSA PIPED WATER SUPPLY SCHEME. | SM/13734 | New | Material Requisition To Resource Division |  |  | RTOR000054/2023-2024 | 1811/MD | 27/04/2023 | 27/04/2023 | Resource Division | 11.31 | 0 | 0 | 0
4 | MALDAH | Gazole | Malda Division | ARAZI JALSA PIPED WATER SUPPLY SCHEME. | SM/13734 | New | Continuation work order for Hiring of 1 no diesel vehicle in good condition (traffic worthily) having licensed contract carriage permit from Regional Transport Authority for office of the Superintending Engineer, North Bengal Circle-II, PHE Dte. (Period from 10/05/2024 to 19/06/2024=41 Days). | Mr. Prosanta Mandal, Assistant Engineer | Mr. Sujit Sarkar, Junior Engineer | ORD/000576/2024-2025 | 2421/MD | 09/05/2024 | 19/06/2024 | TARUN KUMAR BHATTACHARYA | 0.19 | 0.26 | 131.94 | 0
5 | MALDAH | Gazole | Malda Division | ARAZI JALSA PIPED WATER SUPPLY SCHEME. | SM/13734 | New | Construction of Boundary Wall at Head Work site of Arazi Jalsa Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Arnab Giri, Assistant Engineer | Amit Karmakar, Junior Engineer | ORD/000265/2024-2025 | 3213/MD | 27/06/2024 | 01/09/2025 | LABANYA ENGINEERS CO-OPERATIVE SOCIETY LTD. | 21.89 | 0 | 0 | 70
6 | MALDAH | Gazole | Malda Division | ARAZI JALSA PIPED WATER SUPPLY SCHEME. | SM/13734 | New | Material Requisition To Resource Division |  |  | RTOR000096/2023-2024 | 29/MD | 04/01/2024 | 04/01/2024 | Resource Division | 20.4 | 0 | 0 | 0
7 | MALDAH | Gazole | Malda Division | ARAZI JALSA PIPED WATER SUPPLY SCHEME. | SM/13734 | New | Formal work order for the work of Implementation of ARAZI JALSA Water Supply Scheme at Gazole Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Mr. Arnab Giri, Assistant Engineer | Amit Karmakar, Junior Engineer | ORD/000046/2023-2024 | 2008/MD | 17/05/2023 | 01/09/2025 | M/S TAPAS KUMAR CHAKRABORTY & CO | 1160.94 | 738.03 | 63.57 | 65
8 | MALDAH | Gazole | Malda Mechanical | ARAZI JALSA PIPED WATER SUPPLY SCHEME. | SM/13734 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Arazi Jalsa Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/013468) | Assistant Engineer - II | Junior Engineer-07 | ORD/000505/2023-2024 | 2575/MLMD | 04/08/2023 | 29/08/2025 | NIRMAN. | 26.75 | 0 | 0 | 87
9 | MALDAH | Gazole | Malda Division | ARAZI JALSA PIPED WATER SUPPLY SCHEME. | SM/13734 | New | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Arazi Jalsa Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Arnab Giri, Assistant Engineer | Amit Karmakar, Junior Engineer | ORD/000634/2024-2025 | 5913/MD | 26/11/2024 | 01/10/2025 | EUREKA UNEMPLOYED ENGINEERS CO-OPERATIVE SOCIETY LTD. | 28.74 | 0 | 0 | 0
10 | MALDAH | Gazole | Malda Division | ARAZI JALSA PIPED WATER SUPPLY SCHEME. | SM/13734 | New | Hiring of 1 no diesel vehicle in good condition (traffic worthily) having licensed contract carriage permit from Regional Transport Authority for office of the Superintending Engineer, North Bengal Circle-II, PHE Dte. (Period from 20/06/2024 to 16/12/2024=180 Days). | Mr. Prosanta Mandal, Assistant Engineer | Mr. Sujit Sarkar, Junior Engineer | ORD/000577/2024-2025 | 3108/MD | 18/06/2024 | 15/12/2024 | TARUN KUMAR BHATTACHARYA | 0.86 | 1.41 | 164.96 | 0
11 | MALDAH | Gazole | Malda Division | ARAZI JALSA PIPED WATER SUPPLY SCHEME. | SM/13734 | New | Continuation work order for Hiring of 1 no diesel vehicle in good condition (traffic worthily) having licensed contract carriage permit from Regional Transport Authority for office of the Superintending Engineer, North Bengal Circle-II, PHE Dte. (Period from 20/06/2024 to 16/12/2024=180 Days). Vehicle no. WB 65A/4911.Hiring of 1 no diesel vehicle in good condition (traffic worthily) having licensed contract carriage permit from Regional Transport Authority for office of the Superintending Engineer, North Bengal Circle-II, PHE Dte. (Period from 17/12/2024 to 14/06/2025=180 Days). | Mr. Prosanta Mandal, Assistant Engineer | Mr. Sujit Sarkar, Junior Engineer | ORD/000918/2024-2025 | 6328/MD | 16/12/2024 | 14/06/2025 | USHA ENTERPRISE | 0.86 | 0.93 | 108.4 | 0
12 | MALDAH | Gazole | Malda Division | ARAZI JALSA PIPED WATER SUPPLY SCHEME. | SM/13734 | New | Design, Supplying, Fabrication, Erection & Commissioning including 3 (three) months Trial Run of 80m³/hr. capacity Pressure type IRON ELIMINATION Plant with Construction of Blower room & backwash water disposal at head work site of Arazi Jalsha Water Supply Scheme of Gazole Dev. Block under Malda Division P.H.E Dte in the District of Malda. | Mr. Arnab Giri, Assistant Engineer | Amit Karmakar, Junior Engineer | ORD/000133/2025-2026 | 2507/MD | 29/05/2025 | 11/10/2025 | WIST WATER SOLUTIONS | 31.43 | 0 | 0 | 0
Total | [13 empty] | 1316.81 | 754.06 | 57.26