## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH | Habibpur | Malda Mechanical | KRISHNAPUR PIPED WATER SUPPLY SCHEME. | SM/13746 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. I of KRISHNAPUR, Aiho C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II | Junior Engineer-03 | ORD/001964/2023-2024 | 3004508461 | 07/12/2023 | 06/03/2024 | W.B.S.E.D.C.LTD | 3.89 | 3.89 | 100 | 100
2 | MALDAH | Habibpur | Malda Mechanical | KRISHNAPUR PIPED WATER SUPPLY SCHEME. | SM/13746 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. II of KRISHNAPUR, Aiho C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II | Junior Engineer-03 | ORD/001965/2023-2024 | 3004508446 | 05/12/2023 | 04/03/2024 | W.B.S.E.D.C.LTD | 7.95 | 7.95 | 100 | 100
3 | MALDAH | Habibpur | Malda Division | KRISHNAPUR PIPED WATER SUPPLY SCHEME. | SM/13746 | New | Material Requisition To Resource Division |  |  | RTOR000041/2023-2024 | 1811/MD | 27/04/2023 | 27/04/2023 | Resource Division | 13.07 | 0 | 0 | 0
4 | MALDAH | Habibpur | Malda Division | KRISHNAPUR PIPED WATER SUPPLY SCHEME. | SM/13746 | New | Construction of Boundary Wall at 2nd Tube well Site of Krishnapur Water Supply Scheme under Habibpur Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000164/2024-2025 | 2939/MD | 10/06/2024 | 10/07/2024 | PRITAM ENTERPRISE | 7.16 | 0 | 0 | 0
5 | MALDAH | Habibpur | Malda Division | KRISHNAPUR PIPED WATER SUPPLY SCHEME. | SM/13746 | New | Acceptance cum formal work order for Laying of Distribution of UPVC Pipeline of KRISHNAPUR Piped Water Supply Scheme at Habibpur Block of Malda District under Malda Division, PHE Dte., Govt. of West Bengal. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000107/2023-2024 | 2334/MD | 08/06/2023 | 07/08/2023 | GOBINDA ENTERPRISE | 90.08 | 85.4 | 94.81 | 85
6 | MALDAH | Habibpur | Malda Division | KRISHNAPUR PIPED WATER SUPPLY SCHEME. | SM/13746 | New | Construction of Boundary Wall at Head Work site of Krishnapur Water Supply Scheme under Habibpur Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000887/2023-2024 | 161/MD | 08/01/2024 | 22/02/2024 | GOBINDA ENTERPRISE | 18.55 | 4.84 | 26.12 | 100
7 | MALDAH | Habibpur | Malda Division | KRISHNAPUR PIPED WATER SUPPLY SCHEME. | SM/13746 | New | Placement of fund against the work for road restoration for laying pipe line for Bulbulchandi- Katlapukur road from 0552 KM to 9.943 Km under Talpukur and Krishnapur PWSS under Malda Division,PHE Dte. |  |  | BILL/00513/2024-2025 | BP-2024-25-260 | 13/09/2024 | 13/09/2024 | EXECUTIVE ENGINEER, PUBLIC WORKS (ROADS) DIRECTORATE. | 30.66 | 0 | 0 | 0
8 | MALDAH | Habibpur | Malda Mechanical | KRISHNAPUR PIPED WATER SUPPLY SCHEME. | SM/13746 | New | PAYMENT FOR SHIFTING OF 11 KV OVER HEAD LINE AT THE SITE OF KRISHNAPUR PHE UNDER RATHBARI CCC UNDER MALDA DISTRICT |  |  | BILL/03574/2023-2024 | BP-2023-24-593 | 22/02/2024 | 22/02/2024 | W.B.S.E.D.C.LTD | 3.79 | 0 | 0 | 0
9 | MALDAH | Habibpur | Malda Division | KRISHNAPUR PIPED WATER SUPPLY SCHEME. | SM/13746 | New | Formal work order for the work of Implementation of KRISHNAPUR Piped Water Supply Scheme at Habibpur Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000010/2023-2024 | 1573/MD | 10/04/2023 | 01/05/2025 | M/S MAA TARA CONSTRUCTION | 570.36 | 387.45 | 67.93 | 80
10 | MALDAH | Habibpur | Malda Mechanical | KRISHNAPUR PIPED WATER SUPPLY SCHEME. | SM/13746 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Krishnapur Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/013458) | Assistant Engineer - II | Junior Engineer-03,Junior Engineer-06 | ORD/000498/2023-2024 | 2568/MLMD | 04/08/2023 | 14/07/2025 | DAS ENTERPRISE. | 28.26 | 0 | 0 | 70
11 | MALDAH | Habibpur | Malda Division | KRISHNAPUR PIPED WATER SUPPLY SCHEME. | SM/13746 | New | Design, Supplying, Fabrication, Erection & Commissioning including 3 (three) months Trial Run of 70 m³/hr. capacity Pressure type IRON ELIMINATION Plant with Construction of Blower room & backwash water disposal at Krishnapur Water Supply Scheme of Habibpur Block under Malda Division P.H.E Dte in the District of Malda. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000630/2024-2025 | 5837/MD | 22/11/2024 | 01/07/2025 | VISCOUS ENGINEERS PVT. LTD. | 30.14 | 0 | 0 | 0
12 | MALDAH | Habibpur | Malda Division | KRISHNAPUR PIPED WATER SUPPLY SCHEME. | SM/13746 | New | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Krishnapur Water Supply Scheme under Habibpur Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000631/2024-2025 | 5838/MD | 22/11/2024 | 01/04/2025 | M/S MAA TARA CONSTRUCTION | 60.55 | 0 | 0 | 0
13 | MALDAH | Habibpur | Malda Division | KRISHNAPUR PIPED WATER SUPPLY SCHEME. | SM/13746 | New | Construction of Boundary Wall at 2nd Tube well site of Krishnapur Water Supply Scheme under Habibpur Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000781/2024-2025 | 347/MD | 30/01/2025 | 30/04/2025 | M/S. NAYAMEE ENGINEERING & CONSTRUCTIONS | 7.18 | 0 | 0 | 0
Total | [13 empty] | 871.63 | 489.53 | 56.16