## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Malda Division | Ground Water Based Augmentation of Chanchal Piped Water Supply Scheme | SM/13792 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000069/2023-2024 | 1811/MD | 27/04/2023 | 27/04/2023 | Resource Division | 186.59 | 0 | 0 | 0
2 | MALDAH |  | Malda Mechanical | Ground Water Based Augmentation of Chanchal Piped Water Supply Scheme | SM/13792 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II ,Solarisation of WBSEDCL energised pump house with Supply and Installation of Grid-connected Ground Mounted Solar PV systems with Net Metering and making compound lighting arrangement at T/W no. I of Chanchal (zone-I) Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/011884) | Assistant Engineer - II | Junior Engineer-05 | ORD/000627/2023-2024 | 2662/MLMD | 10/08/2023 | 04/02/2029 | HANNAN BUILDERS PVT. LTD. | 35.18 | 20.93 | 59.5 | 60
3 | MALDAH |  | Malda Mechanical | Ground Water Based Augmentation of Chanchal Piped Water Supply Scheme | SM/13792 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II, Solarisation of WBSEDCL energised pump house with Supply and Installation of Grid-connected Ground Mounted Solar PV systems with Net Metering and making compound lighting arrangement at T/W no. I of Chanchal (zone-III) Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/011884) | Assistant Engineer - II | Junior Engineer-05 | ORD/001704/2023-2024 | 3425/MLMD | 01/11/2023 | 27/01/2026 | NABAUDYAG ELECTRICAL ENGINEERING CO-OPERATIV SOCIETY LTD. | 33.92 | 21.99 | 64.84 | 65
4 | MALDAH |  | Malda Division | Ground Water Based Augmentation of Chanchal Piped Water Supply Scheme | SM/13792 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000134/2023-2024 | 111/MD | 05/01/2024 | 05/01/2024 | Resource Division | 34.35 | 0 | 0 | 0
5 | MALDAH |  | Malda Mechanical | Ground Water Based Augmentation of Chanchal Piped Water Supply Scheme | SM/13792 | Augmentation | New service connection at CHANCHAL PWSS Zone III T/W NO I Under EE/MLMD PHE DTE DIST. Malda.( CHANCHAL c c c) |  |  | BILL/00236/2024-2025 | BP-2024-25-85 | 16/04/2024 | 16/04/2024 | W.B.S.E.D.C.LTD | 3.36 | 0 | 0 | 0
6 | MALDAH |  | Malda Division | Ground Water Based Augmentation of Chanchal Piped Water Supply Scheme | SM/13792 | Augmentation | Formal work order for the work of Augmentation of CHANCHAL ZONE-I, ZONE-II AND ZONE-III Piped Water Supply Scheme at Chanchal-I Dev. Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000658/2022-2023 | 1026/MD | 13/03/2023 | 28/03/2026 | GHOSH BROTHERS | 1318.2 | 69.76 | 5.29 | 15
7 | MALDAH |  | Malda Mechanical | Ground Water Based Augmentation of Chanchal Piped Water Supply Scheme | SM/13792 | Augmentation | Supply, installation, commissioning of electro-mechanical components at T/W no. I, II,III &IV of Chanchal (zone-II) Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/011884) | Assistant Engineer - II | Junior Engineer-05 | ORD/000377/2023-2024 | 2385/MLMD | 28/07/2023 | 28/12/2025 | GHOSH BROTHERS... | 39.33 | 0 | 0 | 0
8 | MALDAH |  | Malda Division | Ground Water Based Augmentation of Chanchal Piped Water Supply Scheme | SM/13792 | Augmentation | Laying of Distribution Sysytem of Chanchal Zone -I, II & III Piped Water Supply Scheme at Chanchal -I Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000926/2023-2024 | 535/MD | 30/01/2024 | 04/11/2024 | GHOSH BROTHERS | 56.98 | 0 | 0 | 35
9 | MALDAH |  | Malda Division | Ground Water Based Augmentation of Chanchal Piped Water Supply Scheme | SM/13792 | Augmentation | Emergent Interconnection between Existing Tube Well and Bolck office building water tank in connection of CHANCHAL Piped Water Supply Scheme at Chanchal-I Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer,Yusuf Sk, Junior Engineer | ORD/000763/2024-2025 | 6621/MD | 31/12/2024 | 29/06/2025 | BIDYUT MAHALDAR | 0.86 | 0 | 0 | 100
10 | MALDAH |  | Malda Division | Ground Water Based Augmentation of Chanchal Piped Water Supply Scheme | SM/13792 | Augmentation | Construction of Boundary Wall at Head Work site of Chanchal Zone-III Water Supply Scheme under Chanchal-I Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Sumit Kumar Ghosh, Assistant Engineer ,Sri Susanta Saha, Assistant Engineer | Mr. Tilok Roy, Junior Engineer,Yusuf Sk, Junior Engineer | ORD/000447/2024-2025 | 4734/MD | 11/09/2024 | 01/02/2025 | M/S MADHU CONSTRUCTION | 19.9 | 0 | 0 | 0
11 | MALDAH |  | Malda Division | Ground Water Based Augmentation of Chanchal Piped Water Supply Scheme | SM/13792 | Augmentation | Hiring of inspection Vehicle (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long journey and should be covered anywhere without any trouble on monthly hire basis for Official use of the office of the Assistant Engineer, Chanchal Sub-Division Division, PHE Dte.(Car-2) (Period from 01/01/2025 to 30/06/2025). | Mr. Sumit Kumar Ghosh, Assistant Engineer ,Sri Susanta Saha, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer ,Mr. Susanta Pal, JE_Deputation | ORD/000873/2024-2025 | 6636/MD | 31/12/2024 | 30/06/2025 | M/S TEWARI CONSTRUCTION | 0.86 | 0 | 0 | 0
12 | MALDAH |  | Malda Division | Ground Water Based Augmentation of Chanchal Piped Water Supply Scheme | SM/13792 | Augmentation | Hiring of inspection Vehicle (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long journey and should be covered anywhere without any trouble on monthly hire basis for Official use of the office of the Assistant Engineer, Chanchal Sub-Division , PHE Dte.(Car-1) (Period from 01/01/2025 to 30/06/2025). | Mr. Sumit Kumar Ghosh, Assistant Engineer ,Sri Susanta Saha, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer ,Mr. Susanta Pal, JE_Deputation | ORD/000872/2024-2025 | 6635/MD | 31/12/2024 | 30/06/2025 | M/S FOUR STAR CONSTRUCTION | 0.86 | 0 | 0 | 0
Total | [13 empty] | 1730.39 | 112.69 | 6.51