## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH | Chanchal-I | Malda Division | KHARBA PIPED WATER SUPPLY SCHEME. | SM/13793 | New | Material Requisition To Resource Division |  |  | RTOR000070/2023-2024 | 1811/MD | 27/04/2023 | 27/04/2023 | Resource Division | 88.29 | 0 | 0 | 0
2 | MALDAH | Chanchal-I | Malda Division | KHARBA PIPED WATER SUPPLY SCHEME. | SM/13793 | New | Bill for reimbursement of cost of Diesel and mobil in respect of hired vehicle Ambassador Car No.- WB-65/D2727 For the month of January, February and March 2023. |  |  | BILL/00336/2023-2024 |  | 22/08/2023 | 22/08/2023 | ARUN KUMAR DAS | 0.96 | 0 | 0 | 0
3 | MALDAH | Chanchal-I | Malda Division | KHARBA PIPED WATER SUPPLY SCHEME. | SM/13793 | New | Laying of Rising Main including Specials and Valves for KHARBA Piped Water Supply Scheme at Chanchal-I Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000963/2023-2024 | 716/MD | 09/02/2024 | 25/03/2024 | M/S. NAYAMEE ENGINEERING & CONSTRUCTIONS | 14.87 | 4.43 | 29.78 | 80
4 | MALDAH | Chanchal-I | Malda Division | KHARBA PIPED WATER SUPPLY SCHEME. | SM/13793 | New | Construction of Boundary Wall at 3rd Tube Well site of Kharba Water Supply Scheme under Chanchal-I Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000172/2024-2025 | 2947/MD | 10/06/2024 | 10/07/2024 | M/S GHOSH ENTERPRISE | 8.66 | 0 | 0 | 0
5 | MALDAH | Chanchal-I | Malda Division | KHARBA PIPED WATER SUPPLY SCHEME. | SM/13793 | New | Construction of Boundary Wall at Head Work site of Kharba Water Supply Scheme under Chanchal-I Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer ,Mr. Tilok Roy, Junior Engineer | ORD/000219/2024-2025 | 3040/MD | 13/06/2024 | 13/07/2024 | SOVAN KUMAR ROY | 24.8 | 0 | 0 | 0
6 | MALDAH | Chanchal-I | Malda Division | KHARBA PIPED WATER SUPPLY SCHEME. | SM/13793 | New | Acceptance cum formal work order for Sinking of 250mm. Dia. x 150 mm. dia. and 160 Mtr. Deep Big dia Tube well (2 Nos.) at KHARBA Water Supply Scheme under Chanchal-I Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000676/2022-2023 | 1140/MD | 20/03/2023 | 19/04/2023 | DUTTA ENTERPRISE | 21.12 | 18.31 | 86.72 | 95
7 | MALDAH | Chanchal-I | Malda Division | KHARBA PIPED WATER SUPPLY SCHEME. | SM/13793 | New | Sinking of 250mm. Dia. x 150 mm. Big dia. Tube Well of 160 Mtr. Deep at Head Work Site at Kharba under Chanchal-I under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000902/2023-2024 | 275/MD | 11/01/2024 | 25/02/2024 | A. L. ENGINEERING SOLUTION | 10.64 | 9.12 | 85.72 | 95
8 | MALDAH | Chanchal-I | Malda Division | KHARBA PIPED WATER SUPPLY SCHEME. | SM/13793 | New | Material Requisition To Resource Division |  |  | RTOR000116/2023-2024 | 86/MD | 05/01/2024 | 05/01/2024 | Resource Division | 16.23 | 0 | 0 | 0
9 | MALDAH | Chanchal-I | Malda Mechanical | KHARBA PIPED WATER SUPPLY SCHEME. | SM/13793 | New | New service connection at kharba w/s supply sch. under EE/MLMD PHE DTE Dist. malda (chanchal c.c.c) |  |  | BILL/03548/2023-2024 | BP-2023-24-561 | 16/02/2024 | 16/02/2024 | W.B.S.E.D.C.LTD | 5.27 | 0 | 0 | 0
10 | MALDAH | Chanchal-I | Malda Mechanical | KHARBA PIPED WATER SUPPLY SCHEME. | SM/13793 | New | New service connection at KHARBA PWSS T/W NO II Under EE/MLMD PHE DTE DIST. Malda.( Chanchal c c c) |  |  | BILL/01932/2024-2025 | BP-2024-25-473 | 28/08/2024 | 28/08/2024 | W.B.S.E.D.C.LTD | 4.6 | 0 | 0 | 0
11 | MALDAH | Chanchal-I | Malda Mechanical | KHARBA PIPED WATER SUPPLY SCHEME. | SM/13793 | New | New service connection at KHARBA PWSS T/W NO III Under EE/MLMD PHE DTE DIST. Malda.( CHANCHAL c c c) |  |  | BILL/01931/2024-2025 | BP-2024-25-472 | 28/08/2024 | 28/08/2024 | W.B.S.E.D.C.LTD | 4.04 | 0 | 0 | 0
12 | MALDAH | Chanchal-I | Malda Division | KHARBA PIPED WATER SUPPLY SCHEME. | SM/13793 | New | Acceptance cum formal work order for Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement at 2nd Tube Well site. of KHARBA Water Supply Scheme at Chanchal-I Block of Malda District under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000482/2022-2023 | 1128/MD | 20/03/2023 | 04/05/2023 | M/S FOUR STAR CONSTRUCTION | 4.2 | 0 | 0 | 100
13 | MALDAH | Chanchal-I | Malda Division | KHARBA PIPED WATER SUPPLY SCHEME. | SM/13793 | New | Formal work order for the work of Laying distribution pipe line of KHARBA and it's adjoining mouzas Piped Water Supply Scheme at Chanchal-I Block of Malda district under Malda Division, PHE Dte. Govt of West Bengal. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000068/2023-2024 | 2033/MD | 19/05/2023 | 17/08/2023 | HANNAN BUILDERS PVT. LTD. | 430.15 | 384.15 | 89.31 | 80
14 | MALDAH | Chanchal-I | Malda Division | KHARBA PIPED WATER SUPPLY SCHEME. | SM/13793 | New | Formal work order for the work of Construction of 750 M3 Capacity OHR with Soil Investigation and FHTC of KHARBA Piped Water Supply Scheme at Chanchal-I Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000063/2023-2024 | 2020/MD | 18/05/2023 | 27/12/2025 | SOVAN KUMAR ROY | 355.8 | 68.83 | 19.34 | 40
15 | MALDAH | Chanchal-I | Malda Mechanical | KHARBA PIPED WATER SUPPLY SCHEME. | SM/13793 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I , II & III and making compound lighting arrangement at T/W no. I of Augmentation of Kharba Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/011882) | Assistant Engineer - II | Junior Engineer-05 | ORD/000263/2023-2024 | 2223/MLMD | 18/07/2023 | 27/01/2026 | NABAUDYAG ELECTRICAL ENGINEERING CO-OPERATIV SOCIETY LTD. | 42.98 | 31.15 | 72.47 | 90
16 | MALDAH | Chanchal-I | Malda Division | KHARBA PIPED WATER SUPPLY SCHEME. | SM/13793 | New | Construction of Boundary Wall at 2nd Tube Well site of Kharba Water Supply Scheme under Chanchal-I Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000171/2024-2025 | 2946/MD | 10/06/2024 | 01/10/2025 | M/S RAKHI ENTERPRISE | 8.66 | 0 | 0 | 80
Total | [13 empty] | 1041.25 | 515.99 | 49.55