## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH | Ratua-I | Malda Division | Ratua Zone-II Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/14097 | New | Acceptance cum formal work order for Route survey, design and preparation of DPR of Ratua Zone-II Piped Water Supply Scheme at Ratua-I Dev. Block under Malda Division, PHE Dte. | Mr. Prosanta Mandal, Assistant Engineer | Mr. Sujit Sarkar, Junior Engineer | ORD/000681/2021-2022 | 647/MD | 22/03/2022 | 06/04/2022 | ENVIROTECH SOLUTIONS | 3.67 | 3.42 | 93.16 | 1
2 | MALDAH | Ratua-I | Malda Division | Ratua Zone-II Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/14097 | New | Formal work order for the work of Augmentation of RATUA ZONE-II Piped Water Supply Scheme at Ratua-I Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Mr. Prosanta Mandal, Assistant Engineer | Tapan Haldar, Junior Engineer | ORD/000053/2023-2024 | 1999/MD | 17/05/2023 | 01/01/2026 | NIRMAN | 550.19 | 106.27 | 19.32 | 30
3 | MALDAH | Ratua-I | Malda Mechanical | Ratua Zone-II Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/14097 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I,II & III and making compound lighting arrangement at Head worksite of Ratua (zone-II) Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/011274) | Assistant Engineer - II | Junior Engineer-05 | ORD/000507/2023-2024 | 2578/MLMD | 04/08/2023 | 24/09/2026 | NABAUDYAG ELECTRICAL ENGINEERING CO-OPERATIV SOCIETY LTD. | 33.37 | 27.2 | 81.51 | 81
4 | MALDAH | Ratua-I | Malda Division | Ratua Zone-II Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/14097 | New | Bill for reimbursement of cost of Diesel and Mobil in respect of hired vehicle Car No. WB-65C/6570 for the Month of JUNE 2023 under Malda Division PHE Dte. |  |  | BILL/00296/2023-2024 | BP-2023-24-159 | 18/08/2023 | 18/08/2023 | UTTAM KUMAR GHOSH | 0.39 | 0 | 0 | 0
5 | MALDAH | Ratua-I | Malda Mechanical | Ratua Zone-II Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/14097 | New | Continuation work- Hiring of Inspection vehicle (Diesel driven) for official use of Assistant Engineer-II under office of the Executive Engineer, Malda Mechanical Division, P.H.E. Dte. | Assistant Engineer - II | Junior Engineer-03 | ORD/000120/2024-2025 | 1200/MLMD | 02/04/2024 | 02/06/2024 | SUBRATA SAHA | 0.78 | 0.76 | 97.69 | 100
6 | MALDAH | Ratua-I | Malda Division | Ratua Zone-II Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/14097 | New | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Ratua Zone-II Supply Scheme under Ratua-I Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Prosanta Mandal, Assistant Engineer | Tapan Haldar, Junior Engineer | ORD/000600/2024-2025 | 5739/MD | 20/11/2024 | 19/05/2025 | M/S TEWARI CONSTRUCTION | 72.46 | 0 | 0 | 0
7 | MALDAH | Ratua-I | Malda Division | Ratua Zone-II Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/14097 | New | Hiring of inspection Vehicle (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long journey and should be covered anywhere without any trouble on monthly hire basis for Official use of the Assistant Engineer, Malda Division, PHE Dte. (Period from 01/01/2025 to 30/06/2025). | Mr. Prosanta Mandal, Assistant Engineer | Mr. Sujit Sarkar, Junior Engineer | ORD/000871/2024-2025 | 6634/MD | 31/12/2024 | 30/06/2025 | AMIN ENTERPRISE | 0.86 | 0 | 0 | 0
8 | MALDAH | Ratua-I | Malda Division | Ratua Zone-II Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/14097 | New | Material Requisition To Resource Division |  |  | RTOR000144/2023-2024 | 121/MD | 06/01/2024 | 06/01/2024 | Resource Division | 54.12 | 0 | 0 | 0
9 | MALDAH | Ratua-I | Malda Mechanical | Ratua Zone-II Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/14097 | New | New service connection at RATUA (ZONE II) PWSS T/W NO I Under EE/MLMD PHE DTE DIST. Malda.( SAMSI c c c) |  |  | BILL/00762/2024-2025 | BP-2024-25-198 | 22/05/2024 | 22/05/2024 | W.B.S.E.D.C.LTD | 4.6 | 0 | 0 | 0
10 | MALDAH | Ratua-I | Malda Mechanical | Ratua Zone-II Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/14097 | New | New service connection at RATUA (ZONE II) PWSS T/W NO II Under EE/MLMD PHE DTE DIST. Malda.( SAMSI c c c) |  |  | BILL/00761/2024-2025 | BP-2024-25-197 | 22/05/2024 | 22/05/2024 | W.B.S.E.D.C.LTD | 4.16 | 0 | 0 | 0
11 | MALDAH | Ratua-I | Malda Division | Ratua Zone-II Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/14097 | New | Erection of Property board related to Jal Jeevan Mission works of Sambalpur, Gobarjona, Kadamtali & Magura PWSS under Ratua-II Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Debasis Pal, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000971/2024-2025 | 660/MD | 19/02/2025 | 26/02/2025 | J. M. CONSTRUCTION | 0.73 | 0 | 0 | 0
12 | MALDAH | Ratua-I | Malda Division | Ratua Zone-II Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/14097 | New | Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room at Pump House No. 3 of Ratua Zone-II Piped Water Supply Scheme under Ratua-I Dev. Block under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Prosanta Mandal, Assistant Engineer | Tapan Haldar, Junior Engineer | ORD/000134/2025-2026 | 2508/MD | 29/05/2025 | 13/07/2025 | M/S NAMITA CONSTRUCTION | 4.18 | 0 | 0 | 0
13 | MALDAH | Ratua-I | Malda Division | Ratua Zone-II Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/14097 | New | Hiring of inspection Vehicle (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long journey and should be covered anywhere without any trouble on monthly hire basis for Official use of the Assistant Engineer, Malda Division, PHE Dte. (Car-2) (Period from 01/01/2026 to 30/06/2026). | Mr. Prosanta Mandal, Assistant Engineer | Mr. Sujit Sarkar, Junior Engineer | ORD/000847/2025-2026 | 6433/MD | 31/12/2025 | 30/06/2026 | ARUN KUMAR DAS | 0.86 | 0 | 0 | 0
14 | MALDAH | Ratua-I | Malda Division | Ratua Zone-II Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/14097 | New | Hiring of inspection Vehicle (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long journey and should be covered anywhere without any trouble on monthly hire basis for Official use of the Assistant Engineer, Malda Division, PHE Dte. (Car-1) (Period from 01/01/2026 to 30/06/2026). | Mr. Prosanta Mandal, Assistant Engineer | Mr. Sujit Sarkar, Junior Engineer | ORD/000846/2025-2026 | 6432/MD | 31/12/2025 | 30/06/2026 | UTTAM KUMAR GHOSH | 0.86 | 0 | 0 | 0
15 | MALDAH | Ratua-I | Malda Division | Ratua Zone-II Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/14097 | New | Material Requisition To Resource Division |  |  | RTOR000028/2024-2025 | 1041/MD | 18/03/2025 | 18/03/2025 | Resource Division | 20.53 | 0 | 0 | 0
16 | MALDAH | Ratua-I | Malda Division | Ratua Zone-II Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/14097 | New | Material Requisition To Resource Division |  |  | RTOR000070/2025-2026 | 5549/MD | 29/10/2025 | 29/10/2025 | Resource Division | 1.18 | 0 | 0 | 0
Total | [13 empty] | 752.91 | 137.65 | 18.28