## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH | Ratua-I | Malda Division | Ratua Zone-I Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/14098 | New | Acceptance cum formal work order for Route survey, design and preparation of DPR of Ratua Zone-I Piped Water Supply Scheme at Ratua-I Dev. Block under Malda Division, PHE Dte. | Mr. Prosanta Mandal, Assistant Engineer | Mr. Sujit Sarkar, Junior Engineer | ORD/000680/2021-2022 | 646/MD | 22/03/2022 | 06/04/2022 | ENVIROTECH SOLUTIONS | 4.4 | 0 | 0 | 1
2 | MALDAH | Ratua-I | Malda Division | Ratua Zone-I Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/14098 | New | Material Requisition To Resource Division |  |  | RTOR000067/2023-2024 | 1811/MD | 27/04/2023 | 27/04/2023 | Resource Division | 80.51 | 0 | 0 | 0
3 | MALDAH | Ratua-I | Malda Division | Ratua Zone-I Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/14098 | New | Bill for reimbursement of cost of Diesel and Mobil in respect of hired vehicle Car No. WB-04-H-8254 for the Month of MAY, JUNE and JULY 2023 under Malda Division PHE Dte. |  |  | BILL/00295/2023-2024 |  | 10/08/2023 | 10/08/2023 | SHABNAM ARA | 1.18 | 0 | 0 | 0
4 | MALDAH | Ratua-I | Malda Division | Ratua Zone-I Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/14098 | New | Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room at Ratua Zone-I PWSS under Ratua-I Block under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Prosanta Mandal, Assistant Engineer | Mr. Sujit Sarkar, Junior Engineer | ORD/000689/2024-2025 | 6206/MD | 09/12/2024 | 23/01/2025 | RAJA CONSTRUCTION | 4.51 | 0 | 0 | 0
5 | MALDAH | Ratua-I | Malda Division | Ratua Zone-I Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/14098 | New | Formal work order for the work of Augmentation of RATUA ZONE-I Piped Water Supply Scheme at Ratua-I Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Mr. Prosanta Mandal, Assistant Engineer | Mr. Sujit Sarkar, Junior Engineer | ORD/000069/2023-2024 | 2042/MD | 19/05/2023 | 27/04/2026 | STARCO CONSTRUCTIONS | 853.24 | 0 | 0 | 60
6 | MALDAH | Ratua-I | Malda Mechanical | Ratua Zone-I Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/14098 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I,II & III and making compound lighting arrangement at Head worksite of Ratua (zone-I) Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/011269) | Assistant Engineer - II | Junior Engineer-05 | ORD/000508/2023-2024 | 2579/MLMD | 04/08/2023 | 27/01/2026 | NABAUDYAG ELECTRICAL ENGINEERING CO-OPERATIV SOCIETY LTD. | 33.64 | 0 | 0 | 87
7 | MALDAH | Ratua-I | Malda Division | Ratua Zone-I Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/14098 | New | Dismantling of abandoned room at Head work site of Ratua-I PWSS under Ratua-I Dev. Block under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Prosanta Mandal, Assistant Engineer | Mr. Sujit Sarkar, Junior Engineer | ORD/000951/2023-2024 | 654/MD | 08/02/2024 | 09/03/2024 | M/S. TEWARI CONSTRUCTION | 1.93 | 0 | 0 | 100
8 | MALDAH | Ratua-I | Malda Division | Ratua Zone-I Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/14098 | New | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Ratua Zone-I Water Supply Scheme under Ratua-I Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Prosanta Mandal, Assistant Engineer | Mr. Sujit Sarkar, Junior Engineer | ORD/001015/2023-2024 | 1517/MD | 16/03/2024 | 01/03/2026 | UTTAM KUMAR GHOSH | 79.16 | 0 | 0 | 0
9 | MALDAH | Ratua-I | Malda Division | Ratua Zone-I Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/14098 | New | Construction of Boundary Wall at 3rd Tube well site of Ratua Zone-I Water Supply Scheme under Ratua-I Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Prosanta Mandal, Assistant Engineer | Mr. Sujit Sarkar, Junior Engineer | ORD/000675/2024-2025 | 6200/MD | 09/12/2024 | 23/01/2025 | UTTAM KUMAR GHOSH | 7.56 | 0 | 0 | 100
Total | [13 empty] | 1066.12 | 0 | 0