## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Malda Division | Augmentation of Baharal Zone-I & II Piped Water Supply Scheme | SM/14099 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000071/2023-2024 | 1811/MD | 27/04/2023 |  | Resource Division | 90.88 | 0 | 0 | 0
2 | MALDAH |  | Malda Division | Augmentation of Baharal Zone-I & II Piped Water Supply Scheme | SM/14099 | Augmentation | Acceptance cum formal work order for Route survey, design and preparation of DPR of Baharal Piped Water Supply Scheme at Ratua-I Dev. Block under Malda Division, PHE Dte. | Mr. Prosanta Mandal, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000685/2021-2022 | 650/MD | 22/03/2022 | 06/04/2022 | ENVIROTECH SOLUTIONS | 4.59 | 4.59 | 100 | 100
3 | MALDAH |  | Malda Division | Augmentation of Baharal Zone-I & II Piped Water Supply Scheme | SM/14099 | Augmentation | Formal work order for the work of Augmentation of BAHARAL ZONE-I and II Piped Water Supply Scheme at Ratua-I Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Mr. Prosanta Mandal, Assistant Engineer | Rahul Das Biswas, Junior Engineer | ORD/000362/2023-2024 | 3067/MD | 09/08/2023 | 05/05/2024 | GHOSH BROTHERS | 1160.22 | 0 | 0 | 3
4 | MALDAH |  | Malda Mechanical | Augmentation of Baharal Zone-I & II Piped Water Supply Scheme | SM/14099 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I,II & III and making compound lighting arrangement at Head worksite of Baharal (zone-II) Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/011899) | Assistant Engineer - II | Junior Engineer-05 | ORD/000510/2023-2024 | 2582/MLMD | 04/08/2023 | 02/12/2023 | ANIMA ENTERPRISE | 33.36 | 12.61 | 37.79 | 76
5 | MALDAH |  | Malda Mechanical | Augmentation of Baharal Zone-I & II Piped Water Supply Scheme | SM/14099 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I,II & III and making compound lighting arrangement at Head worksite of Baharal (zone-I) Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/011899) | Assistant Engineer - II | Junior Engineer-05 | ORD/000509/2023-2024 | 2581/MLMD | 04/08/2023 | 02/12/2023 | MERCURY ENGINEERING COMPANY. | 33.22 | 12.61 | 37.95 | 76
Total | [13 empty] | 1322.27 | 29.8 | 2.25