## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Malda Division | Augmentation of Baharal Zone-I & II Piped Water Supply Scheme | SM/14099 | Augmentation | Acceptance cum formal work order for Route survey, design and preparation of DPR of Baharal Piped Water Supply Scheme at Ratua-I Dev. Block under Malda Division, PHE Dte. | Mr. Prosanta Mandal, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000685/2021-2022 | 650/MD | 22/03/2022 | 06/04/2022 | ENVIROTECH SOLUTIONS | 4.59 | 4.59 | 100 | 100
2 | MALDAH |  | Malda Division | Augmentation of Baharal Zone-I & II Piped Water Supply Scheme | SM/14099 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000071/2023-2024 | 1811/MD | 27/04/2023 | 27/04/2023 | Resource Division | 90.88 | 0 | 0 | 0
3 | MALDAH |  | Malda Mechanical | Augmentation of Baharal Zone-I & II Piped Water Supply Scheme | SM/14099 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I,II & III and making compound lighting arrangement at Head worksite of Baharal (zone-I) Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/011899) | Assistant Engineer - II | Junior Engineer-05 | ORD/000509/2023-2024 | 2581/MLMD | 04/08/2023 | 20/09/2026 | MERCURY ENGINEERING COMPANY. | 33.22 | 25.22 | 75.91 | 76
4 | MALDAH |  | Malda Mechanical | Augmentation of Baharal Zone-I & II Piped Water Supply Scheme | SM/14099 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I,II & III and making compound lighting arrangement at Head worksite of Baharal (zone-II) Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/011899) | Assistant Engineer - II | Junior Engineer-05 | ORD/000510/2023-2024 | 2582/MLMD | 04/08/2023 | 07/10/2026 | ANIMA ENTERPRISE | 33.36 | 25.21 | 75.58 | 76
5 | MALDAH |  | Malda Division | Augmentation of Baharal Zone-I & II Piped Water Supply Scheme | SM/14099 | Augmentation | Formal work order for the work of Augmentation of BAHARAL ZONE-I and II Piped Water Supply Scheme at Ratua-I Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Mr. Prosanta Mandal, Assistant Engineer | Rahul Das Biswas, Junior Engineer | ORD/000362/2023-2024 | 3067/MD | 09/08/2023 | 19/07/2026 | GHOSH BROTHERS | 1160.22 | 0 | 0 | 2
6 | MALDAH |  | Malda Division | Augmentation of Baharal Zone-I & II Piped Water Supply Scheme | SM/14099 | Augmentation | Erection of Property board and dissemination of Property information through pipe painting related to Jal Jeevan Mission works of Bharal, Bhado, Bilaimari and Chandmoni-I & II GP under Ratua-I Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Debasis Pal, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000970/2024-2025 | 659/MD | 19/02/2025 | 26/02/2025 | M/S TEWARI CONSTRUCTION | 0.97 | 0 | 0 | 0
7 | MALDAH |  | Malda Division | Augmentation of Baharal Zone-I & II Piped Water Supply Scheme | SM/14099 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000030/2024-2025 | 1042/MD | 18/03/2025 | 18/03/2025 | Resource Division | 32.35 | 0 | 0 | 0
8 | MALDAH |  | Malda Mechanical | Augmentation of Baharal Zone-I & II Piped Water Supply Scheme | SM/14099 | Augmentation | New service connection at Baharal PWSS Zone II T/W NO I Under EE/MLMD PHE DTE DIST. Malda.( samsi c c c) |  |  | BILL/02730/2024-2025 | BP-2024-25-613 | 06/02/2025 | 06/02/2025 | W.B.S.E.D.C.LTD | 7 | 0 | 0 | 0
Total | [13 empty] | 1362.59 | 55.02 | 4.04