## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH | Ratua-II | Malda Division | Pukuria Piped Water Supply Scheme | SM/14100 | New | Acceptance cum formal work order for Route survey, design and preparation of DPR of Pukuria Piped Water Supply Scheme at Ratua-II Dev. Block under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000694/2021-2022 | 659/MD | 22/03/2022 | 06/04/2022 | ECO CARE | 3.71 | 3.71 | 100 | 1
2 | MALDAH | Ratua-II | Malda Division | Pukuria Piped Water Supply Scheme | SM/14100 | New | Formal work order for the work of Augmentation of PUKHURIA Piped Water Supply Scheme at Ratua-II Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Mr. Prosanta Mandal, Assistant Engineer | Sudip Kumar Mahata, Junior Engineer | ORD/000062/2023-2024 | 2022/MD | 18/05/2023 | 26/09/2026 | DUTTA ENTERPRISE | 957.93 | 467.08 | 48.76 | 60
3 | MALDAH | Ratua-II | Malda Mechanical | Pukuria Piped Water Supply Scheme | SM/14100 | New | Name of Work: Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I,II,III & IV and making compound lighting arrangement at Head worksite of Pukuria Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/011879) | Assistant Engineer - II | Junior Engineer-05 | ORD/000515/2023-2024 | 2580/MLMD | 04/08/2023 | 24/09/2026 | DEY ENTERPRISE.. | 44.39 | 37.04 | 83.45 | 92
4 | MALDAH | Ratua-II | Malda Division | Pukuria Piped Water Supply Scheme | SM/14100 | New | Material Requisition To Resource Division |  |  | RTOR000068/2023-2024 | 1811/MD | 27/04/2023 | 27/04/2023 | Resource Division | 120.24 | 0 | 0 | 0
5 | MALDAH | Ratua-II | Malda Division | Pukuria Piped Water Supply Scheme | SM/14100 | New | Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room and dismantling abandoned pump house corresponding to Tube Well No 1 at Pukuria Piped Water Supply Scheme at Ratua-II Dev. Block under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Prosanta Mandal, Assistant Engineer | Sudip Kumar Mahata, Junior Engineer | ORD/000950/2023-2024 | 652/MD | 08/02/2024 | 24/03/2024 | J. M. CONSTRUCTION | 4.76 | 0 | 0 | 0
6 | MALDAH | Ratua-II | Malda Division | Pukuria Piped Water Supply Scheme | SM/14100 | New | Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room and dismantling abandoned pump house corresponding to Tube Well No 2 at Pukuria Piped Water Supply Scheme at Ratua-II Dev. Block under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Prosanta Mandal, Assistant Engineer | Sudip Kumar Mahata, Junior Engineer | ORD/000942/2023-2024 | 651/MD | 08/02/2024 | 24/03/2024 | CHAKRABORTY & MANDAL ENTERPRISE | 4.76 | 0 | 0 | 100
7 | MALDAH | Ratua-II | Malda Division | Pukuria Piped Water Supply Scheme | SM/14100 | New | Construction of Boundary Wall at 3rd Tube Well site of Pukuria Water Supply Scheme under Ratua-II Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Prosanta Mandal, Assistant Engineer | Sudip Kumar Mahata, Junior Engineer | ORD/000190/2024-2025 | 2969/MD | 10/06/2024 | 03/05/2025 | M/S A. B. CONSTRUCTION | 7.13 | 0 | 0 | 75
8 | MALDAH | Ratua-II | Malda Division | Pukuria Piped Water Supply Scheme | SM/14100 | New | Construction of Boundary Wall at 4th Tube Well site of Pukuria Water Supply Scheme under Ratua-II Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Prasanta Mandal, Assistant Engineer | Sudip Kumar Mahata, Junior Engineer | ORD/000315/2024-2025 | 3955/MD | 07/08/2024 | 21/09/2024 | MAHA MAYA CONSTRUCTION | 7.12 | 0 | 0 | 100
9 | MALDAH | Ratua-II | Malda Mechanical | Pukuria Piped Water Supply Scheme | SM/14100 | New | New service connection at PUKURIA PWSS T/W NO III Under EE/MLMD PHE DTE DIST. Malda.( Paranpur c c c) |  |  | BILL/02204/2024-2025 | BP-2024-25-524 | 26/09/2024 | 26/09/2024 | W.B.S.E.D.C.LTD | 4.77 | 0 | 0 | 0
10 | MALDAH | Ratua-II | Malda Mechanical | Pukuria Piped Water Supply Scheme | SM/14100 | New | New service connection at pukuria PWSS T/W NO Iv Under EE/MLMD PHE DTE DIST. Malda.( paranpur c c c) |  |  | BILL/02203/2024-2025 | BP-2024-25-523 | 26/09/2024 | 26/09/2024 | W.B.S.E.D.C.LTD | 4.96 | 0 | 0 | 0
11 | MALDAH | Ratua-II | Malda Division | Pukuria Piped Water Supply Scheme | SM/14100 | New | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Pukuria Water Supply Scheme under Ratua-II Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Prosanta Mandal, Assistant Engineer | Sudip Kumar Mahata, Junior Engineer | ORD/000167/2025-2026 | 5794/MD | 13/11/2025 | 12/01/2026 | DUTTA ENTERPRISE | 117.25 | 0 | 0 | 0
12 | MALDAH | Ratua-II | Malda Division | Pukuria Piped Water Supply Scheme | SM/14100 | New | Erection of Property board related to Jal Jeevan Mission works of Paharpur, Sultanpur, Pukuria PWSS under Ratua-II Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Debasis Pal, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000972/2024-2025 | 661/MD | 19/02/2025 | 26/02/2025 | J. M. CONSTRUCTION | 0.73 | 0 | 0 | 0
13 | MALDAH | Ratua-II | Malda Division | Pukuria Piped Water Supply Scheme | SM/14100 | New | Material Requisition To Resource Division |  |  | RTOR000029/2024-2025 | 1039/MD | 18/03/2025 | 18/03/2025 | Resource Division | 24.64 | 0 | 0 | 0
Total | [13 empty] | 1302.38 | 507.83 | 38.99