## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH | Gazole | Malda Mechanical | FATEPUR Piped Water Supply Scheme | SM/14173 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I ,II & III and making compound lighting arrangement at T/W no. I of Fatepur Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/015785) | Assistant Engineer - II | Junior Engineer-06,Junior Engineer-07 | ORD/000380/2023-2024 | 2388/MLMD | 28/07/2023 | 24/01/2024 | NUPUR CHANDRA HALDER | 42.13 | 21.89 | 51.96 | 51
2 | MALDAH | Gazole | Malda Division | FATEPUR Piped Water Supply Scheme | SM/14173 | New | Construction of Boundary Wall at Head Work site of Fatepur Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Arnab Giri, Assistant Engineer | Amit Karmakar, Junior Engineer | ORD/000272/2024-2025 | 3229/MD | 28/06/2024 | 29/08/2025 | THREE BROTHERS CONSTRUCTION & CO | 26.65 | 24.18 | 90.73 | 60
3 | MALDAH | Gazole | Malda Division | FATEPUR Piped Water Supply Scheme | SM/14173 | New | Material Requisition To Resource Division |  |  | RTOR000147/2023-2024 | 124/MD | 06/01/2024 | 06/01/2024 | Resource Division | 121.21 | 0 | 0 | 0
4 | MALDAH | Gazole | Malda Division | FATEPUR Piped Water Supply Scheme | SM/14173 | New | Material Requisition To Resource Division |  |  | RTOR000153/2023-2024 | 243/MD | 10/01/2024 | 10/01/2024 | Resource Division | 13.18 | 0 | 0 | 0
5 | MALDAH | Gazole | Malda Mechanical | FATEPUR Piped Water Supply Scheme | SM/14173 | New | W.B.S.E.D.C.LTD Quotation charge at TW No- I of Fatepur, Pandua CCC in the dist of Malda Under Malda Mechanical Division PHE Dte |  |  | BILL/00776/2024-2025 | BP-2024-25-196 | 22/05/2024 | 22/05/2024 | W.B.S.E.D.C.LTD | 11.26 | 0 | 0 | 0
6 | MALDAH | Gazole | Malda Mechanical | FATEPUR Piped Water Supply Scheme | SM/14173 | New | W.B.S.E.D.C.LTD Quotation charge at TW No- II of Fatepur, Pandua CCC in the dist of Malda Under Malda Mechanical Division PHE Dte |  |  | BILL/00769/2024-2025 | BP-2024-25-195 | 22/05/2024 | 22/05/2024 | W.B.S.E.D.C.LTD | 10.78 | 0 | 0 | 0
7 | MALDAH | Gazole | Malda Division | FATEPUR Piped Water Supply Scheme | SM/14173 | New | Formal work order for the work of Implementation of FATEPUR and its adjoinining mouzas Piped Water Supply Scheme at Gazol Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Arnab Giri, Assistant Engineer | Amit Karmakar, Junior Engineer | ORD/000642/2022-2023 | 1028/MD | 13/03/2023 | 01/04/2026 | GHOSH BROTHERS | 1157.58 | 181.56 | 15.68 | 50
8 | MALDAH | Gazole | Malda Division | FATEPUR Piped Water Supply Scheme | SM/14173 | New | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Fatepur Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Arnab Giri, Assistant Engineer | Amit Karmakar, Junior Engineer | ORD/000002/2025-2026 | 1305/MD | 04/04/2025 | 03/06/2025 | MILLENNIUM ENTERPRISE | 105.3 | 0 | 0 | 0
Total | [13 empty] | 1488.09 | 227.63 | 15.3