## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH | Gazole | Malda Division | RAHIMPUR Piped Water Supply Scheme | SM/14174 | New | Material Requisition To Resource Division |  |  | RTOR000052/2023-2024 | 1811/MD | 27/04/2023 |  | Resource Division | 14.65 | 0 | 0 | 0
2 | MALDAH | Gazole | Malda Mechanical | RAHIMPUR Piped Water Supply Scheme | SM/14174 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. II of RAHIMPUR PWSS, Gazole C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II |  | ORD/000720/2023-2024 | 3004390672 | 11/08/2023 | 09/11/2023 | W.B.S.E.D.C.LTD | 5.39 | 5.39 | 100 | 100
3 | MALDAH | Gazole | Malda Mechanical | RAHIMPUR Piped Water Supply Scheme | SM/14174 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of Rahimpur PWSS, Gazole C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II |  | ORD/000772/2023-2024 | 3004390718 | 16/08/2023 | 14/11/2023 | W.B.S.E.D.C.LTD | 18.35 | 18.35 | 100 | 100
4 | MALDAH | Gazole | Malda Division | RAHIMPUR Piped Water Supply Scheme | SM/14174 | New | Material Requisition To Resource Division |  |  | RTOR000099/2023-2024 | 28/MD | 04/01/2024 |  | Resource Division | 16.25 | 0 | 0 | 0
5 | MALDAH | Gazole | Malda Mechanical | RAHIMPUR Piped Water Supply Scheme | SM/14174 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Rahimpur Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/015255) | Assistant Engineer - II | Junior Engineer-07 | ORD/000324/2023-2024 | 2326/MLMD | 26/07/2023 | 23/11/2023 | JAL PRAVAHIKA PVT. LTD. | 28.25 | 0 | 0 | 82
6 | MALDAH | Gazole | Malda Division | RAHIMPUR Piped Water Supply Scheme | SM/14174 | New | Formal work order for the work of Implementation of Rahimpur Piped Water Supply Scheme at Gazol Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Arnab Giri, Assistant Engineer | Amit Karmakar, Junior Engineer | ORD/000006/2023-2024 | 1571/MD | 10/04/2023 | 05/01/2024 | M/S GUPTA ENTERPRISE | 841.12 | 539.65 | 64.16 | 65
7 | MALDAH | Gazole | Malda Division | RAHIMPUR Piped Water Supply Scheme | SM/14174 | New | Construction of Boundary Wall at 2nd Tube Well site of Rahimpur Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Arnab Giri, Assistant Engineer | Amit Karmakar, Junior Engineer | ORD/000179/2024-2025 | 2954/MD | 10/06/2024 | 10/07/2024 | M/S AMIT KUMAR GUPTA | 7.17 | 0 | 0 | 0
Total | [13 empty] | 931.18 | 563.39 | 60.5