## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH | Gazole | Malda Mechanical | RAHIMPUR Piped Water Supply Scheme | SM/14174 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of Rahimpur PWSS, Gazole C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II |  | ORD/000772/2023-2024 | 3004390718 | 16/08/2023 | 14/11/2023 | W.B.S.E.D.C.LTD | 18.35 | 0 | 0 | 100
2 | MALDAH | Gazole | Malda Mechanical | RAHIMPUR Piped Water Supply Scheme | SM/14174 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. II of RAHIMPUR PWSS, Gazole C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II |  | ORD/000720/2023-2024 | 3004390672 | 11/08/2023 | 09/11/2023 | W.B.S.E.D.C.LTD | 5.39 | 0 | 0 | 100
3 | MALDAH | Gazole | Malda Division | RAHIMPUR Piped Water Supply Scheme | SM/14174 | New | Material Requisition To Resource Division |  |  | RTOR000052/2023-2024 | 1811/MD | 27/04/2023 | 27/04/2023 | Resource Division | 14.65 | 0 | 0 | 0
4 | MALDAH | Gazole | Malda Division | RAHIMPUR Piped Water Supply Scheme | SM/14174 | New | Construction of Boundary Wall at 2nd Tube Well site of Rahimpur Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Arnab Giri, Assistant Engineer | Amit Karmakar, Junior Engineer | ORD/000179/2024-2025 | 2954/MD | 10/06/2024 | 01/02/2025 | M/S AMIT KUMAR GUPTA | 7.17 | 0 | 0 | 50
5 | MALDAH | Gazole | Malda Division | RAHIMPUR Piped Water Supply Scheme | SM/14174 | New | Material Requisition To Resource Division |  |  | RTOR000099/2023-2024 | 28/MD | 04/01/2024 | 04/01/2024 | Resource Division | 16.25 | 0 | 0 | 0
6 | MALDAH | Gazole | Malda Division | RAHIMPUR Piped Water Supply Scheme | SM/14174 | New | Formal work order for the work of Implementation of Rahimpur Piped Water Supply Scheme at Gazol Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Arnab Giri, Assistant Engineer | Amit Karmakar, Junior Engineer | ORD/000006/2023-2024 | 1571/MD | 10/04/2023 | 01/04/2025 | M/S GUPTA ENTERPRISE | 841.12 | 0 | 0 | 90
7 | MALDAH | Gazole | Malda Mechanical | RAHIMPUR Piped Water Supply Scheme | SM/14174 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Rahimpur Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/015255) | Assistant Engineer - II | Junior Engineer-06,Junior Engineer-07 | ORD/000324/2023-2024 | 2326/MLMD | 26/07/2023 | 19/09/2025 | JAL PRAVAHIKA PVT. LTD. | 28.25 | 0 | 0 | 84
8 | MALDAH | Gazole | Malda Division | RAHIMPUR Piped Water Supply Scheme | SM/14174 | New | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Rahimpur Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Arnab Giri, Assistant Engineer | Amit Karmakar, Junior Engineer | ORD/000632/2024-2025 | 5911/MD | 26/11/2024 | 01/10/2025 | TULIP ENGINEERS CO OP. SOCIETY LTD. | 48.65 | 0 | 0 | 20
9 | MALDAH | Gazole | Malda Division | RAHIMPUR Piped Water Supply Scheme | SM/14174 | New | Construction of Boundary Wall at Head Work site of Rahimpur Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Arnab Giri, Assistant Engineer | Amit Karmakar, Junior Engineer | ORD/000844/2024-2025 | 831/MD | 06/03/2025 | 01/10/2025 | M/S GUPTA ENTERPRISE | 28.39 | 0 | 0 | 60
10 | MALDAH | Gazole | Malda Division | RAHIMPUR Piped Water Supply Scheme | SM/14174 | New | Dedicated Pipe laying for better Functionality and Providing Balance FHTC for RAHIMPUR Water Supply Scheme at Gazole Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Arnab Giri, Assistant Engineer | Amit Karmakar, Junior Engineer | ORD/000213/2025-2026 | 3770/MD | 04/08/2025 | 01/01/2026 | M/S GUPTA ENTERPRISE | 11.35 | 0 | 0 | 0
Total | [13 empty] | 1019.57 | 0 | 0