## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Malda Division | Source Augmentation of Khatil Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/14420 | Augmentation | Acceptance cum formal work order for Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement in connection with source Augmentation of Khatil Piped Water Supply Scheme at Bamangola Block of Malda District under Malda Division, PHE Dte. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000756/2022-2023 | 1304/MD | 23/03/2023 | 07/05/2023 | A. L. ENGINEERING SOLUTION | 4.18 | 0 | 0 | 0
2 | MALDAH |  | Malda Division | Source Augmentation of Khatil Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/14420 | Augmentation | Acceptance cum formal work order for Sinking of ( 200mm. Dia. x 150mm. Dia ) Big dia Tube Well No - 3 ( 150.00 Mtr. deep ) by D.R. Rig method using P.V.C. pipe including supply of Materials at KHATIL Water Supply Scheme under Malda Division P.H.E Dte in the District of Malda. (2nd Call) | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000774/2022-2023 | 1432/MD | 29/03/2023 | 28/04/2023 | ASHIS CONSTRUCTION | 7.56 | 0 | 0 | 100
3 | MALDAH |  | Malda Division | Source Augmentation of Khatil Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/14420 | Augmentation | Construction of Boundary Wall of Khatil Water Supply Scheme under Bamongola Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Amit Biswas, Assistant Engineer | Mukaddar Parvage, Junior Engineer | ORD/001002/2023-2024 | 1181/MD | 14/03/2024 | 13/04/2024 | M/S EHAN ENTERPRISE | 10.2 | 0 | 0 | 0
4 | MALDAH |  | Malda Division | Source Augmentation of Khatil Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/14420 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Khatil Water Supply Scheme under Bamongola Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Amit Biswas, Assistant Engineer | Mukaddar Parvage, Junior Engineer | ORD/001003/2023-2024 | 1182/MD | 14/03/2024 | 28/04/2024 | S. N. CONSTRUCTION | 21.18 | 0 | 0 | 0
5 | MALDAH |  | Malda Mechanical | Source Augmentation of Khatil Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/14420 | Augmentation | QUOTATION PAYMENT FOR KHATIL T/W III UNDER BAMONGOLA CCC UNDER MALDA DISTRICT |  |  | BILL/00759/2024-2025 | BP-2024-25-194 | 22/05/2024 | 22/05/2024 | W.B.S.E.D.C.LTD | 4.69 | 0 | 0 | 0
6 | MALDAH |  | Malda Mechanical | Source Augmentation of Khatil Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/14420 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. III of Khatil Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/015034) | Assistant Engineer - II | Junior Engineer-03 | ORD/000382/2023-2024 | 2390/MLMD | 28/07/2023 | 11/07/2025 | NEOGI ENTERPRISE. | 11.1 | 0 | 0 | 20
7 | MALDAH |  | Malda Division | Source Augmentation of Khatil Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/14420 | Augmentation | Augmentation of Head work site Pump House, Pump House No.-2, Earth filling and 2 Nos. Boundary wall at Khatil Water Supply Scheme at Bamangola Dev. Block under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000778/2024-2025 | 296/MD | 29/01/2025 | 06/03/2026 | M/S ROY CONSTRUCTION | 8.52 | 0 | 0 | 0
8 | MALDAH |  | Malda Division | Source Augmentation of Khatil Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/14420 | Augmentation | Acceptance cum formal work order for Extension of Pipe line and replacing of damage A.C /upvc pipe line by different dia UPVC pipe for KHATIL Piped Water Supply Scheme at Bamangola Dev. Block in the District of Malda under Malda Division, PHE Dte. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000511/2022-2023 | 414/MD | 02/02/2023 | 01/03/2025 | M/S AMIT KUMAR GUPTA | 74.79 | 0 | 0 | 100
Total | [13 empty] | 142.2 | 0 | 0