## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH | Gazole | Malda Division | RAJARAM CHAK PIPED WATER SUPPLY SCHEME | SM/14461 | New | Material Requisition To Resource Division |  |  | RTOR000042/2023-2024 | 1811/MD | 27/04/2023 | 27/04/2023 | Resource Division | 27.36 | 0 | 0 | 0
2 | MALDAH | Gazole | Malda Division | RAJARAM CHAK PIPED WATER SUPPLY SCHEME | SM/14461 | New | Acceptance cum formal work order for Construction of 5.40 mtr.X 3.6 mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement at Head Work Site of RAJARAMCHAK Water Supply Scheme at Gazole Block of Malda District under Malda Division, PHE Dte. | Mr. Arnab Giri, Assistant Engineer | Amit Karmakar, Junior Engineer ,Biswajit Gosh, Junior Engineer | ORD/000682/2022-2023 | 1131/MD | 20/03/2023 | 04/05/2023 | ABHIJIT PAUL | 6.57 | 0 | 0 | 100
3 | MALDAH | Gazole | Malda Division | RAJARAM CHAK PIPED WATER SUPPLY SCHEME | SM/14461 | New | Acceptance cum formal work order for Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement at 2nd Tube Well site. of RAJARAMCHAK Water Supply Scheme at Gazole Block of Malda District under Malda Division, PHE Dte. | Mr. Arnab Giri, Assistant Engineer | Amit Karmakar, Junior Engineer ,Biswajit Gosh, Junior Engineer | ORD/000684/2022-2023 | 1136/MD | 20/03/2023 | 04/05/2023 | RAJIB MANI | 4.17 | 0 | 0 | 100
4 | MALDAH | Gazole | Malda Division | RAJARAM CHAK PIPED WATER SUPPLY SCHEME | SM/14461 | New | Material Requisition To Resource Division |  |  | RTOR000162/2023-2024 | 253/MD | 10/01/2024 | 10/01/2024 | Resource Division | 7.85 | 0 | 0 | 0
5 | MALDAH | Gazole | Malda Mechanical | RAJARAM CHAK PIPED WATER SUPPLY SCHEME | SM/14461 | New | W.B.S.E.D.C.LTD Quotation charge at TW No- I of Rajaramchak, Gazol CCC in the dist of Malda Under Malda Mechanical Division PHE Dte. |  |  | BILL/03685/2023-2024 | BP-2023-24-668 | 11/03/2024 | 11/03/2024 | W.B.S.E.D.C.LTD | 4.18 | 0 | 0 | 0
6 | MALDAH | Gazole | Malda Mechanical | RAJARAM CHAK PIPED WATER SUPPLY SCHEME | SM/14461 | New | W.B.S.E.D.C.LTD Quotation charge at TW No- II of Rajaramchak, Gazole CCC in the dist of Malda Under Malda Mechanical Division PHE Dte. |  |  | BILL/03718/2023-2024 | BP-2023-24-709 | 18/03/2024 | 18/03/2024 | W.B.S.E.D.C.LTD | 5.4 | 0 | 0 | 0
7 | MALDAH | Gazole | Malda Division | RAJARAM CHAK PIPED WATER SUPPLY SCHEME | SM/14461 | New | Formal work order for the work of Implementation of RAJARAMCHAK Piped Water Supply Scheme at Gazole Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Mr. Arnab Giri, Assistant Engineer | Amit Karmakar, Junior Engineer | ORD/000371/2023-2024 | 3087/MD | 10/08/2023 | 01/10/2025 | MONDAL CONSTRUCTION | 234.19 | 0 | 0 | 55
8 | MALDAH | Gazole | Malda Mechanical | RAJARAM CHAK PIPED WATER SUPPLY SCHEME | SM/14461 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I & II and making compound lighting arrangement at T/W no. I of Rajaram Chak Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/013552) | Assistant Engineer - II | Junior Engineer-06,Junior Engineer-07 | ORD/000492/2023-2024 | 2564/MLMD | 04/08/2023 | 27/10/2025 | M/S. KUNDU CONSTRACTION | 28.76 | 0 | 0 | 88
9 | MALDAH | Gazole | Malda Division | RAJARAM CHAK PIPED WATER SUPPLY SCHEME | SM/14461 | New | Laying of Distribution of UPVC Pipeline of RAJARAM CHAK Piped Water Supply Scheme at Gazole Block of Malda District under Malda Division, PHE Dte., Govt. of West Bengal. | Mr. Arnab Giri, Assistant Engineer | Amit Karmakar, Junior Engineer | ORD/000710/2023-2024 | 4640/MD | 24/11/2023 | 01/10/2025 | M/S MOON LIGHT CONSTRUCTION & CO. | 51.23 | 0 | 0 | 25
10 | MALDAH | Gazole | Malda Division | RAJARAM CHAK PIPED WATER SUPPLY SCHEME | SM/14461 | New | Construction of Boundary Wall at Head Work site of Rajaramchak Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Arnab Giri, Assistant Engineer | Amit Karmakar, Junior Engineer | ORD/000269/2024-2025 | 3227/MD | 28/06/2024 | 01/02/2025 | MONDAL CONSTRUCTION | 20.25 | 0 | 0 | 0
Total | [13 empty] | 389.96 | 0 | 0