## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Malda Division | Source Augmentation of Kankot Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15057 | Augmentation | Acceptance cum formal work order for Extension of Pipe line and Replacing of damaged A.C pipe line by different dia UPVC pipe for Kankot Water Supply Scheme in Ratua I Block for Installation of FHTC under Malda Division PHE. Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer |  | ORD/000563/2022-2023 | 754/MD | 17/02/2023 | 19/03/2023 | PRITAM ENTERPRISE | 4.76 | 0 | 0 | 0
2 | MALDAH |  | Malda Division | Source Augmentation of Kankot Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15057 | Augmentation | Acceptance cum formal work order for Sinking of 01(one) nos. 250mm. Dia. x 150mm. Big dia Tube Well 138 Mtr. deep by D.R. Rig method using UPVC pipe & Strainer in connection with Source Augmentation of KANKOT Piped Water Supply Scheme under Malda Division P.H.E Dte in the District of Malda. (2nd Call) | Mr. Sumit Kumar Ghosh, Assistant Engineer |  | ORD/000777/2022-2023 | 1435/MD | 29/03/2023 | 28/04/2023 | ABHIJIT PAUL | 8.68 | 0 | 0 | 0
3 | MALDAH |  | Malda Division | Source Augmentation of Kankot Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15057 | Augmentation | Acceptance cum formal work order for Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement in connection with source Augmentation of Kankot Piped Water Supply Scheme at Ratua-I Block of Malda District under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer |  | ORD/000724/2022-2023 | 1198/MD | 21/03/2023 | 05/05/2023 | PRITAM ENTERPRISE | 4.16 | 0 | 0 | 0
4 | MALDAH |  | Malda Mechanical | Source Augmentation of Kankot Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15057 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. III of Kankot Water Supply Scheme in the District of Malda under Mechanical Division, PHE Dte.(TSM/017203) | Assistant Engineer - II | Junior Engineer-05 | ORD/000574/2023-2024 | 2623/MLMD | 10/08/2023 | 26/06/2026 | M/S SABANA CONSTRUCTION | 11.44 | 0 | 0 | 87
Total | [13 empty] | 29.04 | 0 | 0