## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Malda Division | Source Augmentation of Rampur Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15062 | Augmentation | Acceptance cum formal work order for Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement in connection with source Augmentation of Rampur Piped Water Supply Scheme at Chanchal-II Block of Malda District under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Junior Engineer | ORD/000753/2022-2023 | 1301/MD | 23/03/2023 | 07/05/2023 | SUBINDU PRAMANIK | 4.19 | 0 | 0 | 0
2 | MALDAH |  | Malda Division | Source Augmentation of Rampur Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15062 | Augmentation | Acceptance cum formal work order for Laying of additional UPVC Pipe line in connection with Source Augmentation of Rampur Piped Water Supply Scheme, Chanchal II Block under Malda Division, P.H.E. Dte. in the District of Malda | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000573/2022-2023 | 764/MD | 17/02/2023 | 19/03/2023 | PACIFIC ENGINEER'S CO-OPERATIVE SOCIETY LTD. | 18.18 | 0 | 0 | 100
3 | MALDAH |  | Malda Division | Source Augmentation of Rampur Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15062 | Augmentation | Acceptance cum formal work order for Sinking of ( 200mm. Dia. x 150mm. Dia ) Big dia Tube Well ( 250.00 Mtr. deep ) by D.R. Rig method using P.V.C. pipe including supply of Materials at Rampur Water Supply Scheme under Malda Division P.H.E Dte in the District of Malda. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Junior Engineer | ORD/000769/2022-2023 | 1397/MD | 28/03/2023 | 27/04/2023 | A. L. ENGINEERING SOLUTION | 13.37 | 0 | 0 | 100
4 | MALDAH |  | Malda Mechanical | Source Augmentation of Rampur Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15062 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. III of Rampur Water Supply Scheme in the District of Malda under Mechanical Division, PHE Dte. (TSM/016552) | Assistant Engineer - II | Junior Engineer-05 | ORD/000577/2023-2024 | 2626/MLMD | 10/08/2023 | 23/11/2025 | JIBON GHOSH. | 11.42 | 0 | 0 | 88
5 | MALDAH |  | Malda Division | Source Augmentation of Rampur Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15062 | Augmentation | Interconnection between New Tube Well and Existing UPVC/DI/HDPE pipe line in connection with Source Augmentation of Rampur Piped Water Supply Scheme at Chanchal-II Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000585/2024-2025 | 5619/MD | 06/11/2024 | 06/12/2024 | M/S JHA CONSTRUCTION | 2.88 | 0 | 0 | 0
6 | MALDAH |  | Malda Division | Source Augmentation of Rampur Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15062 | Augmentation | Replacement of existing tube well by 200x200 mm dia. and 250 M Deep by Big Dia Tube Well at 2nd Tube Well site of Rampur Piped Water Supply Scheme at Chanchal-II block of Malda District under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000463/2024-2025 | 4820/MD | 13/09/2024 | 14/12/2024 | M/S. NAYAMEE ENGINEERING & CONSTRUCTIONS | 13.75 | 0 | 0 | 100
7 | MALDAH |  | Malda Division | Source Augmentation of Rampur Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15062 | Augmentation | Augmentation work of OHR, Pump House and Boundary Wall of Rampur Water Supply Scheme at Chanchal-II Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer ,Yusuf Sk, Junior Engineer | ORD/000179/2025-2026 | 2894/MD | 17/06/2025 | 16/08/2025 | S. N. CONSTRUCTION | 29.67 | 0 | 0 | 0
Total | [13 empty] | 93.44 | 0 | 0