## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Malda Mechanical | Source Augmentation of Adhna Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15063 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at P/H No. III of Adhna PWSS, Pandua C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II |  | ORD/000778/2023-2024 | 3004387448 | 18/08/2023 | 16/11/2023 | W.B.S.E.D.C.LTD | 3.51 | 0 | 0 | 100
2 | MALDAH |  | Malda Division | Source Augmentation of Adhna Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15063 | Augmentation | Acceptance cum formal work order for Extension of Pipe line and replacing of damage uPVC pipe line by different dia UPVC pipe for ADHNA Piped Water Supply Scheme at Gazole Dev. Block of Malda District under Malda Division, PHE Dte. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000556/2022-2023 | 1181/MD | 21/03/2023 | 20/04/2023 | GOBINDA ENTERPRISE | 40.5 | 0 | 0 | 90
3 | MALDAH |  | Malda Division | Source Augmentation of Adhna Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15063 | Augmentation | Acceptance cum formal work order for Sinking of ( 200mm. Dia. x 150mm. Dia ) Big dia Tube Well No - 3 ( 150.00 Mtr. deep ) by D.R. Rig method using P.V.C. pipe including supply of Materials at ADHNA Water Supply Scheme under Malda Division P.H.E Dte in the District of Malda. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000715/2022-2023 | 1173/MD | 20/03/2023 | 19/04/2023 | JAYA ENTERPRISE | 7.56 | 0 | 0 | 100
4 | MALDAH |  | Malda Division | Source Augmentation of Adhna Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15063 | Augmentation | Acceptance cum formal work order for Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement in connection with source Augmentation of Adhna Piped Water Supply Scheme at Gazole Block of Malda District under Malda Division, PHE Dte. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000725/2022-2023 | 1199/MD | 21/03/2023 | 05/05/2023 | M/S GHOSH ENTERPRISE | 4.17 | 0 | 0 | 100
5 | MALDAH |  | Malda Mechanical | Source Augmentation of Adhna Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15063 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. III of Source Augmentation Adhna Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/016220) | Assistant Engineer - II | Junior Engineer-06,Junior Engineer-07 | ORD/000596/2023-2024 | 2718/MLMD | 14/08/2023 | 10/02/2024 | JOY ENTERPRISE. | 10.67 | 0 | 0 | 100
6 | MALDAH |  | Malda Division | Source Augmentation of Adhna Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15063 | Augmentation | Augmentation of Head work site Pump House,Pump House No.-2 ,Earth filling and 2 Nos. Boundary wall at ADHNA Water Supply scheme at Gazole Dev. Block under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000876/2024-2025 | 1115/MD | 21/03/2025 | 01/10/2025 | GOBINDA ENTERPRISE | 7.83 | 0 | 0 | 0
7 | MALDAH |  | Malda Division | Source Augmentation of Adhna Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15063 | Augmentation | Replacement of 200 mm dia. all through Big Dia. Tube Well at Head Work site (150m Deep) by D.R. Rig. Method using P.V.C. pipe & filter including supply of materials of ADHNA Piped Water Supply Scheme at Gazole Dev. Block under Malda Division, PHE Dte. Govt. of West Bengal. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000115/2025-2026 | 2466/MD | 28/05/2025 | 27/07/2025 | GOBINDA ENTERPRISE | 9.82 | 0 | 0 | 0
8 | MALDAH |  | Malda Division | Source Augmentation of Adhna Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15063 | Augmentation | Construction of Boundary Wall of Adhna Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000082/2025-2026 | 2267/MD | 21/05/2025 | 05/07/2025 | M/S. B. K. ASSOCIATES | 10.13 | 0 | 0 | 0
9 | MALDAH |  | Malda Division | Source Augmentation of Adhna Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15063 | Augmentation | Sinking of 200 mm (all through) Big Dia. Tube-Well NO-02 (170 ) M Deep by D.R Rig. Method using P.V.C pipe & Filter including supply of materials at ADHNA Water Supply Scheme of Gazol Block under Malda Division, PHE Dte, Govt. of West Bengal | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000458/2024-2025 | 4812/MD | 13/09/2024 | 16/02/2025 | A. D. D. ASSOCIATES | 10.6 | 0 | 0 | 100
Total | [13 empty] | 104.79 | 0 | 0