## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Malda Division | Source Augmentation of Arjuna Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15074 | Augmentation | Acceptance cum formal work order for Extension of Pipe line and Replacing of damaged A.C pipe line by different dia UPVC pipeline connection to Source Augmentation of Arjuna Piped Water Supply scheme at Harishchandrapur-II under Malda Division, P.H.E.Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Junior Engineer | ORD/000564/2022-2023 | 755/MD | 17/02/2023 | 19/03/2023 | GHOSH CONSTRUCTION | 15.53 | 15.5 | 99.86 | 0
2 | MALDAH |  | Malda Division | Source Augmentation of Arjuna Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15074 | Augmentation | Acceptance cum formal work order for Sinking of 01(one) nos. 250mm. Dia. x 150mm. Big dia Tube Well 138 Mtr. deep by D.R. Rig method using UPVC pipe & Strainer in connection with Source Augmentation of ARJUNA Piped Water Supply Scheme under Malda Division P.H.E Dte in the District of Malda. (2nd Call) | Mr. Sumit Kumar Ghosh, Assistant Engineer |  | ORD/000775/2022-2023 | 1433/MD | 29/03/2023 | 28/04/2023 | ABHIJIT PAUL | 8.68 | 8.68 | 100 | 100
3 | MALDAH |  | Malda Division | Source Augmentation of Arjuna Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15074 | Augmentation | Acceptance cum formal work order for Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement in connection with source Augmentation of Arjuna Piped Water Supply Scheme at Harishchandrapur-II Block of Malda District under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Susanta Pal, JE_Deputation | ORD/000749/2022-2023 | 1297/MD | 23/03/2023 | 07/05/2023 | SAYEM ENTERPRISE | 4.2 | 0 | 0 | 100
4 | MALDAH |  | Malda Mechanical | Source Augmentation of Arjuna Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15074 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. III of Arjuna Water Supply Scheme in the District of under Malda Mechanical Division, PHE Dte.(TSM/016722) | Assistant Engineer - II | Junior Engineer-05 | ORD/000564/2023-2024 | 2617/MLMD | 10/08/2023 | 01/04/2025 | NEOGI ENTERPRISE. | 10.92 | 8.12 | 74.36 | 100
5 | MALDAH |  | Malda Division | Source Augmentation of Arjuna Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15074 | Augmentation | Interconnection between New Tube Well and Existing UPVC/DI/HDPE pipe line in connection with Source Augmentation of ARJUNA Piped Water Supply Scheme at Harishchandrapur-II Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Susanta Pal, JE_Deputation | ORD/000194/2024-2025 | 2898/MD | 07/06/2024 | 01/02/2025 | SK ENTERPRISE | 1.41 | 0 | 0 | 100
6 | MALDAH |  | Malda Mechanical | Source Augmentation of Arjuna Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15074 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at P/H No. III of Arjuna PWSS, Bhaluka C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. |  |  | BILL/02547/2023-2024 | BP-2023-24-448 | 10/01/2024 | 10/01/2024 | W.B.S.E.D.C.LTD | 4.4 | 0 | 0 | 0
7 | MALDAH |  | Malda Division | Source Augmentation of Arjuna Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15074 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Arjuna Mouza of Arjuna Water Supply Scheme under Harishchandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Susanta Pal, JE_Deputation | ORD/000734/2024-2025 | 10 | 03/01/2025 | 17/02/2025 | TWO BROTHERS CONSTRUCTION | 10.01 | 0 | 0 | 0
8 | MALDAH |  | Malda Division | Source Augmentation of Arjuna Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15074 | Augmentation | Augmentation work of OHR, Pump House and Boundary Wall of Arjuna Water Supply Scheme at Harishchandrapur-II Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Susanta Pal, JE_Deputation | ORD/000860/2024-2025 | 1053/MD | 18/03/2025 | 01/06/2025 | M/S KUNDU CONSTRUCTION | 28.76 | 0 | 0 | 0
Total | [13 empty] | 83.9 | 32.3 | 38.5