## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Malda Division | Source Augmentation of Dalla Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15079 | Augmentation | Acceptance cum formal work order for Sinking of ( 250mm. Dia. x 200mm. Dia ) Big dia Tube Well No - 3 ( 78.00 Mtr. deep ) by D.R. Rig method using P.V.C. pipe & Gravel Filter including supply of Materials at DALLA Water Supply Scheme of Habibpur Block under Malda Division P.H.E Dte in the District of Malda. | Mr. Arnab Giri, Assistant Engineer | Biswajit Gosh, Junior Engineer,Mukaddar Parvage, Junior Engineer | ORD/000770/2022-2023 | 1428/MD | 29/03/2023 | 28/04/2023 | ABHIJIT PAUL | 6.86 | 5.98 | 87.18 | 100
2 | MALDAH |  | Malda Division | Source Augmentation of Dalla Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15079 | Augmentation | Acceptance cum formal work order for Sinking of ( 250mm. Dia. x 200mm. Dia ) Big dia Tube Well No - 4 ( 78.00 Mtr. deep ) by D.R. Rig method using P.V.C. pipe & Gravel Filter including supply of Materials at DALLA Water Supply Scheme of Habibpur Block under Malda Division P.H.E Dte in the District of Malda. (2nd Call) | Mr. Arnab Giri, Assistant Engineer | Biswajit Gosh, Junior Engineer,Mukaddar Parvage, Junior Engineer | ORD/000771/2022-2023 | 1429/MD | 29/03/2023 | 28/04/2023 | ABHIJIT PAUL | 6.86 | 6.17 | 90.04 | 100
3 | MALDAH |  | Malda Mechanical | Source Augmentation of Dalla Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15079 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at T/W No. IV of Dalla, Aiho C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II |  | ORD/000924/2023-2024 | 3004413357 | 05/09/2023 | 04/12/2023 | W.B.S.E.D.C.LTD | 4.77 | 4.77 | 100 | 100
4 | MALDAH |  | Malda Division | Source Augmentation of Dalla Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15079 | Augmentation | Construction of Boundary Wall of Tubewell site at Dalla Mouza of Dalla Water Supply Scheme under Habibpur Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/001018/2023-2024 | 1186/MD | 14/03/2024 | 13/04/2024 | J. M. CONSTRUCTION | 11.89 | 9.92 | 83.43 | 75
5 | MALDAH |  | Malda Division | Source Augmentation of Dalla Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15079 | Augmentation | Acceptance cum formal work order for Construction of 2 (two) Nos 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement in connection with source Augmentation of Dalla Piped Water Supply Scheme at Habibpur Block of Malda District under Malda Division, PHE Dte. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000755/2022-2023 | 1303/MD | 23/03/2023 | 07/05/2023 | M/S BHARATI CONSTRUCTION | 8.34 | 8.32 | 99.74 | 100
6 | MALDAH |  | Malda Mechanical | Source Augmentation of Dalla Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15079 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. III & IV of Dalla Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/016720) | Assistant Engineer - II | Junior Engineer-03 | ORD/000560/2023-2024 | 2615/MLMD | 10/08/2023 | 06/02/2024 | ANIMA ENTERPRISE | 22.09 | 22.03 | 99.72 | 100
7 | MALDAH |  | Malda Division | Source Augmentation of Dalla Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15079 | Augmentation | Devlopment of 200 mm dia. (90 Mtr. Deep) Big dia. Tube Well at Head Work Site by using suitable Air compressor at DALLA Piped Water Supply Scheme of Habibpur Block under Malda Division, PHE Dte. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000977/2023-2024 | 456/MD | 19/01/2024 | 26/01/2024 | ABHIJIT PAUL | 0.68 | 0.68 | 100 | 100
8 | MALDAH |  | Malda Division | Source Augmentation of Dalla Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15079 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000021/2024-2025 | 3997/MD | 08/08/2024 | 08/08/2024 | Resource Division | 7.39 | 0 | 0 | 0
9 | MALDAH |  | Malda Mechanical | Source Augmentation of Dalla Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15079 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at T/W No. III of Dalla, Aiho C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. |  |  | BILL/02468/2023-2024 | BP-2023-24-401 | 03/01/2024 | 03/01/2024 | W.B.S.E.D.C.LTD | 4.25 | 0 | 0 | 0
10 | MALDAH |  | Malda Division | Source Augmentation of Dalla Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15079 | Augmentation | Acceptance cum formal work order for Extension of Pipe line and replacing of damage uPVC pipe line by different dia UPVC pipe for DALLA Piped Water Supply Scheme (Moua-Aragacchhi, JL-No. 57) at Habibpur Dev. Block of Malda District under Malda Division, PHE Dte. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000736/2022-2023 | 1208/MD | 21/03/2023 | 01/04/2024 | EUREKA UNEMPLOYED ENGINEERS CO-OPERATIVE SOCIETY LTD. | 22.03 | 20.79 | 94.37 | 100
11 | MALDAH |  | Malda Division | Source Augmentation of Dalla Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15079 | Augmentation | Acceptance cum formal work order for Extension of Pipe line and replacing of damage uPVC pipe line by different dia UPVC pipe for DALLA Piped Water Supply Scheme (Mouza-Dalla, JL No. 54) at Habibpur Dev. Block of Malda District under Malda Division, PHE Dte. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000738/2022-2023 | 1210/MD | 21/03/2023 | 16/03/2024 | TARUN KUMAR DEY | 28.46 | 26.39 | 92.73 | 100
Total | [13 empty] | 123.61 | 105.04 | 84.98