## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Malda Division | Source Augmentation of Mabrakpur Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15080 | Augmentation | Acceptance cum formal work order for Extension of Pipe line and replacing of damage uPVC pipe line by different dia UPVC pipe for MABARAKPUR Piped Water Supply Scheme (Mouza- Jalkar Bithan, JL No. 115) at Old Malda Dev. Block of Malda District under Malda Division, PHE Dte. | Mr. Amit Biswas, Assistant Engineer | Bikash Balo, Junior Engineer | ORD/000706/2022-2023 | 1164/MD | 20/03/2023 | 04/05/2023 | AVIK KUMAR GHOSH | 27.37 | 13.46 | 49.17 | 85
2 | MALDAH |  | Malda Division | Source Augmentation of Mabrakpur Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15080 | Augmentation | Design, Fabrication, Supplying, Installation, Commissioning,and 3 (three) months Trial Run and 25 cum/hr. capacity of Iron Elimination Plants (Pressure type) with provision of polishing unit alongwith Construction of 3.60 mtr.X 3.00 mtr Blower Room in connection with source Augmentation at 3rd Tube Well site of MABARAKPUR Water Supply Scheme of Old Malda Block under Malda Division, P.H.E.Dte. in the District of Malda. | Mr. Arnab Giri, Assistant Engineer,Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer | ORD/000608/2023-2024 | 4112/MD | 10/10/2023 | 07/02/2024 | M/S AMIT KUMAR GUPTA | 14.74 | 13.29 | 90.15 | 90
3 | MALDAH |  | Malda Division | Source Augmentation of Mabrakpur Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15080 | Augmentation | Acceptance cum formal work order for Extension of Pipe line and replacing of damage uPVC pipe line by different dia UPVC pipe for MABARAKPUR Piped Water Supply Scheme (Moua Mabrakpur, JL No.- 123 & Mouza-Muchia, JL No. 124) at Old Malda Dev. Block of Malda District under Malda Division, PHE Dte. | Mr. Amit Biswas, Assistant Engineer | Bikash Balo, Junior Engineer | ORD/000699/2022-2023 | 1156/MD | 20/03/2023 | 04/05/2023 | TARUN KUMAR DEY | 41.74 | 40.94 | 98.06 | 100
4 | MALDAH |  | Malda Division | Source Augmentation of Mabrakpur Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15080 | Augmentation | Acceptance cum formal work order for Sinking of ( 250mm. Dia. x 200mm. Dia ) Big dia Tube Well No - 3 ( 99.00 Mtr. deep ) by D.R. Rig method using P.V.C. pipe & Gravel Filter including supply of Materials at MABARAKPUR Water Supply Scheme of Old Malda Block under Malda Division P.H.E Dte in the District of Malda. | Mr. Amit Biswas, Assistant Engineer | Bikash Balo, Junior Engineer | ORD/000707/2022-2023 | 1165/MD | 20/03/2023 | 19/04/2023 | ASHIS CONSTRUCTION | 7.79 | 7.03 | 90.24 | 100
5 | MALDAH |  | Malda Mechanical | Source Augmentation of Mabrakpur Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15080 | Augmentation | Supply, installation, commissioning & Trial operation of electro-mechanical components at T/W no III & IV of Source Augmentation Mabarakpur Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/016719) | Assistant Engineer - II | Junior Engineer-07 | ORD/000700/2023-2024 | 2775/MLMD | 14/08/2023 | 10/02/2024 | SUDIP DEY | 21.81 | 21.54 | 98.77 | 100
6 | MALDAH |  | Malda Division | Source Augmentation of Mabrakpur Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15080 | Augmentation | Acceptance cum formal work order for Construction of 2 (two) Nos 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement in connection with source Augmentation of Mobarakpur Piped Water Supply Scheme at Old Malda Block of Malda District under Malda Division, PHE Dte. | Mr. Amit Biswas, Assistant Engineer | Bikash Balo, Junior Engineer | ORD/000730/2022-2023 | 1204/MD | 21/03/2023 | 05/05/2023 | M. S. AGENCY | 8.3 | 8.28 | 99.83 | 100
7 | MALDAH |  | Malda Division | Source Augmentation of Mabrakpur Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15080 | Augmentation | Acceptance cum formal work order for Sinking of ( 250mm. Dia. x 200mm. Dia ) Big dia Tube Well No - 4 ( 99.00 Mtr. deep ) by D.R. Rig method using P.V.C. pipe & Gravel Filter including supply of Materials at MABARAKPUR Water Supply Scheme of Old Malda Block under Malda Division P.H.E Dte in the District of Malda. | Mr. Amit Biswas, Assistant Engineer | Bikash Balo, Junior Engineer | ORD/000708/2022-2023 | 1166/MD | 20/03/2023 | 19/04/2023 | ASHIS CONSTRUCTION | 7.79 | 6.2 | 79.53 | 100
8 | MALDAH |  | Malda Division | Source Augmentation of Mabrakpur Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15080 | Augmentation | Construction of Boundary Wall and pathway at 3rd Tube well Site of MOBARAKPUR Piped Water Supply Scheme at Old Malda Block under Malda Division, P.H.E.Dte. in the District of Malda. | Mr. Amit Biswas, Assistant Engineer | Bikash Balo, Junior Engineer | ORD/000908/2023-2024 | 286/MD | 11/01/2024 | 25/02/2024 | M. S. AGENCY | 7.66 | 7.61 | 99.26 | 100
9 | MALDAH |  | Malda Division | Source Augmentation of Mabrakpur Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15080 | Augmentation | Construction of Boundary Wall at 4th Tube well Site of MOBARAKPUR Piped Water Supply Scheme at Old Malda Block under Malda Division, P.H.E.Dte. in the District of Malda. | Mr. Amit Biswas, Assistant Engineer | Bikash Balo, Junior Engineer | ORD/000961/2023-2024 | 712/MD | 09/02/2024 | 25/03/2024 | S. R. ENTERPRISE | 6.71 | 6.7 | 99.83 | 100
10 | MALDAH |  | Malda Division | Source Augmentation of Mabrakpur Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15080 | Augmentation | Augmentation work of Boundary wall, Pump House, Blower Room RCC Over Head Reservoir and Construction Pathway & Approach Road at Head Work Site of MOBARAKPUR Water Supply Scheme of Old Malda Block under Malda Division, P.H.E.Dte. in the District of Malda. | Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer | ORD/000156/2025-2026 | 2707/MD | 04/06/2025 | 18/08/2025 | SAHA CONSTRUCTION | 19.71 | 0 | 0 | 0
11 | MALDAH |  | Malda Division | Source Augmentation of Mabrakpur Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15080 | Augmentation | Augmentation work of Boundary wall, Pump House and Construction of Toilet at 2nd Tube Well Site of MOBARAKPUR Water Supply Scheme of Old Malda Block under Malda Division, P.H.E.Dte. in the District of Malda. | Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer | ORD/000022/2025-2026 | 1740/MD | 08/05/2025 | 16/12/2025 | M/S DEY ENTERPRISE | 5.78 | 0 | 0 | 100
Total | [13 empty] | 169.42 | 125.04 | 73.81