## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Malda Division | Source Augmentation of Bihari Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15083 | Augmentation | Acceptance cum formal work order for Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement in connection with source Augmentation of Bihari Piped Water Supply Scheme at Ratua-I Block of Malda District under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Tapan Haldar, Junior Engineer | ORD/000721/2022-2023 | 1195/MD | 21/03/2023 | 05/05/2023 | M/S MAJAF CONSTRUCTION | 4.17 | 0 | 0 | 0
2 | MALDAH |  | Malda Division | Source Augmentation of Bihari Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15083 | Augmentation | Acceptance cum formal work order for Sinking of 01(one) nos. 250mm. Dia. x 150mm. Big dia Tube Well 138 Mtr. deep by D.R. Rig method using UPVC pipe & Strainer in connection with Source Augmentation of BIHARI Piped Water Supply Scheme under Malda Division P.H.E Dte in the District of Malda. (2nd Call) | Mr. Sumit Kumar Ghosh, Assistant Engineer | Tapan Haldar, Junior Engineer | ORD/000776/2022-2023 | 1434/MD | 29/03/2023 | 28/04/2023 | ABHIJIT PAUL | 8.68 | 0 | 0 | 0
3 | MALDAH |  | Malda Division | Source Augmentation of Bihari Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15083 | Augmentation | Acceptance cum formal work order for Laying of Distribution pipe line for Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA ) under command area of Rampur village of Bihari Water Supply Scheme under Malda Division PHE. Dte in The District of Malda. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Tapan Haldar, Junior Engineer | ORD/000558/2022-2023 | 749/MD | 17/02/2023 | 19/03/2023 | M/S. NAYAMEE ENGINEERING & CONSTRUCTIONS | 5.67 | 5.35 | 94.37 | 100
4 | MALDAH |  | Malda Mechanical | Source Augmentation of Bihari Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15083 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. III of Behari Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/016679) | Assistant Engineer - II | Junior Engineer-05 | ORD/000566/2023-2024 | 2618/MLMD | 10/08/2023 | 06/02/2024 | NEOGI ENTERPRISE. | 10.92 | 3.07 | 28.08 | 56
Total | [13 empty] | 29.43 | 8.41 | 28.58