## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Malda Division | Laying of additional pipe line at various Piped Water Supply Schemes under Harishchandrapur-I & II Block under Malda Division, PHE Dte. | SM/15086 | Augmentation | Acceptance cum formal work order for Laying of additional pipeline for Talbangura Piped Water Supply Scheme in Harischandrapur II Block for Installation of FHTC under Malda Division PHE. Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000570/2022-2023 | 761/MD | 17/02/2023 | 19/03/2023 | M/S N. N. ENTERPRISE | 19.12 | 19.05 | 99.65 | 100
2 | MALDAH |  | Malda Division | Laying of additional pipe line at various Piped Water Supply Schemes under Harishchandrapur-I & II Block under Malda Division, PHE Dte. | SM/15086 | Augmentation | Acceptance cum formal work order for Laying of additional pipeline for Daulatpur Piped Water Supply Scheme in Harischandrapur II Block for Installation of FHTC under Malda Division PHE. Dte. (Part-I) | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000559/2022-2023 | 750/MD | 17/02/2023 | 19/03/2023 | M/S FOUR STAR CONSTRUCTION | 14.54 | 14.37 | 98.8 | 100
3 | MALDAH |  | Malda Division | Laying of additional pipe line at various Piped Water Supply Schemes under Harishchandrapur-I & II Block under Malda Division, PHE Dte. | SM/15086 | Augmentation | Acceptance cum formal work order for Laying of additional pipeline Gannadia Piped Water Supply Scheme in Harischandrapur I & II Block for Installation of FHTC under Malda Division PHE. Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Susanta Pal, JE_Deputation | ORD/000561/2022-2023 | 752/MD | 17/02/2023 | 03/04/2023 | PARIJAT RAY | 31.32 | 25.46 | 81.29 | 77
4 | MALDAH |  | Malda Division | Laying of additional pipe line at various Piped Water Supply Schemes under Harishchandrapur-I & II Block under Malda Division, PHE Dte. | SM/15086 | Augmentation | Acceptance cum formal work order for Laying of additional pipeline for Daulatpur Piped Water Supply Scheme in Harischandrapur II Block for Installation of FHTC under Malda Division PHE. Dte. (Part-II) | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000566/2022-2023 | 757/MD | 17/02/2023 | 19/03/2023 | M/S SABANA CONSTRUCTION | 18.76 | 13.66 | 72.85 | 70
5 | MALDAH |  | Malda Division | Laying of additional pipe line at various Piped Water Supply Schemes under Harishchandrapur-I & II Block under Malda Division, PHE Dte. | SM/15086 | Augmentation | Acceptance cum formal work order for Laying of additional pipeline Konar Piped Water Supply Scheme in Harischandrapur I Block for Installation of FHTC under Malda Division PHE. Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000735/2022-2023 | 1214/MD | 21/03/2023 | 05/05/2023 | M/S. TEWARI CONSTRUCTION | 21.7 | 21.21 | 97.75 | 90
Total | [13 empty] | 105.43 | 93.75 | 88.92